11th MEETING OF THE CONFERENCE OF THE PARTIES

## Quito, Ecuador, 4-9 November 2014

Agenda Item 14.2

| CMS |  |  |
| --- | --- | --- |
|  | ## CONVENTION ON ## MIGRATORY ## SPECIES | Distribution: General UNEP/CMS/COP11/Doc.14.2/Rev.1 15 October 2014 Original: English |

## DRAFT COSTED PROGRAMME OF WORK 2015-2017

Summary:

It is for the first time ever that a costed Programme of Work (POW) for CMS is submitted to the Conference of the Parties. The format used has been cleared by the Standing Committee at its 
40th Meeting (Bonn, November 2012).

The POW should be considered in conjunction with: UNEP/CMS/COP11/Doc.14.3 on the proposed Budget for the triennium 2015-2017

## DRAFT COSTED PROGRAMME OF WORK 2015-2017

(Prepared by the UNEP/CMS Secretariat)

Introduction

- The present document has been prepared in response to call by Parties for greater clarity on the work of the Secretariat and related resource requirements.

- In the period since the Tenth Meeting of the Conference of Parties to CMS (COP10), the Secretariat has given consideration to the format of the costed Programme of Work (POW) and the format is based on the one that is used by CITES.

- The current format has been cleared by the Standing Committee at its 40th Meeting (Bonn, November 2012).

- A detailed list of activities of the Secretariat for 2015-2017 has been developed, based on existing mandates as well as those merging from COP10 and the work required to service the various instruments.

- The detailed list of activities is being grouped into programme areas and the resources (both from the core budget and those to be raised through voluntary contributions) contributing to each Programme area identified. The programme areas identified are as follows:

- Executive Direction and Management;

- Implementation Support;

- Resource Mobilization and Interagency Affairs;

- Information Management, Communication and Outreach;

- Capacity Building;

- Servicing of Governing Bodies and other CMS meetings; and

- Operating Costs.

- For each activity priority ranking has been given. Core activities are activities which the Secretariat will implement during the triennium 2015-2017. Thereafter, and as far as resources permitting, priority will be given to those activities ranked as high followed by those indicated as medium. Little attention will be given to those listed as low.

- Finally for each activity the funding source has been indicated being funds provided through the Budget 2015-2017 as proposed in UNEP/CMS/COP11/Doc.14.3 being Core and/ or through Voluntary Contribution still to be raised. Where no funding source has been indicated means that the activity can be carried out by Human Resources available.

Action requested:

The Conference of the Parties is requested to review and adopt the costed Programme of Work for 2015-2017.

| EXECUTIVE DIRECTION AND MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity No. | Activities | Priority ranking | 2015 |  |  | 2016 |  |  | 2017 |  |  |
|  |  |  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  |  |  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
| 1 | Providing overall management of the Secretariat, including regular Management meetings | Core |  |  |  |  |  |  |  |  |  |
| 2 | Supervising the administrative and financial management of the Secretariat | Core |  |  |  |  |  |  |  |  |  |
| 3 | Representing CMS and/or CMS Family; raising awareness, visibility, etc. | Core |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |
|  | Staff costs: D-1 (0.3), P-5 (0.4), G-6 (0.85), G-4 (0.35) |  | 208.204 |  | 208.204 | 212.368 |  | 212.368 | 216.615 |  | 216.615 |
|  | Grand total |  | 208.204 |  | 208.204 | 212.368 |  | 212.368 | 216.615 |  | 216.615 |
|  | SCENARIO 2 |  |  |  |  |  |  |  |  |  |  |
| 4 | Developing Strategic Plan (Indicators, Companion Volume, etc) | High | 15.000 | 15.000 | 30.000 | 15.000 | 15.000 | 30.000 | 15.000 |  | 15.000 |

IMPLEMENTATION SUPPORT

| Activity No. | Activities | Priority ranking | 2015 |  |  | 2016 |  |  | 2017 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  |  |  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
|  | AQUATIC SPECIES TEAM |  |  |  |  |  |  |  |  |  |  |
| 1 | Supporting implementation activities | High | 6.700 |  | 6.700 | 6.700 |  | 6.700 | 6.600 |  | 6.600 |
| 2 | Implementation of the several Resolutions adopted at COP11 and where relevant COP10 e.g. on Marine Debris, Boat-based Wildlife watching, Bycatch, etc. | High |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Coordinate, promote and facilitate the implementation of: |  |  |  |  |  |  |  |  |  |  |
| 3 | The Atlantic Turtle MoU |  |  |  |  |  |  |  |  |  |  |
|  | Revitalisation of the MoU by organizing a brainstorming meeting in conjunction with Western African Aquatic Mammals MoU | Medium |  | 25.000 | 25.000 |  |  |  |  |  |  |
|  | Supporting implementation | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing 3rd Meeting of Signatories | Medium |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 4 | The Western African Aquatic Mammal MoU |  |  |  |  |  |  |  |  |  |  |
|  | Revitalisation of the MoU by organizing a brainstorming meeting in conjunction with Atlantic Turtle MoU | Medium |  | 25.000 | 25.000 |  |  |  |  |  |  |
|  | Supporting implementation | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing 1st Meeting of Signatories | Medium |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 5 | The Pacific Islands Cetaceans MoU |  |  |  |  |  |  |  |  |  |  |
|  | Outsourcing of the technical coordination | High |  | 25.000 | 25.000 |  | 25.000 | 25.000 |  | 25.000 | 25.000 |
|  | Supporting implementation | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing 4th Meeting of Signatories | High |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 6 | The Mediterranean Monk Seal MoU |  |  |  |  |  |  |  |  |  |  |
|  | Organising meeting to revise the Action Plan | Low |  |  |  |  |  |  |  | 10.000 | 10.000 |
| 7 | The Sharks MoU |  |  |  |  |  |  |  |  |  |  |
|  | Providing in kind support from the CMS Secretariat | High |  |  |  |  |  |  |  |  |  |
|  | Organizing the 2nd Meeting of Signatories (costs of the meeting to be covered by MoU Trust Fund) | High |  |  |  |  |  |  |  |  |  |
| 8 | The Pacific Loggerhead Turtle Action Plan |  |  |  |  |  |  |  |  |  |  |
|  | Initiating and stimulating the implementation of the Action Plan. | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
| 9 | Senior Advisor/IOSEA 12.5 % | High | 20.376 |  | 20.376 | 20.376 |  | 20.376 | 20.376 |  | 20.376 |
|  | AVIAN SPECIES TEAM |  |  |  |  |  |  |  |  |  |  |
| 10 | Supporting implementation activities | High | 6.700 |  | 6.700 | 6.700 |  | 6.700 | 6.600 |  | 6.600 |
| 11 | Implementation of the several Resolutions adopted at COP11 and where relevant COP10 e.g. on illegal hunting and trapping, Bird Poisoning, Landbird Action Plan, etc. | High/ Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Coordinate, promote and facilitate the implementation of: |  |  |  |  |  |  |  |  |  |  |
| 12 | The Aquatic Warbler MoU |  |  |  |  |  |  |  |  |  |  |
|  | Outsourcing of the technical coordination. | High |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |
|  | Supporting implementation. | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing the 3rd Meeting of Signatories. | Medium |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 13 | The Great Bustard MoU |  |  |  |  |  |  |  |  |  |  |
|  | Organizing the 4th Meeting of Signatories. | Medium |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 14 | The Ruddy-headed Goose MoU | Low |  |  |  |  |  |  |  |  |  |
| 15 | The Slender-billed Curlew MoU | Low |  |  |  |  |  |  |  |  |  |
| 16 | The Siberian Crane MoU |  |  |  |  |  |  |  |  |  |  |
|  | Outsourcing of the technical coordination | High |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |
|  | Supporting implementation. | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing the 8th Meeting of Signatories. | Medium |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 17 | The Andean Flamingos MoU |  |  |  |  |  |  |  |  |  |  |
|  | Supporting implementation | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
| 18 | The South American Grassland Birds MoU |  |  |  |  |  |  |  |  |  |  |
|  | Supporting implementation | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
| 19 | The Programme of Work for Migratory Birds and Flyways including organizing meeting of the Working Group | High |  | 50.000 | 50.000 |  | 15.000 | 15.000 |  | 15.000 | 15.000 |
|  | TERRESTRIAL SPECIES TEAM |  |  |  |  |  |  |  |  |  |  |
| 20 | Supporting implementation activities | High | 6.700 |  | 6.700 | 6.700 |  | 6.700 | 6.600 |  | 6.600 |
|  | Implementation of the several Resolutions adopted at COP11 and where relevant COP10 e.g. Argali Action Plan, Guidelines on Mitigating the Impact of Linear Infrastructure and Related Disturbance on Mammals in Central Asia, etc. | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Coordinate, promote and facilitate the implementation of: |  |  |  |  |  |  |  |  |  |  |
| 21 | The Saiga MoU |  |  |  |  |  |  |  |  |  |  |
|  | Finalization of the National Report Forma. | High |  | 15.000 | 15.000 |  |  |  |  |  |  |
|  | Outsourcing of the technical coordination | High |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |
|  | Supporting implementation | High |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing 3rd Meeting of Signatories | High |  | 50.000 | 50.000 |  |  |  |  |  |  |
| 22 | The Bukhara Deer MoU |  |  |  |  |  |  |  |  |  |  |
|  | Supporting implementation. | Medium |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing technical workshop and 2nd Meeting of Signatories | Medium |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 23 | The Western African Elephant MoU |  |  |  |  |  |  |  |  |  |  |
|  | Updating the Medium Term International Work Programme | High |  | 20.000 | 20.000 |  |  |  |  |  |  |
|  | Supporting implementation | High |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing 3rd Meeting of Signatories | High |  |  |  |  | 50.000 | 50.000 |  |  |  |
| 24 | The Huemul Deer MoU | Low |  |  |  |  |  |  |  |  |  |
| 25 | The Gorilla Agreement |  |  |  |  |  |  |  |  |  |  |
|  | Outsourcing of the technical coordination | Low |  | 25.000 | 25.000 |  | 25.000 | 25.000 |  | 25.000 | 25.000 |
|  | Supporting implementation | Low |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Organizing the 3rd Meeting of Parties | Low |  | 50.000 | 50.000 |  |  |  |  |  |  |
| 26 | The Central Asian Mammals Initiative |  |  |  |  |  |  |  |  |  |  |
|  | Coordinating this Initiative on full-time basis | High |  | 51.000 | 51.000 |  | 52.000 | 52.000 |  | 53.000 | 53.000 |
|  | Organize workshops and support implementation of relevant activities on specific issues outlined in the POW | High |  | 100.000 | 100.000 |  | 50.000 | 50.000 |  | 5.000 | 5.000 |
| 27 | The Sahelo/Saharan Mega Fauna Action Plan | Medium |  |  |  |  |  |  |  |  |  |
|  | Organising meeting to update the Action Plan | Medium |  | 60.000 | 60.000 |  |  |  |  |  |  |
|  | SCIENTIFIC ADVISORY SERVICES |  |  |  |  |  |  |  |  |  |  |
|  | Implementation of the several Resolutions adopted at COP11 and where relevant COP10 e.g. Wildlife Crime, Renewable Energy, etc. | High |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
| 28 | Providing scientific advice to the Secretariat and Subsidiary bodies of the Convention | Core |  |  |  |  |  |  |  |  |  |
| 29 | Facilitating the work of the Scientific Council. | Core |  |  |  |  |  |  |  |  |  |
| 30 | Coordinating preparations of review report on the conservation status of species listed on CMS Appendices | High |  | 100.000 | 100.000 |  | 75.000 | 75.000 |  | 25.000 | 25.000 |
| 31 | Coordinating implementation of the Small Grant Programme | High |  | 100.000 | 100.000 |  | 100.000 | 100.000 |  | 100.000 | 100.000 |
| 32 | Coordinate preparation of Atlas on Animal Migration | Medium |  | 750.000 | 750.000 |  | 750.000 | 750.000 |  | 500.000 | 500.000 |
| 33 | Facilitate the implementation of the Programme of Work on Climate Change and prepare progress report to COP12 | High |  |  |  |  |  |  |  |  |  |
|  | Organizing 1st and 2nd meeting | High |  | 50.000 | 50.000 |  |  |  |  | 50.000 | 50.000 |
| 34 | Stimulating the implementation of the Resolution on Ecological Networks particularly in Africa by programme planning in 2015 and a kick-start meeting in 2016 | High |  | 50.000 | 50.000 |  | 200.000 | 200.000 |  | 100.000 | 100.000 |
|  | Total |  | 40.476 | 2.376.000 | 2.416.476 | 40.476 | 2.522.000 | 2.562.476 | 40.176 | 1.738.000 | 1.778.176 |
|  | Staff costs: D-1 (0.1), P-5 (0.255), P-4 (1.85), P-2 (1.15), G-4/5 (1.2) |  | 498.860 |  | 498.860 | 504.757 |  | 504.757 | 514.850 |  | 514.850 |
|  | Grand total |  | 535.336 | 2.376.000 | 2.911.336 | 545.233 | 2.522.000 | 3.067.233 | 555.026 | 1.738.000 | 2.293.026 |
|  | SCENARIO 2 |  |  |  |  |  |  |  |  |  |  |
|  | Supporting implementation activities for: |  |  |  |  |  |  |  |  |  |  |
| 35 | Aquatic Species |  | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 |
| 36 | Avian Species |  | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 |
| 37 | Terrestrial Species |  | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 |
|  | SCENARIO 3 |  |  |  |  |  |  |  |  |  |  |
|  | Supporting implementation activities for: |  |  |  |  |  |  |  |  |  |  |
| 38 | Aquatic Species |  | 10.000 |  |  | 10.000 |  | 10.000 | 10.000 |  | 10.000 |
| 39 | Avian Species |  | 10.000 |  |  | 10.000 |  | 10.000 | 10.000 |  | 10.000 |
| 40 | Terrestrial Species |  | 10.000 |  |  | 10.000 |  | 10.000 | 10.000 |  | 10.000 |

| RESOURCE MOBILIZATION AND INTERAGENCY AFFAIRS |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity No. | Activities | Priority ranking | 2015 |  |  | 2016 |  |  | 2017 |  |  |
|  |  |  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  |  |  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
|  | RESOURCE MOBILIZATION |  |  |  |  |  |  |  |  |  |  |
| 1 | Developing a CMS Resource Assessment and Mobilization Plan | Core |  | 25.000 | 25.000 |  | 25.000 | 25.000 |  |  |  |
| 2 | Implementing the Migratory Species Champion Programme | Core |  | 2.000 | 2.000 |  | 2.000 | 2.000 |  | 2.000 | 2.000 |
| 3 | Developing project proposals | Core |  |  |  |  |  |  |  |  |  |
| 4 | Identifying potential donors, liaise with them on new proposals and/ or report to them ongoing/finalised projects | Core |  |  |  |  |  |  |  |  |  |
| 5 | Pursue partnerships with the Private Sector incl. the development of a strategy as part of the Champion Programme | High |  |  |  |  |  |  |  |  |  |
|  | PROMOTE CMS ISSUES IN UN SYSTEM |  |  |  |  |  |  |  |  |  |  |
|  | Participating in meetings of / with e.g.: |  |  |  |  |  |  |  |  |  |  |
| 6 | Biodiversity Liaison Group (BLG) | High |  |  |  |  |  |  |  |  |  |
| 7 | EMG and IMG Biodiversity Group | Low |  |  |  |  |  |  |  |  |  |
| 8 | UNEP 2015 Strategic Group and Post 2015 process of Sustainable Development Goals | Medium |  |  |  |  |  |  |  |  |  |
| 9 | UNEP MEA Management Team meetings | Medium |  |  |  |  |  |  |  |  |  |
| 10 | Participating in NBSAPs Forum (UNEP, UNDP, CBD led) to provide information on behalf of the CMS Family | High |  |  |  |  |  |  |  |  |  |
| 11 | Global Programme on Oceans (GPO) | Medium |  |  |  |  |  |  |  |  |  |
| 12 | UNEP MEA Focal Points | High |  |  |  |  |  |  |  |  |  |
|  | STRENGTHEN EXISTING COLLABORATION WITH MEAs |  |  |  |  |  |  |  |  |  |  |
| 13 | Coordinating and overseeing the implementation of the Joint Work Plans with CBD, Ramsar and CITES | High |  |  |  |  |  |  |  |  |  |
| 14 | Strengthening the collaboration with UNESCO-WHC, UNFCC, UNCCD and IWC | Medium |  |  |  |  |  |  |  |  |  |
| 15 | Maintaining collaboration with other MEAs e.g. Bern Convention, Cartagena Convention, etc. | Low |  |  |  |  |  |  |  |  |  |
|  | STRENGTHEN EXISTING COLLABORATION WITH IGOs AND CIVIL SOCIETY |  |  |  |  |  |  |  |  |  |  |
| 16 | Strengthening the relationship with e.g. EU, SPREP, IUCN and Civil Society, where appropriate | Medium |  |  |  |  |  |  |  |  |  |
|  | ENGAGEMENT IN NEW STRATEGIC COOPERATIONS |  |  |  |  |  |  |  |  |  |  |
| 17 | Continuing cooperation with IRENA building on results of our joint project. | High |  |  |  |  |  |  |  |  |  |
| 18 | Pursuing joint interests and activities with WWF in the contact of the partnerships agreement | High |  |  |  |  |  |  |  |  |  |
| 19 | Exploring possible engagement of GEF, UNDP, World Bank and others in implementation of CMS. | Medium |  |  |  |  |  |  |  |  |  |
|  | STRENGTENING REGIONAL PRESENCE OF CMS |  |  |  |  |  |  |  |  |  |  |
| 20 | Raising awareness and increasing visibility of CMS and/ or CMS Family, increasing partnerships and networks and mobilizing support for the implementation of CMS in Northern America and the Pacific. | High |  | 45.000 | 45.000 |  | 45.000 | 45.000 |  | 45.000 | 45.000 |
|  | CMS AMBASSADORS |  |  |  |  |  |  |  |  |  |  |
| 21 | Continuing to liaise with the CMS Ambassadors to expand their programme to support CMS and identifying new Ambassadors, as appropriate. | Medium |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |
|  | Total |  |  | 82.000 | 82.000 |  | 82.000 | 82.000 |  | 57.000 | 57.000 |
|  | Staff costs: D-1 (0.1), P-5 (0.12); P-4 (0.35), P-2 (1.37); G-4/5 (0.05) |  | 202.293 |  | 202.293 | 206.339 |  | 206.339 | 211.401 |  | 211.401 |
|  | Grand total |  | 202.293 | 82.000 | 284.293 | 206.339 | 82.000 | 288.339 | 211.401 | 57.000 | 268.401 |

INFORMATION, COMMUNICATION AND OUTREACH

| Activity No. | Activities | Priority ranking | 2015 |  |  | 2016 |  |  | 2017 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  |  |  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
|  | # COMMUNICATION STRATEGY |  |  |  |  |  |  |  |  |  |  |
| 1 | Developing a common Communication Strategy for AEWA and CMS; a first step toward a CMS Family-wide strategy | Core |  | 25.000 | 25.000 |  | 25.000 | 25.000 |  |  |  |
|  | Organising workshops to develop and discuss the Strategy | Core |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  |  |  |
|  | Developing a common branding for the CMS Family | Medium |  |  |  |  | 40.000 | 40.000 |  | 40.000 | 40.000 |
|  | COMMUNICATION, EDUCATION AND PUBLIC AWARENESS (CEPA) |  |  |  |  |  |  |  |  |  |  |
| 2 | Initiating the development of a common CEPA Programme for AEWA and CM | Medium |  |  |  |  |  |  |  |  |  |
|  | Organizing CEPA Workshops to ensure a participatory process | Medium |  |  |  |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
|  | Developing the CEPA Programme | Medium |  |  |  |  |  |  |  | 80.000 | 80.000 |
|  | Developing a CEPA Toolkit | Medium |  |  |  |  | 100.000 | 100.000 |  | 100.000 | 100.000 |
|  | ELECTRONIC INFORMATION TOOLS |  |  |  |  |  |  |  |  |  |  |
| 3 | Maintaining and further developing the CMS Family Website | Core | 6.500 | 3.500 | 10.000 | 6.500 | 3.500 | 10.000 | 6.500 | 3.500 | 10.000 |
| 4 | Maintaining and/ or developing other websites e.g. World Migratory Bird Day | Core |  | 5.000 | 5.000 |  | 5.000 | 5.000 |  | 5.000 | 5.000 |
| 5 | Maintaining and further developing online Workspaces e.g. for the Scientific Council | Core |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |
|  | CAMPAIGNS |  |  |  |  |  |  |  |  |  |  |
| 6 | Organizing the campaigns e.g. World Migratory Bird Day World Wildlife Day, etc. | High |  | 35.000 | 35.000 |  | 35.000 | 35.000 |  | 35.000 | 35.000 |
|  | PRESS AND MEDIA |  |  |  |  |  |  |  |  |  |  |
| 7 | Drafting of Press Releases, Op-Eds, Articles, etc. including responding to Media requests | Core |  |  |  |  |  |  |  |  |  |
| 8 | Furthering the use of Social Media to increase the visibility of the CMS Family | High |  | 50.000 | 50.000 |  | 50.000 | 50.000 |  | 50.000 | 50.000 |
| 9 | Improving the use of Multi Media | Medium |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |
|  | PUBLICATIONS |  |  |  |  |  |  |  |  |  |  |
| 10 | Organising and supervising the printing of Publications | Core |  | 20.000 | 20.000 |  | 20.000 | 20.000 |  | 20.000 | 20.000 |
|  | INFORMATION MANAGEMENT |  |  |  |  |  |  |  |  |  |  |
| 11 | Analysing and synthesizing of National Reports | Core |  |  |  |  |  |  |  | 50.000 | 50.000 |
| 12 | Further developing and maintaining the Online Reporting System incl. Analytical Tool | High |  | 50.000 | 50.000 |  | 50.000 | 50.000 | 50.000 |  | 50.000 |
| 13 | Managing in- and outgoing mail and keeping the contact database up to date | Core |  |  |  |  |  |  |  |  |  |
|  | Total |  | 6.500 | 258.500 | 265.000 | 6.500 | 448.500 | 455.000 | 6.500 | 453.000 | 510.000 |
|  | Staff Costs: D-1(0.2), P-5 (0.05), P-4 (0.11), P-2 (0.81), G-7 (0.85), G 4 (0.5) |  | 234.199 |  | 234.199 | 238.883 |  | 238.883 | 243.660 |  | 243.660 |
|  | Grand total |  | 240.699 | 258.500 | 499.199 | 245.383 | 448.500 | 693.883 | 250.160 | 453.000 | 730.660 |
|  | Please note that Staff time of AEWA has not been included in the Staff Costs. |  |  |  |  |  |  |  |  |  |  |
|  | SCENARIO 2 |  |  |  |  |  |  |  |  |  |  |
| 15 | Programme Officer 25 % |  |  |  |  | 29.784 |  | 29.784 | 30.380 |  | 30.380 |
| 16 | Analysis of National Reports |  |  |  |  |  |  |  | 50.000 |  | 50.000 |
| 17 | Communication and Outreach activities |  | 5.800 |  | 5.800 |  |  |  |  |  |  |
|  | SCENARIO 3 |  |  |  |  |  |  |  |  |  |  |
| 18 | Communication and Outreach activities |  | 10.000 |  | 10.000 | 10.000 |  | 10.000 | 10.000 |  | 10.000 |

CAPACITY BUILDING

| Activity No. | Activities | Priority ranking | 2015 |  |  | 2016 |  |  | 2017 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  |  |  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
|  | CAPACITY BUILDING |  |  |  |  |  |  |  |  |  |  |
| 1 | Implementing the Capacity Building Strategy 2015-2017 by identifying specific needs, training the Trainers, developing materials and organizing capacity building workshops in particularly African, Asia, Latin America and the Pacific, etc. | Core |  | 200.000 | 200.000 |  | 150.000 | 150.000 |  | 150.000 | 150.000 |
| 2 | Stimulating the use of E-community to increase communication between National Focal Points. | Core |  |  |  |  |  |  |  |  |  |
| 3 | Evaluating the usefulness of the existing capacity building tool e.g. National Focal Point Manual, E-community, etc. | High |  |  |  |  |  |  |  |  |  |
| 4 | REGIONAL MEETINGS |  |  |  |  |  |  |  |  |  |  |
|  | Organizing and servicing preparatory meeting for COP12 in Africa, Asia, Latin America and the Pacific. | High |  |  |  |  | 100.000 | 100.000 |  | 100.000 | 100.000 |
|  | RECRUITMENT OF NEW PARTIES |  |  |  |  |  |  |  |  |  |  |
| 5 | Developing a Strategy to recruit new Parties. | Core |  |  |  |  |  |  |  |  |  |
| 6 | Liaising with non-Party Range States to provide them with the necessary information to make an informed decision to join CMS and/ or one or more of its instruments. | Core |  |  |  |  |  |  |  |  |  |
|  | Assisting countries to accede to CMS. | Core |  | 30.000 | 30.000 |  | 30.000 | 30.000 |  | 30.000 | 30.000 |
|  | Total |  |  | 230.000 | 230.000 |  | 280.000 | 280.000 |  | 280.000 | 280.000 |
|  | Staff Costs: D-1(0.1), P-5(0.05), P-4(0.74), P-2 (0.12), G-4 (0.4) |  | 167.921 |  | 167.921 | 171.279 |  | 171.279 | 174.704 |  | 174.704 |
|  | Grand total |  | 167.921 | 230.000 | 397.921 | 171.279 | 280.000 | 451.279 | 174.704 | 280.000 | 454.704 |
|  | SCENARIO 2 |  |  |  |  |  |  |  |  |  |  |
| 7 | Capacity building activities |  | 5.000 |  | 5.000 | 5.000 |  | 5.000 | 5.000 |  | 5.000 |
|  | SCENARIO 3 |  |  |  |  |  |  |  |  |  |  |
| 8 | Capacity building activities |  | 5.800 |  | 5.800 | 5.800 |  | 5.800 | 5.800 |  | 5.800 |

SERVICING OF GOVERNING BODIES AND OTHER CMS MEETINGS

| Activity No. | Activities | Priority ranking | 2015 |  |  | 2016 |  |  | 2017 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  |  |  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
|  | Servicing and organising (logistically as well as substantively) meetings of the following bodies: |  |  |  |  |  |  |  |  |  |  |
| 1 | The 12th Meeting of the Conference of Parties (including hiring Conference Officer, support for funded delegates, contracting ENB and organization of High Level Segment). | Core |  |  |  |  |  |  | 342.771 | 500.000 | 842.771 |
| 2 | The Standing Committee including maintaining regular contact. | Core | 21.649 |  | 21.649 | 22.082 |  | 22.082 |  |  |  |
| 3 | The Scientific Council including maintaining regular contact. | Core | 50.408 | 10.000 | 60.408 | 50.408 | 10.000 | 60.408 |  | 60.000 | 60.000 |
| 4 | Servicing and organizing (logistically) of any other CMS meeting e.g. Meeting of Signatories to MoUs, Meeting of Parties to the Gorilla Agreement, Workshops, etc. | Core |  |  |  |  |  |  |  |  |  |
|  | Total |  | 72.057 | 10.000 | 82.057 | 72.490 | 10.000 | 82.490 | 342.771 | 560.000 | 902.771 |
|  | Staff costs: D1 (0.17), P5 (0.25), P4 (0.8), P2 (0.8) and GS 6/7 (0.3); GS 4/5 (2.5) |  | 441.404 |  | 441.404 | 450.231 |  | 450.231 | 459.235 |  | 459.235 |
|  | Grand total |  | 513.461 | 10.000 | 523.461 | 522.721 | 10.000 | 532.721 | 802.006 | 560.000 | 1.362.006 |

OPERATING COSTS

| Activity No. | Activities | Priority ranking | 2015 |  |  | 2016 |  |  | 2017 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  |  |  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
| 1 | Contractual services (translation etc.). | Core | 74.285 | 10.000 | 84.285 | 74.285 | 10.000 | 84.285 | 92.326 |  | 107.326 |
| 2 | Secretariat Travel | Core | 66.326 | 15.000 | 81.326 | 66.326 | 15.000 | 81.326 | 63.723 |  | 73.723 |
| 3 | Staff development | Core | 15.400 |  | 15.400 | 10.000 |  | 10.000 | 10.000 |  | 10.000 |
| 4 | Procurement of non-expendable equipment and expendable office supplies | Core | 26.957 | 10.000 | 36.957 | 27.496 | 10.000 | 37.496 | 28.044 | 15.000 | 38.044 |
| 5 | Information Technology Services | Core | 74.285 |  | 74.285 | 75.771 |  | 75.771 | 77.286 | 10.000 | 77.286 |
| 6 | Information and document production | Core | 13.266 | 15.000 | 28.266 | 13.266 | 15.000 | 28.266 | 13.266 | 60.000 | 73.266 |
| 7 | Communication and Courier Services | Core | 17.935 |  | 17.935 | 17.935 |  | 17.935 | 17.983 |  | 17.983 |
| 8 | Miscellaneous expenses and hospitality | Core | 3.821 |  | 3.821 | 3.887 |  | 3.887 | 3.954 |  | 3.954 |
|  | Total |  | 292.275 | 50.000 | 342.275 | 288.966 | 50.000 | 338.966 | 306.582 | 95.000 | 401.582 |
|  | Staff costs |  |  |  |  |  |  |  |  |  |  |
|  | Grand total |  | 292.275 | 50.000 | 342.275 | 288.966 | 50.000 | 338.966 | 306.582 | 95.000 | 401.582 |

| SUMMARY OF TOTAL COSTS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities | 2015 |  |  | 2016 |  |  | 2017 |  |  |
|  | Source of funding |  | Total funding | Source of funding |  | Total funding | Source of funding |  | Total funding |
|  | Core | Volycon |  | Core | Volycon |  | Core | Volycon |  |
| Executive Direction and Management | 208,204 | - | 208,204 | 212,368 | - | 212,368 | 216,615 | - | 216,615 |
| Implementation Support | 535,336 | 2,376,000 | 2,911,336 | 545,233 | 2,522,000 | 3,067,233 | 555,026 | 1,738,000 | 2,293,026 |
| Servicing governing bodies and other meetings | 513,461 | 10,000 | 523,461 | 522,721 | 10,000 | 532,721 | 802,006 | 560,000 | 1,362,006 |
| Resource Mobilization and Interagency Affairs | 202,293 | 82,000 | 284,293 | 206,339 | 82,000 | 288,339 | 210,465 | 57,000 | 267,465 |
| Information Management Communication and Outreach | 240,699 | 258,500 | 499,199 | 245,383 | 448,500 | 693,883 | 250,160 | 453,500 | 703,660 |
| Capacity building | 167,921 | 230,000 | 397,921 | 171,279 | 280,000 | 451,279 | 174,704 | 280,000 | 454,704 |
| Operating costs | 292,275 | 50,000 | 342,275 | 288,966 | 50,000 | 338,966 | 306,582 | 95,000 | 401,582 |
| Total | 2,160,190 | 3,006,500 | 5,166,690 | 2,192,288 | 3,392,500 | 5,584,788 | 2,515,560 | 3,183,500 | 5,699,060 |
| Programme support costs | 280,825 | 390,845 | 671,670 | 284,997 | 441,025 | 726,022 | 327,023 | 413,855 | 740,878 |
| Grand total | 2,441,014 | 3,397,345 | 5,838,359 | 2,477,285 | 3,833,525 | 6,310,810 | 2,842,582 | 3,597,355 | 6,439,937 |
| Please note that the figures presented here a slightly deviating from those of the budget proposal due to the fact that figures are rounded up. |  |  |  |  |  |  |  |  |  |