# 1st Meeting of the Sessional Committee of the

# CMS Scientific Council (ScC-SC1)

# Bonn, Germany, 18 – 21 April 2016

UNEP/CMS/ScC-SC1/Doc.10.1.3.1

PROGRAMME OF WORK FOR THE AFRICAN-EURASIAN MIGRATORY LANDBIRDS ACTION PLAN

(Prepared by the African-Eurasian Migratory Landbirds Working Group)

Summary

The African-Eurasian Migratory Landbirds Working Group held its second meeting in Abidjan (Côte d’Ivoire) in November 2015 and discussed a Programme of Work (POW) to implement the Landbirds Action Plan during the period 2016-2020. The POW includes priority activities, lead organizations, time-frame and estimated cost of each activity. The POW contributes to the achievement of the Sustainable Development Goals (SDGs) particularly Goal 15 on sustainable management of ecosystems, combating desertification and halting of biodiversity loss. Since the Landbirds Working Group operates under the umbrella of the Scientific Council, the POW is submitted to the Sessional Committee for endorsement.

Programme of Work (POW) for the African-Eurasian Migratory Landbirds Action Plan

- Resolution 11.17 adopted the African-Eurasian Migratory Landbirds Action Plan (AEMLAP) and requested the continuation of the associated working group until COP12 to facilitate and monitor the implementation of the Action Plan. The working group operates under the umbrella of the Scientific Council.

- The African-Eurasian Migratory Landbirds Working Group (AEMLWG) met in Abidjan (Côte d’Ivoire) on the 25-27 November and discussed a draft Programme of Work for the period 2016-2020. The document has been compiled by the Working Group Coordinator and includes priority actions to be undertaken, lead organizations, time frame and estimated cost.

- The draft POW is appended to this cover note as Annex 1 and is submitted to the Sessional Committee of the Scientific Council for its consideration.

- Once finalized, it is intended to submit this Programme of Work to COP12 in 2017 in the Philippines for adoption.

Action requested:

The Sessional Committee of the Scientific Council is invited to take note of the draft Programme of Work and provide comments and suggestions to the document if needed.

Annex 1

DRAFT PROGRAMME OF WORK FOR THE IMPLEMENTATION OF THE AFRICAN-EURASIAN MIGRATORY LANDBIRDS ACTION PLAN (AEMLAP)

February 2016

(Prepared by the African Eurasian Migratory Landbirds Working Group)

1.0 INTRODUCTION

- The priority actions in this Programme of Work (POW) were identified during the second meeting of the African Eurasian Migratory Landbirds Working Group (AEMLWG) which took place in Côte d’Ivoire, Abidjan in November, 2015.

- The activities were agreed taking into consideration: a) thematic areas and priority actions in the African Eurasian Migratory Land Birds Action Plan (AEMLAP); b) ongoing regional or international efforts contributing to the conservation of migratory landbirds; and c) priority regions within the African Eurasian flyway.

- The implementation of the POW seeks collaboration with existing programmes for greater impact.

- This POW contributes to the achievement of the Sustainable Development Goals (SDGs) particularly Goal 15 on sustainable management of ecosystems, combating desertification and halting of biodiversity loss.  Specifically, the actions of the POW are relevant to targets 2, 5, 7 and 9c of this goal.

- The budget estimates are only indicative and are mainly aimed at undertaking preparatory activities to identify cogent actions for conservation of landbirds as per the AEMLAP thematic areas. Voluntary contributions are invited to realize the implementation of this POW.

- The implementation of the POW will require coordination. A budgetary estimate for the AEMLWG Coordinator is €100,000 per year, including staff time, administrative support and travels.

- The POW will be presented at the meeting of the Sessional Committee of the Scientific Council, 18-21 April 2016.

ACRONYMS

AEWA		African Eurasian Waterbird Agreement

APLORI	Anastasios P. Leventis Ornithological Research Institute (Nigeria)

BLI		BirdLife International

CMS		Convention on the Conservation of Migratory Species of Wild Animals

DD		Doğa Derneği, the BirdLife partner in Turkey

EU		European Union

EURING	European Union for Bird Ringing

EURO SAP	European Union Species Action Plan

FACE		European Federation of Associations for Hunting and Conservation

FAO 		Food and Agriculture Organization

GREPOM	Groupe de Recherche pour la Protection des Oiseaux au Maroc

IAR		Institute of Avian Research “Vogelwarte Helgoland” (Germany)

IUCN		The International Union for Conservation of Nature

IWC		International Waterbird Census

LPO		Ligue pour la Protection des Oiseaux (France)

LIFE 		EU funding instrument for the environment and climate action

MAVA	MAVA Foundation (Maja, André, Vera, and Daria, Luc Hoffmann’s four children)

MME		BirdLife partner in Hungary

MSB		Migratory Soaring Birds Project

MOU		Memorandum of Understanding

NCF		Nigeria Conservation Foundation

ONCFS	Office National de la Chasse et de la Faune Sauvage (France)

OTOP		Polish Society for the Protection of Birds

RSPB		The Royal Society for the Protection of Birds (UK)

SAFRING	South African Bird Ringing Unit

SEO		Spanish Ornithological Society

SPEA		Portuguese Society for the Study of Birds

TBC		To be confirmed

UNCCD	United Nations Convention on Combating Desertification

UNDP		United Nations Development Programme

UNEP		United Nation Environment Programme

2.0 PROGRAMME OF WORK MATRIX

| No. | Thematic Area | Region | Action | Lead organizations | Partners | Time Frame | Budget Estimates |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Migratory Land birds habitat conservation | East Atlantic Flyway and West Africa | Hold a workshop on land use change for and in the West African region | RSPB/NCF/CMS Secretariat | FAO/ UNEP/ UNDP/ UNCCD | 2016 (Nov) | €40,000 |
|  |  |  | Seek synergies with relevant regional workshops and meetings (e.g. African Congress for Conservation Biology, Morocco, Sept 2016) | RSPB/IAR | UNCCD | 2016 – 2017 | €20,000 |
|  |  |  | Support the development and implementation of pilot projects in West Africa that address key aspects of sustainable land use | TBC | TBC | 2017 – 2019 | TBC |
|  | Migratory Land birds habitat conservation | Black Sea-Rift Valley/Red Sea-Eastern Africa Flyway | Promote the use of the CMS/ Migratory Soaring Birds Project (MSB) agricultural guidelines (Bird poisoning, agrochemicals and sustainable agriculture) within the region Seek and create synergies with AEWA and the Raptors MOU | BLI | International Center for the Study of Bird Migration (Israel), AEWA, Raptors MOU, MSB | 2016 - 2017 | €5,000 |
|  | Migratory Land birds habitat conservation | Aquatic Warbler flyway (Senegal, Mauritania, Mali, South East Europe) | Seek synergies with the Aquatic Warbler MOU Investigate habitat requirements of the Aquatic Warbler that could be shared by other species | OTOP | Aquatic Warbler Conservation Team | 2016 - 2017 | €3,000 |
|  | Migratory Land birds habitat conservation | Central and South Asia | Identify stop-over and wintering sites for migratory landbirds | Bombay Natural History Society | CMS Focal points | 2016 – 2020 | €10,000 |
|  | Migratory Land birds habitat conservation | Sahara-Sahel | Identify and enhance conservation of the stop-over sites immediately to the north and south of the Sahara (including through data collection and seeking linkages with relevant stakeholders) | TBC | Mediterranean Task Force on Illegal Killing of Birds, BLI/MAVA capacity building project, UNCCD, Great Green Wall Initiative, AEWA, Wetlands International (through IWC) | Up to 2017 | €30,000 |
|  | Species conservation actions | Russia and East Asia | Develop an Action Plan for the Yellow Breasted Bunting (YBB), including a regional monitoring scheme and addressing illegal killing | BirdLife Asia, Russia, China and Japan through bilateral relations | TBC | 2016 - 2017 | TBC |
|  | Species conservation actions | East Atlantic Flyway and West Africa plus Central Asia | Completion and implementation of the European Turtle Dove Action Plan | RSPB | LIFE+ EURO SAP Project, BLI partners: DD, GREPOM, LPO, RSPB, SEO, SPEA. Other Partners: FACE, ONCFS | 2016- 2018 | €27,900 (SAP planning workshop) |
|  | Species conservation actions | East Atlantic Flyway and West Africa plus Central Asia | Completion and implementation of the European Roller Action Plan | BLI | MME | 2016- 2017 | TBC |
|  | Species conservation actions | Cross-cutting theme for the African Eurasian Flyway | Update and review the AEMLAP annexes (reflecting the 2015 IUCN Red List changes and nomenclature) | CMS/BLI | IUCN | July 2016 | Zero |
|  | Species conservation actions: monitoring | Cross-cutting theme for the African Eurasian Flyway | Support implementation of existing reporting platforms, data gathering using citizens science, tagging, ringing | TBC | EURING, SAFRING | 2016- 2020 | € 1,000 |
|  | Collisions with man-made infrastructure (with priority in the energy sector) | Black Sea-Rift Valley/Red Sea-Eastern Africa | Promote the use of CMS renewable energy and power line guidelines in the region and seek and create synergies with the CMS Energy Task Force | BLI (Africa and Middle East), CMS Parties/Focal points | Energy Task Force | 2016- 2017 | € 5,000 |
|  | Outreach and public awareness | Cross cutting theme for the African Eurasian Flyway | Operationalize the Friends of the Landbirds Action Plan (FLAP) project | BLI | Spring Alive Project of BirdLife International | 2016 | €10,000 |
|  | Outreach and public awareness: education/capacity building for landbirds conservation | Cross cutting theme for the African Eurasian Flyway | Improve capacity for migratory landbirds conservation within the region | TBC | APLORI, University of Abidjan | 2016 - 2020 | €60,000 |
|  | Outreach and public awareness | Cross cutting theme for the African Eurasian Flyway | Create a workspace for information exchange and an online mechanism/template to undertake regular reporting on AEMLAP implementation | CMS Secretariat |  | 2016 – 2017 | Zero |

http://www.cms.int/saiga/sites/default/files/document/CMS-StC41-doc_19_1_aemlap_e.pdf

http://www.un.org/sustainabledevelopment/biodiversity/

Joint actions or partnerships with the African-Eurasian Migratory Landbirds Working Group to be developed as opportunities arise, especially when AEWA and/or Raptor MOU have activities which could also be beneficial to species, sites or habitats used by migratory landbirds

These are sites that are used as stop overs by birds before or after crossing the Sahara in Africa

Capacity for migratory landbirds could be through training on monitoring, bird identification provision of ornithological equipment, protected area identification and management, training of policy makers within government