##### mt-iosea/ss.2/dOC 7 / annex 2

##### ANNOTATED Conservation and Management Plan: SOUTH-EAST ASIA + AUSTRALIA*

##### (*also includes the United States of America, a Signatory State that is not a Range State)

##### Objective 1.  Reduce direct and indirect causes of marine turtle mortality

| Programme | Activity | Implementation progress to date | Further specific actions | Priority |
| --- | --- | --- | --- | --- |
| 1.1 Identify and document the threats to marine turtle populations and their habitats | a) Collate and organise existing data on threats to marine turtle populations | AUS: Threats identified during development of the Draft Turtle Recovery Plan include: incidental catch in fisheries, predation by native and introduced animals, coastal development, decline in water quality, marine debris, loss of habitat, traditional harvesting, and impacts from shark control programmes (beach netting and drum lines). Other threats identified, but yet to be included in the draft Recovery Plan, include mortality in neighbouring States and boat strikes. [IDN]: Data on threats have been compiled specifically in marine protected areas such as Keulauan Sinbu National Park, Alas Punoo, Theru Betiri NP, Panguinbahau, Cikepuh, Seqamat, Derawau and Irian Jaya. KHM: Existing threats were identified and discussed in Sept 2002 in a WWF-funded workshop. PHL: Information on threats gathered in the course of conducting habitat surveys, but needs to be collated and organized. VNM: Programme completed, and a series of recommendations have been delivered so that future studies can fill in the gaps (see IUCN and TRAFFIC survey reports). [THA]: Incidental catch from fishing gears and invasion of nesting beaches. MMR: Conservation and research activities (by DoF) limited to Ayeyarwady Delta region, Turtle Island and nesting beach. USA: Recovery plans for 5 species of sea turtle in the Pacific (excluding Flatback) completed in 1998. Plans include threat assessment. | AUS: Australia will continue to identify threats to marine turtle and analyse data. [IDN]: Monitoring of nesting sites. | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] 2 MMR USA 3 All |
|  | b) Establish baseline data collection and monitoring programmes to gather information on the nature and magnitude of threats | AUS: A marine debris database has been established in the northern region of Australia (recording amount, type and probable origin of marine debris) from a range of monitoring sites. Turtle entanglement reports have been collected from Cape Arhnem from 1996 by the Dhimurra Land Management Council with WWF funding. A net coding system to identify net types to specific fisheries has been established. [IDN]: Baseline data on threats have been documented. PHL: Baseline data can be culled from habitat surveys on nature of threats, but do not include magnitude. VNM: KHM: [THA]: Set up sea turtle stranding network. MMR: USA: Beach patrols for nesting and strandings. Fishery observers in pelagic longline, lobster trap, and purse seine fisheries. |  | AUS [IDN] 2 PHL 2 VNM KHM [THA] 1 MMR USA 1 All |
|  | c) Determine those populations affected by traditional and direct harvest, incidental capture in fisheries, and other sources of mortality | AUS: Australia has identified areas and populations subject to traditional take. The EPBC Act requires reporting of all interactions, and many fisheries require logbooks to be kept recording turtle interactions. [IDN]: No direct harvest since all the species have been protected. PHL: Has identified populations affected by traditional harvests, but data on mortalities from incidental capture in fisheries are poor. VNM: KHM: [THA]: No direct harvest or incidental capture in fisheries reported. MMR: USA: Achieved through programmes conducted in 1.1.b., plus genetic characterisation to identify affected stocks. |  | AUS [IDN] 1 PHL 2 VNM KHM 3 [THA] 1 MMR USA 1 All |
| 1.2 Determine and apply best practice approaches to minimising those threats to marine turtle populations and their habitats | Identify and document best practice protocols for conserving and managing marine turtle populations within the region | AUS: Australia identified and analysed a range of protocols for the conservation and management of marine turtles during the development of the draft Recovery Plan. [IDN]: All six species are protected by government regulation. PHL: ICDP approach is being applied in Turtle Islands, but needs strengthening. VNM: Programme 1.2 is under way; discussions have begun (i.e. National Action Plan workshop and Steering Committee meeting to develop best management practices). Awareness-raising campaigns are under way and more will be organised for 2003. KHM: [THA]: MMR: Follows the ASEAN region protocol: the most adapted practices are hatcheries and tagging. USA: Partial implementation: standardized and documented procedures developed and used for genetic sampling and analysis, standard and satellite tagging, nesting beach monitoring, reduction of turtle bycatch and mortality in longline and trawl fisheries. MoU Secretariat: Plans have been drawn up to include examples on the IOSEA Web site, under development. | AUS: As mitigation measures are discovered, these will be tested and applied, if appropriate, in Australia’s longline fisheries. [IDN]: Review Act # 5 of 1990. | AUS [IDN] 2 PHL 2 VNM KHM 2 [THA] MMR USA 2 All |
|  | b) Adapt and adopt the best conservation and management practices for marine turtle populations | AUS: Many controls have been in place in Australia for years, including placing rookeries in non-traditional land in protection areas, such as the GBRMP protected feeding areas, Ashmore Reef Marine Reserve, Coral Sea Natural Nature Reserve. Also, compulsory introduction of Turtle Excluder Devices (TEDs) in the East Coast Trawl Fishery, the Northern Prawn Fishery and the Torres Prawn Fishery. [IDN]: TEDs have been announced based on decree by the Ministry of Agriculture, 1982. PHL: ICDP approach being applied in Turtle Islands, but needs strengthening VNM: KHM: [THA]: Nesting beaches are protected; all eggs are incubated; laws and enforcement have been enhanced. MMR: USA: Identified practices have been implemented by researchers through permits and by fishermen and the public through regulation. | [IDN]: Implement the Action Plan’s provisions regarding use of TEDs. | AUS [IDN] 1 PHL 1 VNM KHM 2 [THA] MMR USA 2 All |
| 1.3 Implement programmes to correct adverse economic incentives that threaten marine turtle populations | Conduct socio-economic studies among communities that interact with marine turtles and their habitats | AUS: Some studies have been conducted, however these have mostly been by graduate and undergraduate students. [IDN]: Together with WWF, much socio-economic research has been completed in areas such as Bali where the largest amount of illegal consumption occurs. USA: Studies done for Hawaiian and Pacific Islanders with a historical exploitation of sea turtles, and for longline fishermen affected by sea turtle protective regulations. PHL, VNM, KHM, [THA], MMR: | [IDN]: Identify suitable alternative livelihoods. | AUS [IDN] 1 PHL 2 VNM KHM 1 [THA] MMR USA 3 All |
|  | Identify desired modifications to the economic incentives in order to reduce threats and mortality, and develop programmes to implement the modifications | AUS: Australia has completely banned trade in turtle parts and products. Promotion of eco-tourism in areas where turtle rookeries are located as alternative livelihoods and awareness-raising measures. [IDN]: Harvest and trade has been prohibited based on Government regulation No. 7/99. VNM: Trade banned in turtle parts and products as of 2002. USA: Regulatory approach has been taken rather than a “re-incentive” approach. PHL, KHM, [THA], MMR: | [IDN]: Species-based eco-tourism. | AUS [IDN] 1 PHL 1 VNM KHM 2 [THA] MMR USA 3 All |
|  | Identify resources and sources of funding for the programmes | AUS: Australia’s National Heritage Trust has funding available on an application basis for such programmes. [IDN]: Tagging, head starting, nesting, satellite tracking and mtDNA have been conducted through the annual budget and in collaboration with NGOs. KHM: WWF-Indochina sponsorship. PHL: Funding from WWF, DFID, UK Embassy in Manila, WWF-US, USAID, WWF-International, Packard Foundation. [THA]: Government funding. MMR: VNM: DANIDA has been a key supporter of marine turtle conservation programmes. USA: Programmes are funded by Government and granting sources. | [IDN]: Continued support through proposed annual budget. | AUS [IDN] 1 PHL 1 VNM KHM 1 [THA] 2 MMR USA 3 All |
| 1.4 Reduce to the greatest extent practicable the incidental capture and mortality of marine turtles in the course of fishing activities | Develop and use gear, devices and techniques to minimise incidental capture of marine turtles in fisheries, such as devices that effectively allow the escape of marine turtles, and spatial and seasonal closures | AUS: Use of Turtle Excluder Devices (TEDs) is mandatory in Northern Prawn, Torres Prawn and East Coast Trawl Fisheries. Port workshops to educate fishers on the benefits of TEDs and how they work. Seasonal and permanent closures over seagrass beds in Northern Prawn Fishery. Permanent fishery closure within Coral Sea Natural Nature Reserve, closures of areas within the GBRMP ‘green areas’ to protect animals and habitat, as well as establishing Dugong Protection Areas covering important seagrass beds and prohibiting gillnet within. [IDN]: Routine patrols, monitoring, public awareness have been conducted in the local fisheries to best practice standards. PHL: Committed to experiment and apply TED through ASEAN MoU but no progress in implementation due to lack of resources. Marine protected areas established which prohibit fishing in designated zones. Fisheries code prohibits commercial vessels (>3 gross tons) to operate within municipal waters (15 km from shore) but many municipalities have no capacity to enforce. VNM: Programme in early stages of implementation. Following initial research of TEDs by RIMF and SEAFDEC, little work has been conducted. However, recent talks with RIMF staff (10 Jan 2003) have identified specific areas where pilot studies might be conducted. KHM: [THA]: Enforcement of use of TEDs in shrimp trawls. MMR: Spatial closures of fishing activities, seasonal closure of fishing activities USA: Turtle Excluder Devices (TEDs) are required in U.S. shrimp trawl fisheries. Pelagic longline gear modifications to reduce turtle bycatch have been experimented with and partially implemented. Pelagic longline area closures have been used to minimize sea turtle interactions. | AUS: Identification of other fisheries that may be candidates for the use of TEDs; review of bycatch Action Plans; participation in the US Marine Turtle bycatch Workshop in February 2003, Seattle. Projects to: Coordinate via email a team of sea turtle scientists, industry representatives, fisheries management and government officials and NGO represent-atives to determine suitable research components; Test a selection of dipnets, line-cutters and de-hookers in the Australian pelagic longline fisheries; Prepare a video outlining sea turtle handling and logbook data collection guidelines for distribution to all Australian pelagic longline vessels; Collect biological data and samples by trained volunteer fishermen to be used in national and international research projects, including research using morphologi-cal measures, conventional tagging, PIT tagging, satellite and archival tagging, genetic sampling, and fishing operational modifications in a specialist sea turtle logbook. | AUS [IDN] 1 PHL 2 VNM KHM 2 [THA] 2 MMR USA 1 All |
|  |  |  | Port workshops covering sea turtle conservation awareness, sea turtle handling and logbook data collection. [IDN]: Increase public awareness, particularly fishers. |  |
|  | Develop procedures and training programmes to promote implementation of these measures, such as vessel monitoring systems and inspections at sea, in port and at landing sites, and national on-board observer programmes | AUS: Surveillance and enforcement activities by Customs, Navy, National Parks and Fisheries officers. Non-regulatory action includes: (1) East Coast Trawl Fishery Code of Practice – no trawling within 1 mile of major turtle nesting area; (2) Code of conduct for the Eastern Tuna and Billfish Fishery which identifies actions for reducing interactions with turtles, amongst other species. [IDN]: Training of enforcement officers has been conducted by the Ministry of Marine and Fisheries; CITES training is also conducted by Ministry of Forestry. PHL: PCP-PAWB of DENR has an established training sea turtle conservation programme with brief topic on turtle rescues and resuscitation. WWF funds and facilitates volunteer training for Bantay dagat (Sea Watch) to deputize community enforcement groups. VNM: KHM: [THA]: Training to promote and support the use of TED by fishermen. MMR: Fishing inspection and catch monitoring system. USA: Training programmes for TEDs and longline practices have been implemented. |  | AUS [IDN] 2 PHL 2 VNM KHM 3 [THA] 3 MMR USA 1 All |
|  | Exchange information and, upon request, provide technical assistance to other signatory States to promote these activities | [IDN]: No data. PHL: Willing to share experience and technical assistance. USA: Has an active programme to exchange TED technical information with all interested countries. The U.S. has also recently started programmes to seek collaboration and to share information on longline sea turtle bycatch. AUS, VNM, KHM, [THA], MMR: |  | AUS [IDN] 2 PHL 2 VNM KHM 3 [THA] MMR USA 1 All |
|  | Liaise and coordinate with fisheries industries and fisheries management organisations to develop and implement incidental capture mitigation mechanisms in national waters and on the high seas | AUS: Australian representatives attended the 2nd International Fisheries Forum which brought together fishermen, industry associations, fisheries managers, government officials, gear technologists and biologists to discuss solutions to the problem of seabird and turtle bycatch in longline fisheries. [IDN]: A steering committee on fisheries has been established to monitor bycatch. PHL: MoA among 6 government agencies with WWF for on-going environmental enforcement crusade to build and enhance capacity to enforce fisheries and relevant environmental laws. VNM: KHM: [THA]: Training programme of the Department of Fisheries. USA: 1.4.a., b., and c. are all implemented through involvement of fisheries industries and management. |  | AUS [IDN] 1 PHL 2 VNM KHM [THA] 2 MMR USA 1 All |
|  | Support the UN General Assembly resolution 46/215 concerning the moratorium on the use of large-scale driftnets on the high seas | AUS: Fully implemented since 1986. [IDN]: Fully supports the resolution by implementing routine patrols and law enforcement. PHL: It is possible that drift gillnets are still operated in some areas (subject to further information). USA: U.S. implementation includes active enforcement patrols. VNM, KHM, [THA], MMR: | [IDN]: implement the Resolution. | AUS [IDN] 1 PHL 1 VNM KHM [THA] 2 MMR USA 2 All |
|  | Develop and implement net retention and recycling schemes to minimise the disposal of fishing gear at sea and on beaches | AUS: bycatch Action Plans in place for every Commonwealth-managed fishery. Strategic assessment process underway for every Commonwealth-managed fishery and State fisheries with an export component. VMS used on all vessels in Northern Prawn Fishery, Southern and Western Tuna and Billfish Fishery and Eastern Tuna and Billfish Fishery. Establishment of an independent scientific monitoring programme in the South East Trawl and non-trawl fishery and the Great Australian Bight Fishery. Research programmes and surveys conducted by independent scientific agencies on certain fisheries. Development of SeaNet extension programme including training, videos to assist fisherman with mitigation and encourage environmental best practice for industry. Established compliance and enforcement programme including at sea inspections, flights and port inspections. [IDN]: Has already regulated based on establishment of Act No. 9/1987. PHL: WWF project on blue crab fisheries in the Visayas encourages fishing communities and local government to address issue of discarded crab gillnets. VNM: KHM: [THA]: Education and awareness campaign for conservation of environment. MMR: USA: Some non-Federal governmental programmes in place. | [IDN]: Strengthen role of officers in seaports. | AUS [IDN] PHL 1 VNM KHM 1 [THA] 3 MMR USA 3 All |
|  | Provide and ensure the use of port facilities for the disposal of ship-borne waste | [IDN]: Fisheries enforcement office has been set up in each sea port to monitor. PHL: Policy in place, but lacks monitoring of compliance. AUS, VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] 2 PHL 2 VNM KHM [THA] MMR USA 3 All |
| Prohibit the direct harvest (capture or killing) of, and domestic trade in, marine turtles, their eggs, parts or products, whilst allowing exceptions for traditional harvest by communities within each jurisdiction provided that: such harvest does not undermine efforts to protect, conserve and recover marine turtle populations and their habitats; and the marine turtle populations in question are able to sustain the harvest | Enact, where not already in place, legislation to prohibit direct harvest and domestic trade | AUS: Commonwealth legislation – Environment Protection and Biodiversity Conservation Act – and State and Territory legislation prohibit direct harvest and domestic trade with substantial fines and penalties for illegal take and significant impacts, with exception made for traditional harvest. [IDN]: Many pieces of national legislation have been enacted. PHL: New Wildlife Act, Fisheries Code, IPAS Law enacted but lacking serious implementation. KHM: VNM: Programme 1.5 – subsections a), b) completed, Decree 48/2002/N-CP of 22 April 2002 either prohibits or controls the direct harvest of and trade in five species of marine turtles. [THA]: Wildlife Conservation and Protection Act 1992; Act No. 16 prohibiting hunting and capturing protected animals; Act No. 19 prohibiting the possession of protected animals or their carcasses; Act No. 20 prohibiting trade of protected animals and their products. MMR: USA: Endangered Species Act of 1973. All species of sea turtle (except Flatback) listed as endangered or threatened since 1978. |  | AUS [IDN] 1 PHL 3 VNM KHM 3 [THA] 1 MMR USA 3 All |
|  | Assess the level and impact of traditional harvest on marine turtles and their eggs | AUS: [IDN]: Based on the Decree by the Ministry of Agriculture in1980 and Government regulation No. 7/99, there is no more traditional harvest. PHL: Occurring only in the Turtle Islands. KHM: VNM: [THA]: No harvest or traditional harvest is allowed. MMR: Level of harvest – Low; impact of harvest – Low. USA: Traditional harvest is illegal. | [IDN]: Work with NGOs to conduct surveys. | AUS [IDN] 2 PHL 2 VNM KHM 1 [THA] MMR USA 3 All |
|  | Establish management programmes that may include limits on levels of intentional harvest | AUS: Draft Recovery Plan identifies management agreements between Commonwealth, State/Territory jurisdiction and indigenous communities. [IDN]: Intentional harvest is prohibited. PHL: Policy in place but requires adjustment in implementation due to new Wildlife Act. KHM: VNM: [THA]: No intentional harvest is permitted. MMR: USA: Intentional harvest is prohibited. |  | AUS [IDN] 1 PHL 2 VNM KHM 3 [THA] MMR USA 3 All |
|  | Determine the cultural and traditional values and economic uses of marine turtles (both consumptive and non-consumptive) | [IDN]: No traditional commercialisation is allowed. Law enforcement/confiscation has developed. PHL: Limited information. KHM: VNM: Consumptive and non-consumptive uses occurring. [THA]: MMR: Non-consumptive use occurring. USA: Partial implementation: studies of cultural values have been made. Efforts to economically value non-consumptive uses are nascent. |  | AUS [IDN] 1 PHL 2 VNM KHM 1 [THA] MMR USA 2 All |
|  | Negotiate, where appropriate, management agreements on the sustainable level of traditional harvest, in consultation with other concerned States, to ensure that such harvest does not undermine conservation efforts | [IDN]: MoU among stakeholders (Forestry, Fisheries and Local Government) has been enacted. An MoU between ASEAN and China to jointly combat illegal trade is being prepared. PHL: Ongoing discussions with Malaysia through TIHPA. MMR: No activity to report. USA: In addition to the IOSEA, the Inter-American Convention has provisions for this. AUS, VNM, KHM, [THA]: |  | AUS [IDN] PHL 1 VNM KHM [THA] MMR USA 2 All |
| Develop nesting beach management programmes to maximize hatchling recruitment | Evaluate the effectiveness of nest and beach management programmes | AUS: Australia evaluates hatchling success rate. [IDN]: Nest monitoring by counting the body pits of hawksbill turtles has been completed in P. Seribu NP, Beliting and Seqamat. PHL: Nest and beach management programme is being implemented in few areas, but effectiveness not being evaluated. MMR: There many unpublished reports which can be provided. USA: Continuing review through scientific and permit review process. VNM, KHM, [THA]: |  | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] 1 MMR USA 3 All |
|  | Reduce the mortality of eggs and hatchlings to maximise hatchling recruitment and survival, preferably using conservation techniques that emphasize natural processes wherever possible | AUS: Every major turtle rookery in Queensland contained in the Queensland National Park estate, and almost all in Western Australia that are subject to fox predation have established fox control programmes. [IDN]: Head starting in some areas has been conducted. Size and growth of hatchlings have been recorded, and size and weight of eggs have been measured. PHL: Being done, but limited to very few areas. KHM: VNM: [THA]: Workshop and training on marine turtle biology to conservation agencies. MMR: Law enforcement and public education. USA: Beach management emphasizes in situ incubation to the maximum extent possible. |  | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] 1 MMR USA 3 All |
|  | Minimise the mortality of eggs, hatchlings and nesting female turtles caused by feral and domestic animals | AUS: Established an egg relocation programme on mainland beaches in an area around Mon Repos, Queensland, if those nests are prone to flooding. Has resulted in increased hatchling production by 25% of Green turtle ‘doomed eggs’. [IND]: PHL: Hatcheries in some sites established to protect eggs. KHM: VNM: [THA]: Eggs at unsafe places have been moved to hatcheries. MMR: USA: Some feral animal control programmes are being implemented. | [IDN]: Develop suitable techniques. | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] 1 MMR USA 3 All |

##### Objective 2.  Protect, conserve and rehabilitate marine turtle habitats

| Programme | Activity | Implementation progress to date | Further specific actions | Priority |
| --- | --- | --- | --- | --- |
| 2.1 Establish necessary measures to protect and conserve marine turtle habitats | Identify areas of critical habitat such as migratory corridors, nesting beaches, inter-nesting and feeding areas | AUS: Critical nesting beaches have been identified. Migratory corridor has been identified in Torres Strait. Satellite tracking of Green turtles from 1999 in several northern region localities. [IDN]: Critical habitat has been documented, particularly in marine protected areas. PHL: Habitat surveys have been conducted since 1983 covering almost all political regions with coastal habitats. Poor data on feeding areas, internesting habitats, and migratory corridors. WWF-SSME Biodiversity Vision identified priority conservation areas. KHM: VNM: Programme 2.1 a) completed (see IUCN baseline survey and other recent documents listed in that publication). Subsections b) and c) underway: Marine protected areas have been established in Hon Mun (Khanh Hoa) from 2001 and MPA will be established in Cu Lao Cham (Quang Nam) in March 2003. Plans have been considered for Con Dao, Phu Quoc and Co To (Bach Long Vi). Assistance provided by WWF. [THA]: Nesting beach at Phuket Island has been identified as a critical area. MMR: USA: This is an active area of research. | AUS: Proposed satellite tracking of Olive Ridley Turtles in Tiwi Islands. The Representative Area Process underway in the GBRMP will identify further areas important to turtles for additional protection. | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] MMR USA 1 All |
|  | Designate and manage protected/ conservation areas, sanctuaries or temporary exclusion zones in areas of critical habitat, or take other measures (e.g. modification of fishing gear, restrictions on vessel traffic) to remove threats to such areas | AUS: GBRMP (on World Heritage list) was identified as a significant turtle feeding and nesting area. Some State and Commonwealth reserves have been established because of the significance of turtles: Ashmore Reef, Coral Sea. “Green” zones in Great Barrier Reef prohibit fishing. [IDN]: MPAs have been established and are well-managed; routine patrols are conducted. PHL: MNR AO # 8, IPAS Law established several protected areas, but lacks management. KHM: VNM: [THA]: Conservation of seagrass areas for feeding grounds. MMR: Designation and management of protected areas, sanctuaries, exclusion zones etc. USA: Many small protected areas designated (not specifically for sea turtles) as well as the very large Northwestern Hawaiian Islands reserve. Large area of North Pacific has been closed to U.S.-based longline vessels. | [IDN]: Routine patrols. | AUS [IDN] 1 PHL 1 VNM KHM 1 [THA] 1 MMR USA 1 All |
|  | Develop incentives for adequate protection of areas of critical habitat outside protected areas | AUS: Western Australia is negotiating with leaseholders on fox control in nesting areas; has reduced predation from 90% to nearly 0%. Use of poisonous chemicals and explosives in any exploitation of marine resources in Australian waters is explicitly banned. [IDN]: Consultation and coordination with stakeholders has been conducted specifically in local provinces by Fisheries and the Navy. USA: Development regulations protect adjacent beaches and waters. PHL, VNM, KHM, [THA], MMR: | [IDN]: Develop partnerships with NGOs. | AUS [IDN] 2 PHL 2 VNM KHM 1 [THA] 1 MMR USA 2 All |
|  | Undertake assessments of the environmental impact of marine and coastal development and other human activities that may affect marine turtle populations and their habitats | AUS: Environment Impact Assessment processes in Australia take fully into account the likely impact of proposed developments on turtles and/or nesting grounds during approval processes. [IDN]: Based on Act No. 23 of 1997 EIAs have been conducted on many projects. PHL: EIA system in place but needs improvement in implementation. WWF has capacity to conduct Environmental sensitivity index mapping employing digital aerial videography, satellite imageries and GIS. USA: Environmental impact assessment required for most major governmental projects and approvals. VNM, KHM, [THA], MMR: |  | AUS [IDN] 1 PHL 2 VNM KHM 1 [THA] 2 MMR USA 1 All |
|  | Manage and regulate within each jurisdiction the use of beaches and coastal dunes, for example location and design of buildings, use of artificial lighting, and transit of vehicles in nesting areas | AUS: Many areas with nesting beaches require the installation of low sodium lights. [IDN]: Based on above-mentioned EIA regulations no harmful activities are allowed. PHL: Implemented on established protected areas. Guidelines for eco-tourism development in place for the Turtle Islands. KHM: VNM: [THA]: Implemented by informing buildings around the nesting area to reduce lighting. MMR: Regulations in place regarding location and design of buildings, regulation on the transit of vehicles in nesting areas. USA: Being implemented, but measures vary by jurisdiction. | [IDN]: Enforce regulations through national committees. | AUS [IDN] 1 PHL 1 VNM KHM [THA] 2 MMR USA 2 All |
|  | Monitor and promote the protection of water quality from land-based and maritime pollution, including marine debris, that may adversely affect marine turtles | [IDN]: This situation has been coordinated through the National Wetland Committee. PHL: Policy in place but lacks enforcement and monitoring. [THA]: Coastal water long term monitoring. USA: Several statutes address water quality protection. AUS, VNM, KHM, MMR: | AUS: Funding to continue for clean up, research on type and source of debris, and understanding circulation patterns in the Gulf of Carpentaria to identify the location of debris hot spots. | AUS [IDN] 2 PHL 2 VNM KHM 1 [THA] 1 MMR USA 2 All |
|  | Strengthen the application of existing bans on the use of poisonous chemicals and explosives in the exploitation of marine resources | AUS: Use of poisonous chemicals and explosives in any exploitation of marine resources in Australian waters is explicitly banned. [IDN]: Public awareness and law enforcement are conducted regularly. PHL: MoA with DENR, DA-BFAR, DND, DOJ, DILG, DOTC, and WWF for a SSME enforcement crusade to increase effectiveness of enforcement of regulations against illegal and destructive fishing activities (success stories and models available and ready for replication if resources are available). KHM: VNM: [THA]: Use of poisonous chemicals and explosive in marine resources is totally prohibited. MMR: Promulgated 1991 marine fisheries law. USA: Being implemented. |  | AUS [IDN] 2 PHL 1 VNM KHM [THA] 1 MMR USA 3 All |
| 2.2 Rehabilitate degraded marine turtle habitats | Re-vegetate, where appropriate, frontal dunes at nesting beaches, with indigenous flora as far as possible, in order to provide visual barriers to coastal development and to restore appropriate beach temperature regimes | AUS: Many community-based projects funded by Australian governments are designed specifically as re-vegetation activities. Western Australia with Commonwealth NHT (Coastcare) are funding projects on beach access track closure on nesting beaches, and moving entry points away from significant points. [IDN]: Replanting mangroves in some degraded areas has been conducted. VNM: Programme 2.2 – subsections c) and d), Haiphong Institute of Oceanography and Nha Trang Institute of Oceanography have been conducting extensive surveys of seagrass, mangrove and coral reef habitat distribution and quality over the last 10 years. Seagrass restoration trials have begun at these institutes. USA: Major efforts to restore Northwestern Hawaiian Islands to original condition after military use. |  | AUS [IDN] 1 PHL 2 VNM KHM [THA 3] MMR USA 2 All |
|  | Remove debris that impedes turtle nesting and hatchling production | AUS: WWF, Conservation Volunteers Australia and Dhimurru Land Management Aboriginal Council conduct ongoing marine debris research surveys to record type of marine debris, determine its source and clean up beaches of northeast Arnhem Land. [IDN]: No precise activities conducted. PHL: Beach clean-up programmes some involving local communities. Serious problem in Turtle Islands where chainsaw and equipment are needed to remove drifted logs. VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] PHL 1 VNM KHM 1 [THA] MMR USA 3 All |
|  | Enhance recovery of degraded coral reefs | AUS: GBRMP Authority is conducting ongoing research into enhancement mechanisms for reef recovery. [IDN]: Coral transplantation has been conducted. PHL: Thorough enforcement of ban on dynamite and cyanide fishing but only in some localities. Deployed temperature sensors in Turtle Islands, Tubataha, and Anilao to monitor impact of El Nino. VNM: KHM: [THA]: Thailand has strong coral reef conservation and management programme. MMR: USA: Partial implementation: reef restoration focuses on reducing threats, less on active rebuilding. |  | AUS [IDN] 2 PHL 2 VNM KHM 1 [THA] 1 MMR USA 3 All |
|  | Enhance recovery of degraded mangrove and seagrass habitats | AUS: Some fisheries are establishing area closures and protected areas (eg., Northern Prawn Fishery and several marine protected areas are designed to enhance and protect seagrass. [IDN]: Mangrove restoration has been undertaken. PHL: Mangrove reforestation in some areas, with both success and failures. VNM: KHM: [THA]: Thailand is conducting mangrove and seagrass management programme. MMR: USA: Partial implementation: mangrove and seagrass restoration focuses on reducing threats, less on active rebuilding. |  | AUS [IDN] 1 PHL 2 VNM KHM 1 [THA] 1 MMR USA 3 All |

Objective 3.  Improve understanding of marine turtle ecology and populations through research, monitoring and information exchange

| Programme | Activity | Implementation progress to date | Further specific actions | Priority |
| --- | --- | --- | --- | --- |
| 3.1 Conduct studies on marine turtles and their habitats targeted to their conservation and management | Conduct baseline studies or gather secondary information on marine turtle populations and their habitats | AUS: Baseline studies are well progressed in Australia on nesting populations. [IDN]: WWF, TNC, Japan Bekko Association and Indonesia Scientific have conducted many studies. PHL: Habitat surveys conducted since 1983 covering almost all political regions with coastal habitats. Poor data on feeding areas, internesting habitats, and migratory corridors. WWF SSME Biodiversity Vision identified priority conservation areas. VNM: Completed by IUCN and MoFI. KHM: [THA]: MMR: Being done: eg. Ayeyarwady Division, turtle conservation camp and DoF offices. USA: Active area of research. | AUS: Research is needed on how nesting and feeding sites correlate. [IDN]: Invite researchers to carry out assessments. | AUS [IDN] 2 PHL 2 VNM KHM 1 [THA] 1 MMR USA 1 All |
|  | Initiate and/or continue long-term monitoring of priority marine turtle populations in order to assess conservation status | AUS: Three long-term monitoring programmes for: Loggerhead, Green in GBR and Flatbacks in eastern Australia. Flatback monitoring programmes in Baresand and Field Islands, Northern Territory. [IDN]: Monitoring has been conducted regularly as a part of Forest Ranger tasks. PHL: Limited to Turtle Islands. VNM: Completed and being continued by Con Dao National Park and WWF. KHM: [THA]: All nesting beaches have been monitored. MMR: Long-term monitoring programmes in Bogalay, Ngapudaw, as conservation camps. USA: Emphasis on Green turtles in Hawaii and Leatherbacks throughout the Pacific (in cooperation with other States). |  | AUS [IDN] 1 PHL 1 VNM KHM 2 [THA] 1 MMR USA 1 All |
|  | Characterise genetic identity of marine turtle populations | AUS: Identification of boundaries of genetic stocks is being undertaken. [IDN]: Genetic identification is still going on in Kyushu University, Japan. PHL: Limited to Turtle Islands. VNM: Has not been initiated, however a funding source has been identified. KHM: [THA]: Genetic populations of sea turtles have been studied. MMR: Genetic identity has been characterized at Thameehla Island (Diamond). USA: National Sea Turtle Genetics Center, established in La Jolla, California, has active programme to collect and analyse tissue samples for all stocks. | [IDN]: Develop capacity in genetic research. | AUS [IDN] 2 PHL 2 VNM KHM 3 [THA] 1 MMR USA 1 All |
|  | Identify migratory routes through the use of tagging, genetic studies and/or satellite tracking | AUS: Australia has funded research into migration using tagging, genetic studies and satellite telemetry. [IDN]: Some 124 Hawksbill turtles have been tagged. PHL: Tagging limited to few sites. DENR ran out of funds to buy additional tags. Satellite telemetry limited to Turtle Islands. VNM: One satellite transmitter was attached in 1999 to a Green turtle at Con Dao. More funding to support this has been applied for. KHM: [THA]: Migratory pattern has been studied using satellite tracking. MMR: Tagging conducted (Olive ridley nesting in Bogalay township island). USA: Active area of research through all means (tagging, satellite tracking, and genetics). |  | AUS [IDN] 2 PHL 1 VNM KHM 2 [THA] 1 MMR USA 1 All |
|  | Carry out studies on marine turtle population dynamics and survival rates | [IDN]: Surveys on marine turtles are well-documented. VNM: Vietnam does not currently have sufficient data to conduct population dynamics and survival rates, beyond summaries of nesting females at Con Dao since 1995. USA: Very long-term data sets usually required, and the Hawaii data sets are now becoming mature for this purpose. AUS, VNM, KHM, [THA], MMR: | [IDN]: Invite universities/NGOs to carry out advanced studies. | AUS [IDN] 2 PHL 2 VNM KHM 3 [THA] 1 MMR USA 1 All |
|  | Conduct research on the frequency and pathology of diseases of marine turtles | AUS: Minor work has been done to date on the frequency and pathology of diseases of marine turtles, however locations are generally difficult to access by vets. PHL: Has been proposed as an action under SSME tri-national program. [THA]: Research is in the initial stages. USA: NMFS Honolulu Lab is a centre for coordinating priority Green turtle fibropapilloma research at U.S. academic institutions. [IDN], VNM, KHM, MMR: | [IDN]: Invite universities/NGOs to carry out advanced studies. | AUS [IDN] 2 PHL 2 VNM KHM 3 [THA] 1 MMR USA 1 All |
|  | Promote the use of traditional ecological knowledge in research studies | AUS: Use of traditional ecological knowledge in research promoted strongly in the Northern Territory. MMR: USA: Interview and cooperation with local peoples is encouraged in research. [IDN], PHL, VNM, KHM, [THA]: | [IDN]: Increase use of traditional knowledge. | AUS [IDN] 2 PHL 2 VNM KHM 3 [THA] 2 MMR USA 1 All |
|  | Review periodically and evaluate research and monitoring activities | USA: Through permit review process, scientific peer review, periodic update of recovery plans, and specific programme reviews, as appropriate. For example: U.S. head starting programmes have been almost entirely discontinued in the 1980’s and early 1990’s as the result of programme reviews that found their benefit to be unproven and their relative costs to be very high. AUS, [IDN], PHL, VNM, KHM, [THA], MMR: |  | AUS [IDN] 2 PHL2 VNM KHM 3 [THA]1 MMR USA 1 All |
| 3.2 Conduct collaborative research and monitoring | Identify and include priority research and monitoring needs in regional and sub-regional action plans | AUS: [IDN]: WWF, TNC, local NGOs and Japan Bekko Association have drawn up an MoU. PHL: Done for TIHPA with Malaysia. SSME tri-national programme formulated. with Indonesia joining Malaysia and Philippines. VNM: Vietnam Government officials have attended meetings of CMS in Bonn (3 officials travelled), and Bangkok (SEASTAR) (2 persons from RIMF attended) as initial steps towards international collaboration. Tentative plans have been drawn up by RIMF in an effort to host the 2003 SEASTAR meeting. KHM: [THA]: MMR: Priority research and monitoring needs have been identified in ASEAN MoU meeting and workshops of SEAFDEC/MFRDMD. USA: Partial implementation. Formal action plans do not exist, but collaboration is sought and supported, usually on a bilateral basis. | [IDN]: Set up terms of reference for research. | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] 1 MMR USA 2 All |
|  | Conduct collaborative studies and monitoring on genetic identity, conservation status, migrations, and other biological and ecological aspects of marine turtles | [IDN]: Collaborative management has been conducted together with the above agencies. PHL: On-going for TIHPA. Proposed expansion under new SSME tri-national programme. MMR: Examples include: studies of genetic identity, conservation status, other biological and ecological aspects, hatcheries and public awareness. USA: Ongoing, particularly through training, collaboration, and support of these activities by national scientists in the region and the Pacific. AUS, VNM, KHM, [THA]: | [IDN]: Develop partnerships with researchers. | AUS [IDN] 2 PHL 1 VNM KHM [THA] 1 MMR USA 1 All |
| 3.3 Analyse data to support mitigation of threats and to assess and improve conservation politics | Prioritise populations for conservation actions | AUS: [IDN]: Marine turtle Action Plan has put population trends as a priority. PHL: Several areas have been established as conservation areas but many lack management. VNM: Areas have been identified in the draft NAP as priority areas, and in some cases, such as the standardisation of data collection, initial work has begun. Several Vietnamese Government and non-government staff will attend the Kuala Lumpur Sea Turtle Symposium in March 2003 to discuss this issue. KHM: [THA]: MMR: Hatcheries, tagging programme using Inconel tags. USA: Partial implementation. A formalized prioritisation does not exist, but conservation emphasis is directed to populations with most critical threats and lowest populations (currently, for the U.S., Pacific Leatherbacks). |  | AUS [IDN] 1 PHL 1 VNM KHM 2 [THA] 1 MMR USA 1 All |
|  | Identify population trends | PHL: Limited monitoring to few sites. Long term data available for Turtle Islands. USA: Done where data sets are robust enough. Ability to contribute to analysing population trends is a top priority of most data collection activities. AUS, [IDN], VNM, KHM, [THA], MMR: |  | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA]1 MMR USA 1 All |
|  | Use research results to improve management, mitigate threats and assess the efficacy of conservation activities (e.g. hatchery management practices, habitat loss, etc.) | AUS: [IDN]: Recommendations, based on survey results, have focused on habitat loss and declining populations. PHL: Turtle Islands only (tagging, nesting beach research, hatchery techniques, etc.) but findings have been shared with other conservation areas. VNM: KHM: [THA]: For hatchery management, habitat protection, and migration routes. MMR: Research results are being used to improve the efficacy of conservation actions in the areas of: management, threat mitigation, assessment of hatchery management practices. USA: Approval of all major governmental actions requires an evaluation of latest research information. |  | AUS [IDN] 1 PHL 1 VNM KHM 2 [THA] 1 MMR USA 1 All |
| 3.4 Exchange information | Standardise methods and levels of data collection and adopt or develop an agreed set of protocols for inter alia monitoring of nesting beaches, feeding ground studies, genetic sampling, and collection of mortality data | PHL: Established by PCP-PAWB-DENR and disseminated to regions. Agreement with Malaysia under TIHPA arrangements. Expansion to East Kalimantan in Indonesia through SSME tri-national programme. USA: Partial implementation: standardized and documented procedures developed and used for genetic sampling and analysis, standard and satellite tagging, nesting beach monitoring, reduction of turtle bycatch and mortality in longline and trawl fisheries. AUS, [IDN], VNM, KHM, [THA], MMR: | [IDN]: Set up an appropriate database. | AUS [IDN] 2 PHL 1 VNM KHM 3 [THA] 1 MMR USA 3 All |
|  | Determine the most appropriate methods for information dissemination | PHL: On-going awareness campaign under PCP-PAWB-DENR and WWF. Documentary film, radio plugs, posters, brochures, primers, bookmarks, billboards, t-shirts, caps, post cards and stamp cancellers, training-workshops, seminars, lectures, “dalaw turo”( visit and teach), TV and print media, exhibits, networking. These however have not been sustained due to lack of funds. USA: Partial implementation: multiple methods in use (Internet, publication of scientific papers and presentation at scientific fora (e.g. the Sea Turtle Symposium, targeted working groups and conferences, mass media). AUS, [IDN], VNM, KHM, [THA], MMR: |  | AUS [IDN] 2 PHL 2 VNM KHM [THA] 1 MMR USA 2 All |
|  | Exchange at regular intervals scientific and technical information and expertise among nations, scientific institutions, non-governmental and international organisations, in order to develop and implement best practice approaches to conservation of marine turtles and their habitats | PHL: With Malaysia under TIHPA, arrangements being expanded to Indonesia through SSME tri-national program. WWF recently sponsored tri-national training course with Dr. Limpus as trainer. WWF and DENR trained staff of Con Dao park in Vietnam. 3-week course conducted under TIHPA included topics on sea turtles, dugongs, corals and reef fish monitoring and a PADI O/W certification course. [THA]: Co-operation occurring among ASEAN countries. MMR: Occasional exchange of scientific and technical information and expertise at annual meetings, workshops and individual contacts. USA: Occurring both on a government-to-government basis and through support for the Sea Turtle Symposium. (See also 3.4.b.) AUS, [IDN], VNM, KHM: |  | AUS [IDN] 2 PHL 2 VNM KHM [THA] 1 MMR USA 1 All |
|  | Disseminate traditional knowledge on marine turtles and their habitats for conservation and management | MMR: Sea turtle conservation data is occasionally disseminated. USA: Partial implementation. AUS, [IDN], PHL, VNM, KHM, [THA]: |  | AUS [IDN] 2 PHL 2 VNM KHM [THA] 1 MMR USA 2 All |
|  | Compile on a regular basis data on marine turtle populations of regional interest | [IDN]: Updating the existing data sets. [THA]: Co-operation exists among ASEAN countries. USA: Done, as in the Pacific sea turtle recovery plans, for example. MoU Secretariat: Plans have been drawn up to include examples on the IOSEA Web site, under development. |  | AUS [IDN] 2 PHL 1 VNM KHM [THA] 1 MMR USA 2 All |

Objective 4.  Increase public awareness of the threats to marine turtles and their habitats, and enhance public participation in conservation activities

| Programme | Activity | Implementation progress to date | Further specific actions | Priority |
| --- | --- | --- | --- | --- |
| 4.1 Establish public education, awareness and information programmes | Collect, develop and disseminate education materials | AUS: Western Australia Fisheries is producing bycatch brochure for Rock Lobster Fishery. Queensland has produced information brochures on identification, threats and habitats. Information available on Environment Australia website. Port workshops on TEDs in the NPF. [IDN]: Public awareness campaign has been conducted, exhibitions, mass-media and community development as well as dissemination of material. USA: Being done. PHL, VNM, KHM, [THA], MMR: | AUS: Preparing a video outlining sea turtle handling and logbook data collection guidelines for distribution to all Australian pelagic longline vessels. Conducting port workshops covering sea turtle conservation awareness, sea turtle handling and logbook data collection. [IDN]: Conduct public awareness campaign, develop exhibition. | AUS [IDN] 1 PHL 2 VNM KHM 1 [THA] 1 MMR USA 2 All |
|  | Establish community learning / information centres | [IDN]: Established information centres in each MPA. PHL: WWF established children’s library in Turtle Islands and deployed volunteer teachers. [THA]: In progress. USA: Some exist, but usually not governmental. AUS, VNM, KHM, MMR: | [IDN]: Develop further information centres. | AUS [IDN] 1 PHL 1 VNM KHM 1 [THA] 1 MMR USA 2 All |
|  | Develop and implement accurate mass media information programmes | AUS: [IDN]: CEPA has contacted stakeholders regularly. PHL: Part of awareness and participation programme of PCP-PAWB. VNM: KHM: [THA]: Exhibitions. MMR: Done through media (usually not governmental). USA: Done, usually working through existing news outlets. | [IDN]: Develop TV, radio, newspaper information, etc. | AUS [IDN] 1 PHL 2 VNM KHM 3 [THA] 1 MMR USA 2 All |
|  | Develop and conduct focused education and awareness programmes for target groups (e.g. policy makers, teachers, schools, fishing communities, media) | AUS: “Dean the Green turtle” web tracking. [IDN]: Conservation education to schools, youth groups, nature lovers and fishermen has been conducted in some areas. PHL: Part of awareness and participation programme of PCP-PAWB. VNM: Education and awareness materials for school children, fishers, traders and enforcement officers are currently being developed by IUCN, WWF and TRAFFIC. KHM: [THA]: Education and awareness programme in place. MMR: Teachers, fishing communities, media, other – education at the fishing ground, sometime on shore. USA: Conducted, particularly for fishing groups. | [IDN]: Continue public awareness to stakeholders. | AUS [IDN] 1 PHL 1 VNM KHM 1 [THA] 1 MMR USA 2 All |
|  | Encourage the incorporation of marine turtle biology and conservation issues into school curricula | [IDN]: Marine turtle biology is already included in national curricula at high school and university level. PHL: Limited to few local schools. USA: Some NGO initiatives: see, for example, the work of the Caribbean Conservation Corporation (www.ccc.org) | [IDN]: Review school curricula with Ministry of Education. | AUS [IDN] 1 PHL 1 VNM KHM 1 [THA] 1 MMR USA 2 All |
|  | Organise special events related to marine turtle conservation and biology (e.g. Turtle Day, Year of the Turtle, symposia, Track-a-turtle) | AUS: During National Coastcare Week, the Queensland Government nominated marine turtles as focus species and distributed information brochures. [IDN]: Blue Ocean Day, Clean Water Day, World Wetland Day have been conducted. PHL: Part of awareness and participation programme of PCP-PAWB. VNM: KHM: [THA]: Sea turtle releasing festival. MMR: USA: Special events organised. |  | AUS [IDN] 1 PHL 2 VNM KHM 3 [THA] 1 MMR USA 2 All |
| 4.2 Develop alternative livelihood opportunities for local communities to encourage their active participation in conservation efforts | Identify and facilitate alternative livelihoods (including income generating activities) that are not detrimental to marine turtles and their habitats, in consultation with local communities and other stakeholders | AUS: Promotion of eco-tourism (e.g. at Mon Repos, Queensland). Economic gains from such eco-tourism are estimated to be greater than if 100% of turtle eggs were harvested. [IDN]: Community development conducted in Bali; eco-tourism development in Derawan, P Seribu NP, and best practice in shrimp fisheries in Java. PHL: Carried out in Turtle Islands. VNM: KHM: [THA]: Encourage conservation activity of local NGOs. MMR: Implementing ban on destructive fishing gears, such as entangling ripping hooks, for replacement with other non-destructive fishing gear. USA: Not relevant, since turtle exploitation has not been a major economic activity. |  | AUS [IDN] 1 PHL 1 VNM KHM [THA] 2 MMR USA 3 All |
| 4.3 Promote public participation | Involve stakeholders, and local communities in particular, in planning and implementation of conservation and management measures | AUS: Development of the draft Turtle Recovery Plan involved all interested stakeholders (conservation groups, industry and communities as well as government). Involvement of stakeholders, conservationists, fishing industry, managers etc. in a workshop on pelagic longline fisheries. [IDN]: PHL: Stakeholdership and community involvement is a guiding principle in project development and implementation for WWF. VNM: KHM: [THA]: Establishment of local community conservation projects is encouraged (e.g. initiated sea turtle conservation at Phratong Island). MMR: Local communities, stakeholders have been involved by assisting in implementation. USA: This is a usual requirement of government regulation development. |  | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] 1 MMR USA 1 All |
|  | Encourage the participation of Government institutions, non-governmental organisations, the private sector and the general community (e.g. students, volunteers, fishing communities, local communities) in research and conservation efforts | PHL: Stakeholdership and community involvement is a guiding principle in project development and implementation for WWF. AUS, [IDN], PHL, VNM, KHM, [THA], MMR: |  | AUS [IDN] PHL 1 VNM KHM 2 [THA] 1 MMR USA 2 All |
|  | Implement, where appropriate, incentive schemes to encourage public participation (e.g. T-shirts for tag returns, public acknowledgement, certificates) | AUS: Queensland provides a cap as part of their incentive scheme. Northern Prawn Fishery has caps and T-shirts; Western Australia provides T-shirts. [IDN]: PHL: Part of awareness and participation programme of PCP-PAWB. VNM: KHM: [THA]: T-shirts, award for information on tag returns, and certificate given for participation in conservation. MMR: Incentive schemes: public acknowledgement, certificates, award for return of tags. USA: Partial implementation. Materials developed and used ad hoc, without a formal programme. |  | AUS [IDN] PHL 2 VNM KHM 2 [THA] 1 MMR USA 2 All |

Objective 5.  Enhance national, regional and international cooperation

| Programme | Activity | Implementation progress to date | Further specific actions | Priority |
| --- | --- | --- | --- | --- |
| 5.1 Collaborate with and assist signatory and non-signatory States to regulate and share information on trade, to combat illegal trade, and to cooperate in enforcement activities relating to marine turtle products | Encourage signatory States that have not already done so to become Parties to the Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES) | AUS: Australia provides a report to CITES CoP on implementation of CITES. The EPBC Act prohibits all trade in turtle products and parts, enforced through Customs Act and was amended in 2001 to strengthen the provisions relating to imports and exports of wildlife, including turtles, to increase penalties and fines for non-compliance. [IDN]: Ratified CITES in 1978. PHL: Philippines is already signatory to CITES. VNM: Vietnam is signatory to CITES. KHM, [THA], MMR, USA: | [IDN]: Complete Presidential Decree necessary for signing MoU. | AUS [IDN] 2 PHL 1 VNM KHM [THA] MMR USA 2 All |
|  | Review at a national level compliance with obligations under CITES relating to trade in marine turtles, their eggs, parts or products | [IDN]: Draft amendment to Act # 5 of 1990 concerning conservation on natural resources and ecosystem has been completed. PHL: Part of mandate of PAWB and DA-BFAR. VNM: TRAFFIC conducted a national survey of trade in marine turtle products in Vietnam, which looked at both national and international trade. AUS, KHM, [THA], MMR, USA: |  | AUS [IDN] 1 PHL 2 VNM KHM 1 [THA] 1 MMR USA 3 All |
|  | Facilitate better compliance with CITES through training of relevant authorities in cooperation with other signatory States, the CITES Secretariat and other relevant organisations | AUS: Environment Australia provides training on enforcement for customs, navy and wardens. [IDN]: CITES enforcement training is conducted annually for Customs, Police, Fisheries and Forestry staff. VNM: TRAFFIC has been conducting training of relevant authorities in Vietnam and Malaysia on CITES issues. USA: Law enforcement training in particular has been conducted with other States for CITES compliance. PHL, KHM, [THA], MMR: | [IDN]: Continue to conduct annual CITES training. | AUS [IDN] 1 PHL 2 VNM KHM 2 [THA] 1 MMR USA 1 All |
|  | Identify routes of international illegal trade through monitoring, and seek cooperation to take action to prevent, deter and, where possible, eliminate illegal trade | [IDN]: Illegal trade in wildlife has been identified. Routes have been identified to the Philippines, Singapore, Malaysia, Vietnam and China. PHL: Monitoring units deployed in major ports of entries and exits; TRAFFIC investigated South East Asian trade routes for products of Hawksbill turtles. AUS, VNM, KHM, [THA], MMR, USA: | [IDN]: Develop ASEAN-China collaboration to curb illegal trade. | AUS [IDN] 1 PHL 1 VNM KHM [THA] 1 MMR USA 1 All |
|  | Exchange and discuss information on compliance and trade issues at regular intervals, such as through annual reporting to the MoU Secretariat and at meetings of the signatory States | [IDN]: Biannual CITES National report has been submitted to the secretariat; attendance at the CoP 12 in Santiago, Chile Nov. 2002, attendance at ASEAN CITES Export group, Asian CITES (Mongolia 2002), CITES Symposium (Japan 2002). AUS, PHL, VNM, KHM, [THA], MMR, USA: | [IDN]: Continue to attend relevant CITES meetings. | AUS [IDN] 2 PHL 2 VNM KHM 3 [THA] MMR USA 3 All |
|  | Identify, prevent, deter and, where possible, eliminate domestic illegal trade through monitoring, implementation of legislation, identification of gaps in enforcement capabilities in each country, and training of enforcement officers | AUS: [IDN]: The proposal for an “ASEAN-China joint effort to curb illegal trade on wildlife” has been endorsed in 2002. PHL: Monitoring units deployed in major ports of entry and exit. VNM: Working with TRAFFIC to strengthen enforcement capabilities relating to marine turtles. KHM: [THA]: MMR: Taking measures such as monitoring, legislation, identification of enforcement gaps, on-the-job training and public education at conservation areas. USA: Ongoing efforts. | [IDN]: Increase frequency of routine patrols. VNM: MoFI is striving to have turtle products off the shelves by 2004. | AUS [IDN] 1 PHL 1 VNM KHM [THA] 1 MMR USA 3 All |
| 5.2 Assist signatory and non-signatory States, upon request, to develop and implement national, sub-regional and regional action plans for the conservation and management of marine turtles and their habitats | Develop a set of key management measures that could be used as a basis for action plans, through consultation with concerned Government authorities, research institutions, NGOs, local communities and other stakeholders | AUS: Australia has provided funding for a community based Leatherback turtle conservation project in Kamiali nesting beaches in Papua New Guinea. [IDN]: Marine Turtle Action Plan was launched in 1991 and has been reviewed as necessary. PHL: Being facilitated by WWF for SSME and Asia-Pacific region. VNM: A national action plan for the protection of marine turtles in Vietnam is being prepared by MoFI under the guidance of the Project Steering Committee and will be completed by May 2003. KHM: [THA]: MMR: Annual departmental action plan, dealing with hatcheries, tagging, and site-based research. USA: Considers this action should be done jointly or by Advisory Committee, not by a single State. |  | AUS [IDN] PHL 2 VNM KHM 3 [THA] MMR USA 2 All |
|  | Identify existing action plans that could be used as models | [IDN]: Tagging programme, head starting, nest monitoring and satellite tracking have been identified as key high priorities. PHL: TIHPA joint management programme with Malaysia now being expanded to include Indonesia. USA: Considers this action should be done jointly or by Advisory Committee, not by a single State. MoU Secretariat: |  | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] MMR USA 2 All |
|  | Identify specific local management issues where cooperation among States is required for successful conservation and management | MMR: Technical know-how, materials for research work, experts and training. AUS, PHL, VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] PHL 1 VNM KHM 2 [THA] MMR USA 2 All |
|  | Review action plans at regular intervals to take into account recent advances in skills and knowledge regarding marine turtle conservation and management, as well as changes in conservation status of marine turtle populations | [IDN]: Review of Action Plan was finalized in 1995. MMR: Attended two workshops to provide data for review. USA: Not yet done (future activity). AUS, PHL, VNM, KHM, [THA]: |  | AUS [IDN] 2 PHL 2 VNM KHM [THA] MMR USA 2 All |
| 5.3 Enhance mechanisms for cooperation and promote information exchange | Identify and strengthen existing mechanisms for cooperation at the sub-regional level | [IDN]: ASEAN CITES expert and Asian CITES group meetings conducted. PHL: TIHPA, ASEAN Marine Turtle MoU, SSME MMR: Sends information on tagging to SEAFDEC/MFRDMD by e-mail; receives tag information from SEAFDEC member countries at the annual SEAFDEC meetings. AUS, VNM, KHM, [THA], USA: |  | AUS [IDN] 1 PHL 1 VNM KHM 2 [THA] 1 MMR USA 2 All |
|  | Develop a website and/or newsletter to facilitate networking and exchange of information | [IDN]: Indonesian CITES database has been compiled and national legislation related to CITES has been set up. PHL: WWF, SSME, DENR, ARCBC websites on-line. [THA]: Participates in co-operative regional tagging programme through which information is exchanged. USA: Multiple websites for government, academic, private, and NGO sea turtle research and conservation activities exist. The Marine Turtle Newsletter is a global sea turtle conservation and research resource. AUS, VNM, KHM, MMR, USA: MoU Secretariat: IOSEA MoU web site is under development. |  | AUS [IDN] 1 PHL 2 VNM KHM 3 [THA] 1 MMR USA 1 All |
|  | Develop a web-based information resource for marine turtle conservation (including data on populations, nesting, migration, on-going projects) | USA: Partially exists at www.seaturtle.org. Specific resource for the region needs to be collaboratively developed. Under development by IOSEA MoU Secretariat, in cooperation with UNEP-WCMC and C. Limpus | MMR: Can contribute data on marine turtle populations, nesting data and information on the current project. | AUS [IDN] 1 PHL 2 VNM KHM 2 [THA] MMR USA 1 All |
|  | Create a directory of experts and organisations concerned with marine turtle conservation | PHL: With PCP-PAWB and WWF. MoU Secretariat: |  | AUS [IDN] 2 PHL 2 VNM KHM 2 [THA] MMR USA 1 All |
|  | Develop networks for cooperative management of shared populations, within or across sub-regions, and, where appropriate, formalise cooperative management arrangements | PHL: Examples include: TIHPA, SSME, ASEAN USA: Not yet existing in Indo-Pacific; it is hoped that this MoU serves as the vehicle to develop such networks. AUS, [IDN], VNM, KHM, [THA], MMR: |  | AUS [IDN] 1 PHL 1 VNM KHM 3 [THA] MMR USA 2 All |
|  | Cooperate where possible in the establishment of transboundary marine protected areas using ecological rather than political boundaries | PHL: Examples include: TIHPA, SSME, ASEAN AUS, [IDN], VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] PHL 1 VNM KHM 3 [THA] 3 MMR USA 3 All |
|  | Develop a streamlined format for reporting and exchanging information (through the MoU Secretariat and among signatory States) on the state of marine turtle conservation at the national level | MoU Secretariat: Format was prepared for/adopted by 1st Meeting of Signatory States. | USA: Will cooperate with Secretariat and other signatories to achieve suitable format. | AUS [IDN] PHL VNM KHM [THA] MMR USA 2 All |
|  | Encourage MoU signatory States that have not already done so to become Parties to the Convention on Migratory Species (CMS) | [IDN]: Cross sectoral consultation and meetings/workshops have been conducted. PHL: WWF-SSME to support efforts in this regard. VNM: A three person Vietnamese delegation went to the 7th COP (CMS) in Bonn to discuss Vietnam’s accession to CMS. It is the intention of the Vietnam Government that they will sign CMS prior to the 8th COP. USA: Not applicable (the USA is not a Party to CMS). AUS, KHM, [THA], MMR: MoU Secretariat |  | AUS [IDN] 2 PHL 1 VNM KHM [THA] MMR USA 3 All |
|  | Encourage signatory States to become Parties to global fisheries agreements such as the UN Fish Stocks Agreement (1995) and the FAO Compliance Agreement (1993) and implement the FAO Code of Conduct for Responsible Fisheries (1995) | [IDN]: FAO Code of Conduct for Responsible Fisheries is being implemented. PHL: Being promoted though SSME tri-national fisheries framework under BIMP-EAGA USA: Strongly supports the FAO Code of Conduct. AUS, VNM, KHM, [THA], MMR: |  | AUS [IDN] PHL 2 VNM KHM [THA] MMR USA 2 All |
|  | Establish relationships with regional fisheries bodies with a view to obtaining data on incidental capture and encourage them to adopt marine turtle conservation measures within EEZs and on the high seas | PHL: Being promoted though SSME tri-national fisheries framework under BIMP-EAGA AUS, [IDN], VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] PHL 2 VNM KHM [THA] MMR USA 1 All |
| 5.4 Build capacity to strengthen conservation measures | Identify needs for capacity-building in terms of human resources, knowledge and facilities | AUS: Environment Australia provides enforcement training to customs and navy officers and wardens, including on-site training at Ashmore Reef Marine Reserve. Northern Territory University involved in training Indonesian PhD student on turtle conservation and management. PHL: Concerns PCP, WWF, TIHPA, SSME USA: Need to work cooperatively with other signatories. [IDN], VNM, KHM, [THA], MMR: | [IDN]: Conduct training seminars, workshops and exchange programmes. | AUS [IDN] 1 PHL 2 VNM KHM 2 [THA] 1 MMR USA 1 All |
|  | Provide training (e.g. through workshops) in marine turtle conservation and management techniques to relevant agencies, individuals and local communities | AUS: Environment Australia provides enforcement training to customs and navy officers and wardens, including on-site training at Ashmore Reef Marine Reserve. [IDN]: PHL: Concerns PCP, WWF, TIHPA, SSME. VNM: Training course on turtle conservation has been provided by WWF in Con Dao. KHM: [THA]: Training and workshop on sea turtle conservation. MMR: Training course on sea turtle research and conservation; training manuals. USA: Implemented particularly through training of local people and national scientists in sea turtle research techniques (e.g., beach survey methods, tagging studies, satellite tracking) and similar capacity building and through fisheries technology transfer (e.g., TEDs) | [IDN]: Carry out organisational training. | AUS [IDN] 1 PHL 1 VNM KHM 1 [THA] 1 MMR USA 1 All |
|  | Coordinate training programmes and workshops | PHL: Concerns PCP, WWF, TIHPA, SSME MMR: Achieved nationally through a departmental fund USA: Scope of training workshops should depend on situation. U.S. has supported or been involved in narrow (country-to-country) and broad-focussed workshops (e.g., Northern Indian Ocean Sea Turtle Workshop, East African TEDs Training Workshop, Sea Turtle Symposia). AUS, [IDN], VNM, KHM, [THA]: | [IDN]: Develop training programme. | AUS [IDN] 1 PHL 2 VNM KHM 1 [THA] 1 MMR USA 1 All |
|  | Develop partnerships with universities, research institutions, training bodies and other relevant organisations | AUS: Northern Territory University involved in training Indonesian PhD student on turtle conservation and management. PHL: Concerns PCP-PAWB, WWF, TIHPA, SSME MMR: Two MSc thesis students prepared their thesis in 1998 to 1999, Yangon University. USA: Done | [IDN]: Include such institutions in national committee. | AUS [IDN] 1 PHL 1 VNM KHM 2 [THA] 1 MMR USA 3 All |
| 5.5 Strengthen and improve enforcement of conservation legislation | Review domestic policies and laws to address gaps or impediments to marine turtle conservation | [IDN]: Government regulations enacted and Academic draft of Act No. 5 of 1990 has been completed. PHL: Undertaken within framework of PCP-PAWB, WWF, TIHPA, SSME. VNM: Decree 48 strengthens directives for enforcement officers with respect to domestic trade. Decree 11 provides clear direction for CITES matters. USA: Regulations are subject to review and modification as necessary. Congress has reviewed most major conservation laws in recent years and made some important changes, particularly to the fisheries law. AUS, KHM, [THA], MMR: | [IDN]: Complete review of Act No. 5 of 1990 [THA]: Improve laws and punishment. | AUS [IDN] 1 PHL 2 VNM KHM 2 [THA] 1 MMR USA 3 All |
|  | Cooperate in law enforcement to ensure compatible application of laws across and between jurisdictions (including through bilateral/multilateral agreements and intelligence sharing) | AUS: Environment Australia provides enforcement training to customs and navy officers and wardens. [IDN]: Regular contact among CITES member countries has grown. PHL: Inter-agency arrangements among PCP-PAWB, WWF, TIHPA, SSME, USA: Has a domestic law that allows the U.S. to prosecute violators of another State’s conservation laws. VNM, KHM, [THA], MMR: | [IDN]: Strengthen ASEAN Experts Group on CITES | AUS [IDN] PHL 1 VNM KHM 1 [THA] 2 MMR USA 2 All |

##### Objective 6.  Promote implementation of the MoU including the Conservation and Management Plan

| Programme | Activity | Implementation progress to date | Further specific actions | Priority |
| --- | --- | --- | --- | --- |
| 6.1 Broaden membership in the MoU, and ensure continuity of MoU activities | Encourage non-signatory States to sign the MoU | AUS: Australia has made representations at official and Ministerial level to PNG and Indonesia to sign the MoU. Australia also offered to reimburse CMS for both an Indonesian and PNG representative to attend the MoU meeting. USA: Has actively promoted the MoU to non-signatories and has supported the negotiation of the MoU and CMP. [IDN], PHL, VNM, KHM, [THA], MMR: | [IDN]: Currently Indonesia is not a signatory to the MoU. Presidential decree to ratify the MoU is under preparation. PHL: WWF through SSME tri-national programme will support efforts to encourage Malaysia and Indonesia to sign. | AUS [IDN] 1 PHL 1 VNM KHM [THA] MMR USA 1 All |
|  | Arrange sub-regional workshops involving non-signatory States to raise awareness of the MoU | USA: Not undertaken. AUS, [IDN], PHL, VNM, KHM, [THA], MMR: |  | AUS [IDN] 3 PHL 3 VNM KHM [THA] MMR USA 3 All |
|  | Consider at the first meeting of the signatory States the development of a timetable for possible amendment of the MoU to make it a legally binding instrument | USA: Submitted a position paper to the First Meeting of Signatory States on this subject. AUS, [IDN], PHL, VNM, KHM, [THA], MMR: |  | AUS [IDN] 3 PHL 3 VNM KHM [THA] MMR USA 3 All |
| Promote the role of the Secretariat and the Advisory Committee of the MoU in ensuring the objectives of the Conservation and Management Plan are met | Secure reliable sources of funding to support the MoU Secretariat | USA: Has contributed, but has not made a permanent funding commitment, to the Secretariat. AUS, [IDN], PHL, VNM, KHM, [THA], MMR: |  | AUS [IDN] 3 PHL 1 VNM KHM [THA] MMR USA 2 All |
|  | Appoint at the first meeting of the signatory States the members of the Advisory Committee | First Meeting of Signatory States (Bangkok, Jan 2003) appointed six experts to the AC. |  | AUS [IDN] 3 PHL 1 VNM KHM [THA] MMR USA 1 All |
|  | Establish lines of communication between the MoU Secretariat and the Advisory Committee to facilitate advice to the signatory States | MoU Secretariat: organized 1st meeting of AC in March 2003; regular communication with all members achieved through e-mail. |  | AUS [IDN] 3 PHL 1 VNM KHM 2 [THA] MMR USA 1 All |
| 6.3 Seek resources to support the implementation of the MoU | Prioritise conservation and management activities for funding | PHL: Efforts are under way through WWF SSME programme for Indonesia, Malaysia, and Philippines. AUS, [IDN], VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] 3 PHL 1 VNM KHM 1 [THA] MMR USA 1 All |
|  | Explore funding options with Governments and other donors such as the Asian Development Bank, World Bank, UNDP, European Union, UNEP, GEF, etc. | PHL: Efforts are under way through WWF SSME programme for Indonesia, Malaysia, and Philippines. AUS, [IDN], VNM, KHM, [THA], MMR, USA: MoU Secretariat: Submitted proposal for recruitment of Junior Professional Officer in 2002 (and resubmitted in 2003); preliminary inquiries with AusAID for possible assistance in 2004. |  | AUS [IDN] 3 PHL 1 VNM KHM 1 [THA] MMR USA 1 All |
|  | Solicit funding and other contributions from industries that have impacts on marine turtles and their habitats (e.g. fisheries, tourism, oil industry, real estate) | AUS: Oil industry has provided funds for management and conservation in areas in Western Australia. [IDN], PHL, VNM, KHM, [THA], MMR, USA: | [IDN]: Setting-up of benefit sharing scheme. | AUS [IDN] 2 PHL 1 VNM KHM [THA] MMR USA 2 All |
|  | Explore the use of economic instruments for the conservation of marine turtles and their habitats | AUS, [IDN], PHL, VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] PHL 2 VNM KHM [THA] MMR USA 2 All |
|  | Approach the private sector, foundations and NGOs that may have an interest in funding activities in particular countries to catalyse the creation of a small grants fund | PHL: Done through WWF. AUS, [IDN], VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] 1 PHL 1 VNM KHM [THA] MMR USA 3 All |
|  | Generate funding for conservation and management activities through managed eco-tourism and other self-supporting schemes (while benefiting local communities) | PHL: Element of WWF, TIHPA and SSME programme. AUS, [IDN], VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] 1 PHL 1 VNM KHM [THA] MMR USA 3 All |
|  | Seek synergies (with respect to fund-raising, provision of institutional support, etc.) with other regional/global convention secretariats | PHL: Element of WWF TIHPA and SSME programme. AUS, [IDN], VNM, KHM, [THA], MMR, USA: MoU Secretariat: | [IDN]: Harmonize biodiversity related conventions. | AUS [IDN] PHL 1 VNM KHM [THA] MMR USA 2 All |
|  | Explore international funding support and other incentives for signatory States that effectively manage marine turtle populations, which might include the complete prohibition of direct harvest (capture or killing) | PHL: Element of WWF TIHPA and SSME programme. AUS, [IDN], VNM, KHM, [THA], MMR, USA: |  | AUS [IDN] PHL 1 VNM KHM [THA] MMR USA 3 All |
| 6.4 Improve coordination among government and non-government sectors in the conservation of marine turtles and their habitats | Review the roles and responsibilities of government agencies related to the conservation and management of marine turtles and their habitats | PHL: PCP-PAWB-DENR, WWF SSME stakeholders analysis. USA: Regular intra-governmental coordination meetings and reviews occur. AUS, [IDN], VNM, KHM, [THA], MMR: | [IDN]: Organise workshops and meetings for this purpose. | AUS [IDN] 2 PHL 2 VNM KHM [THA] MMR USA 3 All |
|  | Designate a lead agency responsible for coordinating national marine turtle conservation and management policy | PHL: PCP-PAWB-DENR. USA: Responsibility is divided. U.S. Department of State has lead in foreign affairs. U.S. Fish and Wildlife Service has lead for sea turtle management on beaches and is the CITES authority (science and management). U.S. National Marine Fisheries Service has lead for sea turtle management and conservation in the sea and for managing fisheries. AUS, [IDN], VNM, KHM, [THA], MMR: | [IDN]: Propose Ministerial decree. | AUS [IDN] 1 PHL 3 VNM KHM [THA] MMR USA 3 All |
|  | Encourage cooperation within and among government and non-government sectors, including through the development and/or strengthening of national networks | PHL: Achieved within PCP-PAWB-DENR, WWF SSME Programme MMR: Only one turtle conservation unit of DoF, established in 1986, at Thameehla Island and 1998, at Bogalay Township to conserve and to carry out research work on sea turtles. AUS, [IDN], VNM, KHM, [THA], USA: | [IDN]: Establish national committee. | AUS [IDN] 1 PHL 1 VNM KHM [THA] MMR USA 3 All |