## Guidance
Guidance for preparing the Report of Range States on the Implementation of the Single Species Action Plan for the Angelshark (Squatina squatina) in the Mediterranean Sea (SSAP Angelshark Med) (CMS Decision 14.101 e)
The reporting template (see sheet "Report") is based on the actions included in the Single Species Action Plan adopted at CMS COP14.
Range States are kindly requested to fill in columns F - I for each activity, providing information as available and applicable. Please include the name of the country, contact information, and date.
Some activities specifically refer to all Range States, while others only apply to those where Squatina squatina is currently extant.
· Column F: Action taken / Results achieved Please provide a detailed and complete description of action(s) taken and achievements related to the result.
· Column G: Reason for no or limited action taken Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons.
· Column H: References and links Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken.
· Column I: Status of implementation Please use the drop-down menu to choose the status of implementation.
In accordance with CMS Decision 14.101 (f) and (g), the Secretariat will compile all reports from Range States and prepare a brief summary and analysis. This summary will be discussed and presented at the 1st Working Group Meeting, where recommendations for the further implementation of the SSAP Angelshark Med will be developed for COP15.

## Report
Draft Reporting Template |  |  |  |  | Greece 2025 |  |  |  | Greece 2026
Annex to the Angelshark SSAP |  |  |  |  | Contact Person: Charalampos Ververis, Ioannis Giovos Date:xx/3/2025 |  |  |  | Contact Person: Charalampos Ververis, Ioannis Giovos Date:14/10/2026
Objective 1 - Ensure appropriate species-level protection for Angelshark Squatina squatina
Result | Action | Priority | Time Scale | Parties Responsible | Action taken / Results achieved | Reason for no or limited action taken | References and links | Progress | Action taken / Results achieved | Reason for no or limited action taken | References and links | Progress
[5 empty] | Please provide a detailed and complete description of action(s) taken and achievements related to the result. | Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons. | Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken. | Please use the drop-down menu to choose the status of implementation. | Please provide a detailed and complete description of action(s) taken and achievements related to the result. | Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons. | Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken. | Please use the drop-down menu to choose the status of implementation.
Appropriate species protection in line with CMS Appendix I listing, and relevant GFCM recommendations (GFCM/42/2018/2) and GFCM/44/2021/16) are enforced or introduced for Angelshark Squatina squatina*. Such protection may need to apply to both commercial and recreational fisheries (and should also consider other potential sources of anthropogenic mortality), in order to comply fully with obligations to protect CMS Appendix I listed species. Awareness programme to ensure relevant stakeholders are aware of regulations protecting Angelsharks and subsequent monitoring of compliance and enforcement, where necessary. [* and other relevant species] | 1.1 Prohibition in fisheries regulations: Secure national fisheries regulations to ensure that it is prohibited to fish for, retain, tranship, and land Angel Sharks (Squatina spp.) in support of GFCM Recommendation GFCM/42/2018/2 and GFCM/44/2021/16. Note it is important to also prohibit intentional catches of Smoothback Angelshark (Squatina 25culate) and Sawback Angelshark (Squatina aculeata) due to the difficulty to identify and distinguish between the three Angel Shark species found within the Mediterranean. | Essential | Immediate | All Range States | Regulation (EU) 2023/2124 on certain provisions for fishing in the General Fisheries Commission for the Mediterranean (GFCM) Agreement area, particularly Art. 98, requests that all elasmobranch species listed in Annex II of the SPA/BD Protocol shall not be retained on board, transhipped, landed, transferred, stored, sold or displayed or offered for sale. All 3 Squatina species are included in Annex II. This prohibition is mentioned in the fishing terms for professional fishing licenses in Greece. | Circular 4531/83795/20-07-2016 Βan on the trade of shark (eg squatina squatina) and ray species Greece imlements Reg(EU)2019/1241 | * Link for Regulation (EU) 2023/2124: https://eur-lex.europa.eu/search.html?scope=EURLEX&text=2023%2F2124&lang=en&type=quick&qid=1741257562441 https://eur-lex.europa.eu/legal-content/EN/TXT/PDF/?uri=CELEX:32019R1241 | Fully implemented | Regulation (EU) 2023/2124 on certain provisions for fishing in the General Fisheries Commission for the Mediterranean (GFCM) Agreement area, particularly Art. 98, requests that all elasmobranch species listed in Annex II of the SPA/BD Protocol shall not be retained on board, transhipped, landed, transferred, stored, sold or displayed or offered for sale. All 3 Squatina species are included in Annex II. This prohibition is mentioned in the fishing terms for professional fishing licenses in Greece. | Circular 4531/83795/20-07-2016 Βan on the trade of shark (eg squatina squatina) and ray species Greece imlements Reg(EU)2019/1241 | * Link for Regulation (EU) 2023/2124: https://eur-lex.europa.eu/search.html?scope=EURLEX&text=2023%2F2124&lang=en&type=quick&qid=1741257562441 https://eur-lex.europa.eu/legal-content/EN/TXT/PDF/?uri=CELEX:32019R1241 | Fully implemented
| 1.2 Species-protection: Establish national species-level protection against the deliberate killing, injuring, or taking of Angelshark. This is of particular importance for those nations where prohibited species regulations (see 1.1) only apply to commercial fishing vessels, as additional protection against other sources of potential mortality (e.g., artisanal and recreational fisheries) may be required. | Essential | Short | All Range States | No national legislation exists for the species |  |  | Not addressed yet | No national legislation exists for the species |  |  | Not addressed yet
| 1.3 Awareness programmes: Initiate educational and awareness programmes with relevant stakeholder groups in both the fisheries sector (e.g. enforcement officials, fishing industry, fish markets) and recreational sector (e.g. recreational fishers, spearfishers, and amateur divers) as to the prohibited and/or protected status of Angelsharks With a particular focus on species identification to distinguish between the three Squatina spp., but also for classification purposes as Angelsharks are often reported as rays and not sharks. Share resources already developed by the Angel Shark Project for best practice to safely release Angelsharks if accidentally caught and the Angel Shark Sightings Map to report sightings. | Essential | Medium | Range States where Angelsharks are extant | iSea the last 5 years is running awareness and capacity building activities in the context of the Anegl Shark Project Greece. This includes 30 workshops for 200 fishers in critical areas for angel sharks and campaigning in social and mass media during the International Angel Shark Day. In addition, NECCA, in the context of the update of the Red List prepared a video with some iconic species and this included angeshark Squatina squatina |  | https://www.youtube.com/watch?v=wC7PEO5hZdM&ab_channel=%CE%9F.%CE%A6%CE%A5.%CE%A0%CE%95.%CE%9A.%CE%91.%28N.E.C.C.A.Greece%29 | Fully implemented | In the context of environmental projects the last 6 years awareness and capacity building activities from iSea and the Angel Shark Project Greece. This includes 40 workshops for 400 fishers in critical areas for angel sharks and campaigning in social and mass media during the International Angel Shark Day. In addition, NECCA, in the context of the update of the Red List prepared a video with some iconic species and this included angeshark Squatina squatina |  | https://www.youtube.com/watch?v=NiJfZit7CvQ | Fully implemented
| 1.4 Monitoring and enforcement: Ensure that enforcement staff undertake appropriate monitoring of commercial fisheries and landings, particularly regarding those fleets that are more likely to encounter Angelsharks. Develop, or extend, national reporting framework for collating the number of inspections undertaken (by port, fleet, and month) and instances of infringement with regards to Angelsharks. | High | Ongoing | Range States where Angelsharks are extant |  |  |  | Fully implemented | Monitoring exists, training is taking place irregularly in the context of different projects but mostly from the Angelshark Project Greece, however, still misidentifications and landings of angelsharks take place | Greece is a particularly difficult country for monitoring fisheries with a vast amount of islands and about 12.000 activie fishing boats distributed all over the country |  | Partially implemented
Objective 2 - Identification of sites and habitats of Angelshark Squatina squatina
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
To identify former, current and potential Critical Angel Shark Areas (CASAs) and ascertain the status of Angelshark in these areas. | 2.1 Data collation: Collate national data (including both contemporary and historic sources) regarding the presence of Angelsharks Squatina squatina (and sister taxa) from relevant sources (including published studies, commercial and recreational fisheries data, fish market data, fisher and diver interviews, citizen science programmes, trawl survey data, discard observer data, museum specimens, Angelshark survey data and historical resources) to better document the contemporary and historical occurrence of Angelsharks in national waters. Such data may also be enhanced through the collection of data on the current presence of Angelshark through the use of social media. Such data could be usefully collated in a common format (see Annex II), with institutes collating national data collaborating with other national institutes in order that more robust regional data are available. The collation of comparable data for other species of Angel Shark should also be undertaken, in order to aid in the interpretation of data for Squatina squatina. The Angel Shark Sightings Map, hosted by the Angel Shark Conservation Network, is already established, open access and widely used and could be utilised for this purpose. | High | Ongoing | All Range States | In the context of the Work Plan on Data Collection under the EU Data Collection Framework (Regulation (EU) 2017/1004), the Greek state collects data regarding the species. In addition, the International Trawl Survey in the Mediterranean (MEDITS) included all elasmobrach species encountered during sampling. Furthermore, iSea, in the context of the Angel Shark Project, Greece has been collecting current and historical data on the species, having a quite extensive database stored in the Angel Shark Conservation Network. |  |  | Fully implemented | Although the Angel Shark Project Greece has an extensive database with all the records available through bibliography and reports from Citizen Science still data collected from public authorities are not available for use, with the exception of the MEDITS data |  |  | Partially implemented
| 2.2 Habitat modelling: Based on data from action 2.1, undertake Angelshark habitat modelling in national waters and regional seas, in order to better understand and predict Critical Angel Shark Areas (CASAs), including habitats used by key life-history stages, including nursery, mating grounds, pupping and overwintering grounds. | High | Ongoing | All Range States | iSea has prepared a publication in the Critical Angel Sharks Areas but some more sites were provided in the context of the Important Shark and Ray Areas delineations (Truva shelf AoI, Dodecanese AoI, Southeastern Aegean Sea ISRA) |  | https://www.mdpi.com/2077-1312/10/2/269 | Fully implemented |  |  | https://www.mdpi.com/2077-1312/10/2/269 | Fully implemented
| 2.3 Environmental DNA (eDNA) sampling: undertake eDNA sampling of appropriate areas (i.e., former, current and potential Angelshark habitats identified in 2.2) to gauge potential presence of Angelshark in the region. | Medium | Medium | All Range States |  |  |  | Not addressed yet |  |  |  | Not addressed yet
| 2.4 Non-destructive site sampling: Depending on the results of 2.1, 2.2, and/or 2.3, undertake non-destructive surveys (e.g., underwater visual census) of contemporary/potential Angelshark habitat to determine whether effective non extractive field programmes could be developed in order to monitor localised populations of Angelshark. | High | Medium/Long | All Range States |  | Contemporary/potential Angelshark habitats have not been determined yet. |  | Not addressed yet | A new site for angel sharks has been discovered int eh context of two projects. In June 2026 the first underwater visual census campaign took place however no angel sharks were encountered but more expeditions are prepared plus ROV surveys |  | https://www.endangeredlandscapes.org/project/lemnos/ https://isea.com.gr/project/lemnos/ | Partially implemented
| 2.5 Role of current MPA network: Undertake appropriate sampling (e.g., eDNA sampling, underwater visual census) of existing Marine Protected Areas which may provide suitable habitat for Angelshark, in order to ascertain the likely presence/absence of Angelshark and the effectiveness of conservation measures in place in the current MPA network. | Medium | Long | All Range States | iSea has shown through modelling and overlapping that Critical Angel Sharks Areas are not included in the Marine Protected Areas Netwrok of the country |  |  | Partially implemented |  |  |  | Partially implemented
Objective 3 - Support and undertake scientific studies, including data collection and liaison with the fishing sectors, to improve scientific knowledge of Angelsharks Squatina squatina, including population trends
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
Improved scientific data from commercial fisheries on Angelsharks becomes available, to inform on the status of the species, pressures and enable more robust monitoring of population trends. Improved scientific data from recreational fisheries and other recreational activities on Angelsharks becomes available, to inform on the status of the species, pressures and enable more robust monitoring of population trends | 3.1 Scientific monitoring: Based on the results of 2.1, 2.2, and/or 2.3, initiate (or expand) scientific observer programmes to ensure dedicated and robust observer coverage of those commercial fleets that may interact with Angelshark, covering Angelshark habitats in order to improve contemporary data on the presence of Angelshark and their interactions with fisheries.), and associated biological information (length, gender, females that are pregnant or giving birth). | High | Medium | Range States where Angelsharks are extant | At the moment, scientific monitoring of catches from commercial fisheries and from independent research surveys (MEDITS) involve all elasmobranchs. |  |  | Partially implemented |  |  |  | Partially implemented
| 3.2 Commercial fishery-dependent catch-per-unit-effort data: Improved reporting of interactions with commercial fishing fleets, including data on the numbers of Angelsharks caught, fate (discarded alive or discarded dead). Comparable data on fishing effort, especially for those fleets expected to have a higher number of interactions with Angelsharks, should also be recorded. Such work could utilise the existing reporting requirements of GFCM and potentially focus on a particular ‘reference fleet’ as a case study. | High | Short (Implementation) Ongoing (Monitoring) | Range States where Angelsharks are extant | Greece implements Reg (EC)1185/2003 about Shark Fins |  |  | Partially implemented |  |  |  | Partially implemented
| 3.3 Recreational fishery: Encourage reporting of sightings to both the relevant national fisheries institute and the Angel Shark Sightings Map22. Adapt and distribute a code of conduct to safely release Angelsharks if accidentally caught (already developed by the Angel Shark Project) to the recreational fishing community. | High | Ongoing | Range States where Angelsharks are extant | No data exist with the exception of one capture from a recreational fisher reported in the context of citizen science |  |  | Not addressed yet |  |  |  | Not addressed yet
| 3.4 Citizen science: Through awareness programmes developed in Action 1.3, encourage reporting of Angelshark sightings to both the relevant national fisheries institute and the Angel Shark Sightings Map22, whether amateur or commercial divers, recreational fishers or someone sighting them in a market. Adapt and share a code of conduct for scuba and snorkel23 (already developed by Angel Shark Project) with the diving community. | Medium | Ongoing | Range States where Angelsharks are extant | iSea is promoting the Angel Shark Conservation Network and the M.E.C.O. project. Currently more than 3000 records of sharks and rays have been reported and a big number of records of angel sharks |  |  | Fully implemented |  |  |  | Fully implemented
| 3.5 Fishery-independent survey trends: For any areas of localised Angelshark abundance or suitable Angelshark habitat (as surveyed under Actions 2.2, 2.3 and 2.4), initiate standardised, longer-term, non-destructive monitoring programmes to understand seasonal and annual trends in the presence and relative abundance of Angelsharks. Such work could involve collaborative studies with relevant stakeholder groups (e.g., commercial fishers, recreational fishers, divers etc.). | High | Medium (Implementation) Ongoing (Monitoring) | Range States where Angelsharks are extant | iSea is working in East Lemnos and in Nysiros with the fishing fleet that interacts with angel sharks. Up to now more than 30 angel sharks have been released |  | https://www.facebook.com/iSea.org/videos/447812561476856 | Partially implemented | Only in Lemnos long term monitoring is taking place at the moment |  |  | Partially implemented
| 3.6 Quantification and characterization of discarded Angelshark survival and options for minimising discard mortality: Depending on the results of Action 3.1 and 3.2, detailed studies are needed to provide more robust estimates of discard survival (at-vessel mortality and post-release mortality) of Angelsharks from commercial fleets. Such work should be undertaken in conjunction with current levels and patterns of fleet activity and should be designed in such a way that would decrease fishing mortality on Angelsharks. Such work should also identify where changes in fisher behaviour (e.g., soak times of nets) can prevent or minimise mortality of incidentally caught Angelshark. | High | Long | Range States where Angelsharks are extant |  | Data are scattered and no analysis can be performed |  | Not addressed yet |  | Data are scattered and no analysis can be performed |  | Not addressed yet
| 3.7 Tagging: For any areas of localised Angelshark abundance (as surveyed under Action 2.4), consider the utility of visual and/or electronic tagging to inform on seasonality, habitat use, home range and movement. Such studies should be designed carefully and follow an ethical review process, to avoid increasing mortality. | Medium | Long | Range States where Angelsharks are extant | iSea will perform conventional tagging in East Lemnos and in 2026 sattelite tagging will be performed |  |  | Partially implemented | iSea is performing a tagging campaign since june 2026. One staellite tag has been deployed in the Context of ELSP Lemnos project and it is expected to pop up on October 2026 while another 4 tags will be deployed in 2027 |  | https://www.endangeredlandscapes.org/news/first-satellite-tagged-angel-shark-marks-milestone-for-lemnos-restoration-project/ | Fully implemented
| 3.8 Population structure and connectivity: Collect opportunistic tissue samples (e.g., from dead bycatch) and ensure appropriate longer-term archiving and storage. Subsamples of this material should be made available for scientific studies to facilitate Atlanto-Mediterranean genetic analyses to understand Angelshark connectivity in the region and global range. | Medium | Long | All Range States | iSea has collected angelshark tissue samples and genetic analysis is pending to understand the connectivity with other Mediterranean and East Atlantic populations |  |  | Partially implemented | Tissues have been collected and shared with colleagues from abroad for analysis. Results are expected soon |  |  | Fully implemented
| 3.9 Life-history studies: Depending on studies being undertaken under the Concerted Action Plan, relevant national institutes could usefully collect life-history information (length, sex, weight, maturity, collection of biological material for supporting studies, including genetic samples, stomach contents, tissue samples, and parasites). In accordance with the “no taking” rule described in CMS Article III (524) such work should only be undertaken when based on specimens of incidental dead bycatch and under authorised derogation from relevant national regulatory frameworks (see Objective 1). | Medium | Ongoing | Range States where Angelsharks are extant |  | records are scarce and information is nto available |  | Not addressed yet | Information of all available specimens is collected but data scarce |  |  | Partially implemented
| 3.10 Longer-term, historical population dynamics: Depending on the data available (see Action 2.1), undertake analyses of longer-term population trends of Angelsharks for national waters and regional seas to understand historical population trends. | Low | Long | All Range States |  | Available data are limited for undertaking such analysis. |  | Not addressed yet | Available data are limited for undertaking such analysis. |  |  | Partially implemented
Objective 4 - Sufficient resources secured for long-term Angelshark Squatina squatina conservation actions
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
Resources shall be secured on a long-term basis for the implementation of the Single Species Action Plan. | 4.1 Provide Resources: National and regional governments secure the necessary funds for the implementation of the actions at national and regional levels. Parties shall strive to provide funds to implement priority actions in the plan and financially contribute to staff time and coordination. | High | Ongoing | All Range States | [7 empty] | Not addressed yet
| 4.2 Establish an international working group (IntWG) for the Mediterranean region: An IntWG will be established to coordinate and monitor the implementation of this Single Species Action Plan. | High | Ongoing | All Range States | Greece has formed an IntWG, and plans to contribute to the group. |  |  | Fully implemented |  |  |  | Fully implemented
| 4.3 Appraise protected areas: Expand the existing MPA network to include any identified CASAs and the effectiveness of MPA networks is continually monitored. | Medium | Long | All Range States | At the moment the Critical Angel Shark Areas have been identified but they are not included in the MPAs netwrok of the country | Greece overlooked sharks in the creation of the MPAs network |  | Not addressed yet | Comments for the expantion of the Natura2000 site in Lemnos to include the CASAs of angel sharks has been submitted yet angel sharks are not included in any MPAs in the country |  |  | Not addressed yet
Any other information |  |  |  |  | An identification guide for sharks and rays occurring in Greece is provided by the Directorate General for Fisheries of the Hellenic Ministry of Rural Development and Food and is available to public bodies / authorities and interested parties. (http://www.alieia.minagric.gr/sites/default/files/announcementsFiles/2017%20%CE%9F%CE%94%CE%97%CE%93%CE%9F%CE%A3%20%CE%9A%CE%91%CE%A1%CE%A7%CE%91%CE%A1%CE%99%CE%A9%CE%9D%20%CE%9A%CE%91%CE%99%20%CE%A3%CE%95%CE%9B%CE%91%CE%A7%CE%99%CE%A9%CE%9D.pdf) There are no recorded landings of the species Squatina squatina according to the officially registered data of the ERS (Electronic Reporting System). Moreover, compensation for damages to fishing gears and fishery production caused by protected species is provided under the Maritime, Fisheries, and Aquaculture Operational Programme 2021-2027 - Programme for Greece (https://www.espa.gr/el/Pages/ProclamationsFS.aspx?item=6668), through a measure aimed at mitigating the effects of such damages on fishing activities.

## Progress
Fully implemented
Partially implemented
Not addressed yet
Not relevant in my country