## Guidance
Guidance for preparing the Report of Range States on the Implementation of the Single Species Action Plan for the Angelshark (Squatina squatina) in the Mediterranean Sea (SSAP Angelshark Med) (CMS Decision 14.101 e)
The reporting template (see sheet "Report") is based on the actions included in the Single Species Action Plan adopted at CMS COP14.
Range States are kindly requested to fill in columns F - I for each activity, providing information as available and applicable. Please include the name of the country, contact information, and date.
Some activities specifically refer to all Range States, while others only apply to those where Squatina squatina is currently extant.
· Column F: Action taken / Results achieved Please provide a detailed and complete description of action(s) taken and achievements related to the result.
· Column G: Reason for no or limited action taken Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons.
· Column H: References and links Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken.
· Column I: Status of implementation Please use the drop-down menu to choose the status of implementation.
In accordance with CMS Decision 14.101 (f) and (g), the Secretariat will compile all reports from Range States and prepare a brief summary and analysis. This summary will be discussed and presented at the 1st Working Group Meeting, where recommendations for the further implementation of the SSAP Angelshark Med will be developed for COP15.

## Report
Draft Reporting Template |  |  |  |  | MONTENEGRO 2025 |  |  |  | MONTENEGRO 2026
Annex to the Angelshark SSAP |  |  |  |  | [Ivana Mitrovic, ivana.mitrovic@epa.gov.me] [12 March 2025] |  |  |  | [Ivana Mitrovic; ivana.mitrovic@epa.gov.me] [Date 05.10.2025]
Objective 1 - Ensure appropriate species-level protection for Angelshark Squatina squatina |  |  |  |  | MONTENEGRO |  |  |  | MONTENEGRO
Result | Action | Priority | Time Scale | Parties Responsible | Action taken / Results achieved | Reason for no or limited action taken | References and links | Progress | Action taken / Results achieved | Reason for no or limited action taken | References and links | Progress
[5 empty] | Please provide a detailed and complete description of action(s) taken and achievements related to the result. | Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons. | Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken. | Please use the drop-down menu to choose the status of implementation. | Please provide a detailed and complete description of action(s) taken and achievements related to the result. | Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons. | Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken. | Please use the drop-down menu to choose the status of implementation.
Appropriate species protection in line with CMS Appendix I listing, and relevant GFCM recommendations (GFCM/42/2018/2) and GFCM/44/2021/16) are enforced or introduced for Angelshark Squatina squatina*. Such protection may need to apply to both commercial and recreational fisheries (and should also consider other potential sources of anthropogenic mortality), in order to comply fully with obligations to protect CMS Appendix I listed species. Awareness programme to ensure relevant stakeholders are aware of regulations protecting Angelsharks and subsequent monitoring of compliance and enforcement, where necessary. [* and other relevant species] | 1.1 Prohibition in fisheries regulations: Secure national fisheries regulations to ensure that it is prohibited to fish for, retain, tranship, and land Angel Sharks (Squatina spp.) in support of GFCM Recommendation GFCM/42/2018/2 and GFCM/44/2021/16. Note it is important to also prohibit intentional catches of Smoothback Angelshark (Squatina 25culate) and Sawback Angelshark (Squatina aculeata) due to the difficulty to identify and distinguish between the three Angel Shark species found within the Mediterranean. | Essential | Immediate | All Range States | Permanent fishing ban on Squatina squatina, S. oculata and S. aculeata is in force since 2015, based on the Law on marine fisheries and mariculture. |  | Regulation on the closed season for age classes of fish and other marine organisms, under the Law on marine fisheries and mariculture. Available in English at: https://www.fao.org/faolex/results/details/en/c/LEX-FAOC151759 | Fully implemented | Everything is the same as last year. |  |  | Fully implemented
| 1.2 Species-protection: Establish national species-level protection against the deliberate killing, injuring, or taking of Angelshark. This is of particular importance for those nations where prohibited species regulations (see 1.1) only apply to commercial fishing vessels, as additional protection against other sources of potential mortality (e.g., artisanal and recreational fisheries) may be required. | Essential | Short | All Range States | The above mentioned fishing ban applies to all types of fisheries. In addition, Montenegro is in the process of adopting a new national list of protected species, which will include the three above mentioned angelshark species. |  | Regulation on the closed season for age classes of fish and other marine organisms, under the Law on marine fisheries and mariculture. Available in English at: https://www.fao.org/faolex/results/details/en/c/LEX-FAOC151759 | Fully implemented | Everything is the same as last year. |  |  | Fully implemented
| 1.3 Awareness programmes: Initiate educational and awareness programmes with relevant stakeholder groups in both the fisheries sector (e.g. enforcement officials, fishing industry, fish markets) and recreational sector (e.g. recreational fishers, spearfishers, and amateur divers) as to the prohibited and/or protected status of Angelsharks With a particular focus on species identification to distinguish between the three Squatina spp., but also for classification purposes as Angelsharks are often reported as rays and not sharks. Share resources already developed by the Angel Shark Project for best practice to safely release Angelsharks if accidentally caught and the Angel Shark Sightings Map to report sightings. | Essential | Medium | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. | No angelsharks were observed in the local catches for decades. Ćetković, I., Serena, F., Barash, A., et al. (2024). Combining official fisheries monitoring and citizen science data to create the first chondrichthyan checklist of Montenegro. Acta Adriatica, 65(1), 21-31. | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 1.4 Monitoring and enforcement: Ensure that enforcement staff undertake appropriate monitoring of commercial fisheries and landings, particularly regarding those fleets that are more likely to encounter Angelsharks. Develop, or extend, national reporting framework for collating the number of inspections undertaken (by port, fleet, and month) and instances of infringement with regards to Angelsharks. | High | Ongoing | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. | No angelsharks were observed in the local catches for decades. Ćetković, I., Serena, F., Barash, A., et al. (2024). Combining official fisheries monitoring and citizen science data to create the first chondrichthyan checklist of Montenegro. Acta Adriatica, 65(1), 21-31. | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
Objective 2 - Identification of sites and habitats of Angelshark Squatina squatina
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
To identify former, current and potential Critical Angel Shark Areas (CASAs) and ascertain the status of Angelshark in these areas. | 2.1 Data collation: Collate national data (including both contemporary and historic sources) regarding the presence of Angelsharks Squatina squatina (and sister taxa) from relevant sources (including published studies, commercial and recreational fisheries data, fish market data, fisher and diver interviews, citizen science programmes, trawl survey data, discard observer data, museum specimens, Angelshark survey data and historical resources) to better document the contemporary and historical occurrence of Angelsharks in national waters. Such data may also be enhanced through the collection of data on the current presence of Angelshark through the use of social media. Such data could be usefully collated in a common format (see Annex II), with institutes collating national data collaborating with other national institutes in order that more robust regional data are available. The collation of comparable data for other species of Angel Shark should also be undertaken, in order to aid in the interpretation of data for Squatina squatina. The Angel Shark Sightings Map, hosted by the Angel Shark Conservation Network, is already established, open access and widely used and could be utilised for this purpose. | High | Ongoing | All Range States | Documented records of angelsharks in Montenegrin waters are available only from historical sources (e.g., Lepetić, 1965; Jukić, 1983; Ikica et al., 2021). Although several elasmobranch conservation campaigns have been carried out in recent years, no new observations were found. Montenegro participates in the regional citizen science initiative, the MECO project, which also did not provide observations of these species in the country's waters. Additionally, data originating from other relevant fisheries monitoring projects did not provide any recent records of angelsharks. |  | Ćetković, I., Serena, F., Barash, A., et al. (2024). Combining official fisheries monitoring and citizen science data to create the first chondrichthyan checklist of Montenegro. Acta Adriatica, 65(1), 21-31. | Partially implemented | We didn't have new actions. | Ćetković, I., Serena, F., Barash, A., et al. (2024). Combining official fisheries monitoring and citizen science data to create the first chondrichthyan checklist of Montenegro. Acta Adriatica, 65(1), 21-31. |  | Partially implemented
| 2.2 Habitat modelling: Based on data from action 2.1, undertake Angelshark habitat modelling in national waters and regional seas, in order to better understand and predict Critical Angel Shark Areas (CASAs), including habitats used by key life-history stages, including nursery, mating grounds, pupping and overwintering grounds. | High | Ongoing | All Range States | There are no current action regarding this species based on national monitoring program, because it isn't priority species recognized by IMAP or EEA proposal for marine biodiversity. | Lack of technical capacity, human and financial resources. |  | Not addressed yet |  |  |  | Not addressed yet
| 2.3 Environmental DNA (eDNA) sampling: undertake eDNA sampling of appropriate areas (i.e., former, current and potential Angelshark habitats identified in 2.2) to gauge potential presence of Angelshark in the region. | Medium | Medium | All Range States | There are no current action regarding this species based on national monitoring program, because it isn't priority species recognized by IMAP or EEA proposal for marine biodiversity. | Lack of technical capacity, human and financial resources. |  | Not addressed yet |  |  |  | Not addressed yet
| 2.4 Non-destructive site sampling: Depending on the results of 2.1, 2.2, and/or 2.3, undertake non-destructive surveys (e.g., underwater visual census) of contemporary/potential Angelshark habitat to determine whether effective non extractive field programmes could be developed in order to monitor localised populations of Angelshark. | High | Medium/Long | All Range States | There are no current action regarding this species based on national monitoring program, because it isn't priority species recognized by IMAP or EEA proposal for marine biodiversity. | Lack of technical capacity, human and financial resources. |  | Not addressed yet | There are no current action regarding this species based on national monitoring program, because it isn't priority species recognized by IMAP or EEA proposal for marine biodiversity. | Lack of technical capacity, human and financial resources. |  | Not addressed yet
| 2.5 Role of current MPA network: Undertake appropriate sampling (e.g., eDNA sampling, underwater visual census) of existing Marine Protected Areas which may provide suitable habitat for Angelshark, in order to ascertain the likely presence/absence of Angelshark and the effectiveness of conservation measures in place in the current MPA network. | Medium | Long | All Range States | There are three MPAs in Montenegro, managed by the Public enterprise for coastal zone management. However, since none of the projects/monitoring programmes carried out in these MPAs haven't provided an angelshark record, it is most likely that these species are not currently present there. | Lack of technical capacity, human and financial resources. |  | Not addressed yet | There are three MPAs in Montenegro, managed by the Public enterprise for coastal zone management. However, since none of the projects/monitoring programmes carried out in these MPAs haven't provided an angelshark record, it is most likely that these species are not currently present there. | Lack of technical capacity, human and financial resources. |  | Not addressed yet
Objective 3 - Support and undertake scientific studies, including data collection and liaison with the fishing sectors, to improve scientific knowledge of Angelsharks Squatina squatina, including population trends
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
Improved scientific data from commercial fisheries on Angelsharks becomes available, to inform on the status of the species, pressures and enable more robust monitoring of population trends. Improved scientific data from recreational fisheries and other recreational activities on Angelsharks becomes available, to inform on the status of the species, pressures and enable more robust monitoring of population trends | 3.1 Scientific monitoring: Based on the results of 2.1, 2.2, and/or 2.3, initiate (or expand) scientific observer programmes to ensure dedicated and robust observer coverage of those commercial fleets that may interact with Angelshark, covering Angelshark habitats in order to improve contemporary data on the presence of Angelshark and their interactions with fisheries.), and associated biological information (length, gender, females that are pregnant or giving birth). | High | Medium | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.2 Commercial fishery-dependent catch-per-unit-effort data: Improved reporting of interactions with commercial fishing fleets, including data on the numbers of Angelsharks caught, fate (discarded alive or discarded dead). Comparable data on fishing effort, especially for those fleets expected to have a higher number of interactions with Angelsharks, should also be recorded. Such work could utilise the existing reporting requirements of GFCM and potentially focus on a particular ‘reference fleet’ as a case study. | High | Short (Implementation) Ongoing (Monitoring) | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.3 Recreational fishery: Encourage reporting of sightings to both the relevant national fisheries institute and the Angel Shark Sightings Map22. Adapt and distribute a code of conduct to safely release Angelsharks if accidentally caught (already developed by the Angel Shark Project) to the recreational fishing community. | High | Ongoing | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks.
| 3.4 Citizen science: Through awareness programmes developed in Action 1.3, encourage reporting of Angelshark sightings to both the relevant national fisheries institute and the Angel Shark Sightings Map22, whether amateur or commercial divers, recreational fishers or someone sighting them in a market. Adapt and share a code of conduct for scuba and snorkel23 (already developed by Angel Shark Project) with the diving community. | Medium | Ongoing | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.5 Fishery-independent survey trends: For any areas of localised Angelshark abundance or suitable Angelshark habitat (as surveyed under Actions 2.2, 2.3 and 2.4), initiate standardised, longer-term, non-destructive monitoring programmes to understand seasonal and annual trends in the presence and relative abundance of Angelsharks. Such work could involve collaborative studies with relevant stakeholder groups (e.g., commercial fishers, recreational fishers, divers etc.). | High | Medium (Implementation) Ongoing (Monitoring) | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.6 Quantification and characterization of discarded Angelshark survival and options for minimising discard mortality: Depending on the results of Action 3.1 and 3.2, detailed studies are needed to provide more robust estimates of discard survival (at-vessel mortality and post-release mortality) of Angelsharks from commercial fleets. Such work should be undertaken in conjunction with current levels and patterns of fleet activity and should be designed in such a way that would decrease fishing mortality on Angelsharks. Such work should also identify where changes in fisher behaviour (e.g., soak times of nets) can prevent or minimise mortality of incidentally caught Angelshark. | High | Long | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.7 Tagging: For any areas of localised Angelshark abundance (as surveyed under Action 2.4), consider the utility of visual and/or electronic tagging to inform on seasonality, habitat use, home range and movement. Such studies should be designed carefully and follow an ethical review process, to avoid increasing mortality. | Medium | Long | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.8 Population structure and connectivity: Collect opportunistic tissue samples (e.g., from dead bycatch) and ensure appropriate longer-term archiving and storage. Subsamples of this material should be made available for scientific studies to facilitate Atlanto-Mediterranean genetic analyses to understand Angelshark connectivity in the region and global range. | Medium | Long | All Range States |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.9 Life-history studies: Depending on studies being undertaken under the Concerted Action Plan, relevant national institutes could usefully collect life-history information (length, sex, weight, maturity, collection of biological material for supporting studies, including genetic samples, stomach contents, tissue samples, and parasites). In accordance with the “no taking” rule described in CMS Article III (524) such work should only be undertaken when based on specimens of incidental dead bycatch and under authorised derogation from relevant national regulatory frameworks (see Objective 1). | Medium | Ongoing | Range States where Angelsharks are extant |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
| 3.10 Longer-term, historical population dynamics: Depending on the data available (see Action 2.1), undertake analyses of longer-term population trends of Angelsharks for national waters and regional seas to understand historical population trends. | Low | Long | All Range States |  | There is no data on the contemporary presence of angelsharks. |  | Not relevant in my country | There is no data on the contemporary presence of angelsharks. |  |  | Not relevant in my country
Objective 4 - Sufficient resources secured for long-term Angelshark Squatina squatina conservation actions
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
Resources shall be secured on a long-term basis for the implementation of the Single Species Action Plan. | 4.1 Provide Resources: National and regional governments secure the necessary funds for the implementation of the actions at national and regional levels. Parties shall strive to provide funds to implement priority actions in the plan and financially contribute to staff time and coordination. | High | Ongoing | All Range States |  | It will take time for the government to recognize and accept the recommendation and allocate funds for research on these species. |  | Not addressed yet |  | It will take time for the government to recognize and accept the recommendation and allocate funds for research on these species. |  | Not addressed yet
| 4.2 Establish an international working group (IntWG) for the Mediterranean region: An IntWG will be established to coordinate and monitor the implementation of this Single Species Action Plan. | High | Ongoing | All Range States | Government Focal Point and a technical Focal Point for the International Working Group on the implementation of the Single Species Action Plan are nominated. |  |  | Fully implemented | Government Focal Point and a technical Focal Point for the International Working Group on the implementation of the Single Species Action Plan are nominated. |  |  | Fully implemented
| 4.3 Appraise protected areas: Expand the existing MPA network to include any identified CASAs and the effectiveness of MPA networks is continually monitored. | Medium | Long | All Range States | Three MPAs are relatively recently declared, and we don't know when a new one will be declared by Government. But we will work on preparing for the proclamation of new protected areas in the sea. | No CASAs have been identified as there are no contemporary records of the species. Existing MPAs are monitored through various projects and activities. |  | Not addressed yet | Three MPAs are relatively recently declared, and we don't know when a new one will be declared by Government. But we will work on preparing for the proclamation of new protected areas in the sea. | No CASAs have been identified as there are no contemporary records of the species. Existing MPAs are monitored through various projects and activities. |  | Not addressed yet
Any other information |  |  |  |  | Please use this space to provide any other relevant information that was not covered by the Objectives and Actions above. |  |  |  | Please use this space to provide any other relevant information that was not covered by the Objectives and Actions above.

## Progress
Fully implemented
Partially implemented
Not addressed yet
Not relevant in my country