## Guidance
Guidance for preparing the Report of Range States on the Implementation of the Single Species Action Plan for the Angelshark (Squatina squatina) in the Mediterranean Sea (SSAP Angelshark Med) (CMS Decision 14.101 e)
The reporting template (see sheet "Report") is based on the actions included in the Single Species Action Plan adopted at CMS COP14.
Range States are kindly requested to fill in columns F - I for each activity, providing information as available and applicable. Please include the name of the country, contact information, and date.
Some activities specifically refer to all Range States, while others only apply to those where Squatina squatina is currently extant.
· Column F: Action taken / Results achieved Please provide a detailed and complete description of action(s) taken and achievements related to the result.
· Column G: Reason for no or limited action taken Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons.
· Column H: References and links Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken.
· Column I: Status of implementation Please use the drop-down menu to choose the status of implementation.
In accordance with CMS Decision 14.101 (f) and (g), the Secretariat will compile all reports from Range States and prepare a brief summary and analysis. This summary will be discussed and presented at the 1st Working Group Meeting, where recommendations for the further implementation of the SSAP Angelshark Med will be developed for COP15.

## Report
Draft Reporting Template |  |  |  |  | Croatia 2025 |  |  |  | Croatia 2026
Annex to the Angelshark SSAP |  |  |  |  | [jelena.uros@mzozt.hr] [04.04.2025.] |  |  |  | [Contact details] [Date XX.XX.XXXX]
Objective 1 - Ensure appropriate species-level protection for Angelshark Squatina squatina
Result | Action | Priority | Time Scale | Parties Responsible | Action taken / Results achieved | Reason for no or limited action taken | References and links | Progress | Action taken / Results achieved | Reason for no or limited action taken | References and links | Progress
[5 empty] | Please provide a detailed and complete description of action(s) taken and achievements related to the result. | Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons. | Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken. | Please use the drop-down menu to choose the status of implementation. | Please provide a detailed and complete description of action(s) taken and achievements related to the result. | Please provide a description, if applicable, why action was not taken or implementation was incomplete, e.g. funding contraints, technical capacity, political reasons. | Please provide any references and links supporting information given in the columns Action taken or Reason for no or limited action taken. | Please use the drop-down menu to choose the status of implementation.
Appropriate species protection in line with CMS Appendix I listing, and relevant GFCM recommendations (GFCM/42/2018/2) and GFCM/44/2021/16) are enforced or introduced for Angelshark Squatina squatina*. Such protection may need to apply to both commercial and recreational fisheries (and should also consider other potential sources of anthropogenic mortality), in order to comply fully with obligations to protect CMS Appendix I listed species. Awareness programme to ensure relevant stakeholders are aware of regulations protecting Angelsharks and subsequent monitoring of compliance and enforcement, where necessary. [* and other relevant species] | 1.1 Prohibition in fisheries regulations: Secure national fisheries regulations to ensure that it is prohibited to fish for, retain, tranship, and land Angel Sharks (Squatina spp.) in support of GFCM Recommendation GFCM/42/2018/2 and GFCM/44/2021/16. Note it is important to also prohibit intentional catches of Smoothback Angelshark (Squatina 25culate) and Sawback Angelshark (Squatina aculeata) due to the difficulty to identify and distinguish between the three Angel Shark species found within the Mediterranean. | Essential | Immediate | All Range States | Pursuant to Regulation (EU) 2019/1241 (Article 10.2 and Annex 1) it is prohibited to fish for, retain on board, tranship, land, store, sell, display or offer for sale species Squatina squatina. In addition to this, species Squatina squatina and Squatina aculeata are both listed as strictly protected on national level within the Ordinance on strictly protected species (Official gazette 144/13 and 73/16). For monitoring of incidental catches and releases, on the basis of the Marine Fisheries Act (Official gazette 62/17, 130/17, 14/19, 30/23, 14/24 and 30/24) the two species of Angel sharks are listed in the Ordinance on the form, content and manner of maintaining and submission of catch data in commercial fishing at sea (Official gazette 114/2023): Smoothback Angelshark (Squatina oculata) and Angelshark (Squatina squatina). Within the Ordinance, it is stated that each incidental catch and release of live or of sensitive species has to be recorded separately. Data have to be recorded at the species level if the species can be identified (Croatian name, or FAO three-letter code if available). Species Squatina aculeata is not listed on a list of prohibithed species beacuse there are no confirmed findings in Adriatic sea. |  |  | Fully implemented
| 1.2 Species-protection: Establish national species-level protection against the deliberate killing, injuring, or taking of Angelshark. This is of particular importance for those nations where prohibited species regulations (see 1.1) only apply to commercial fishing vessels, as additional protection against other sources of potential mortality (e.g., artisanal and recreational fisheries) may be required. | Essential | Short | All Range States | The two species of Angel sharks are listed in the Croatian strictly protected species list according to the Ordinance for strictly protected species (Official Gazzette, 144/2013, 73/2016): Smoothback Angelshark (Squatina oculata) and Angelshark (Squatina squatina). The third species Sawback Angelshark (Squatina aculeata) has never been recorded in the Adriatic Sea. Those two species of Angel Sharks are protected by Croatian Nature Protection Act (Official Gazzette, 80/2013, 15/2018, 14/2019, 127/2019, 155/2023), the following actions with strictly protected species in their natural range are prohibited: all forms of intentional capture or killing, intentional disturbance, especially during breeding, rearing of young, hibernation, and migration; intentional destruction or taking of eggs and their storage, intentional destruction, damage, or removal of their developmental forms, nests, or breeding sites; damaging or destroying areas of their breeding or resting. It is prohibited to keep, transport, sell, exchange, and offer for sale or exchange of live or dead specimens from the wild of strictly protected species. |  | Project a brochure for recreational divers with the rules of conduct when meeting an Angelsharks is developed and disseminated. | Fully implemented
| 1.3 Awareness programmes: Initiate educational and awareness programmes with relevant stakeholder groups in both the fisheries sector (e.g. enforcement officials, fishing industry, fish markets) and recreational sector (e.g. recreational fishers, spearfishers, and amateur divers) as to the prohibited and/or protected status of Angelsharks With a particular focus on species identification to distinguish between the three Squatina spp., but also for classification purposes as Angelsharks are often reported as rays and not sharks. Share resources already developed by the Angel Shark Project for best practice to safely release Angelsharks if accidentally caught and the Angel Shark Sightings Map to report sightings. | Essential | Medium | Range States where Angelsharks are extant | In the scope of AS project, led by WWF Adria in Croatia, partner organizations University of Zadar, Public institution for the management of Protected Areas in the County of Zadar „Natura Jadera“ and WWF Adria, established, on a voluntary basis, a stakeholder group under the name Co-management Council for the conservation of Angelshark (Squatina squatina) in the Adriatic Sea. Co-management council is established with the objective of strengthening the role of the local community (primarily fisheries stakeholders) and institutions in the conservation of Angelshark in the Adriatic Sea through improvement of cooperation and communication between the local and scientific community, as well as Public institution for the management of Protected Areas, to contribute to the conservation of critically endangered and strictly protected species of Angelshark (S. squatina). Through this project a brochure for recreational divers with the rules of conduct when meeting an Angelsharks is developed and disseminated. The data on Angelshark catches will be shared for Angel Shark Sightings Map. Ministry in charge for fishieries published Guide for identifying and handling with the sensitive species in sea fishing. Also, fishermen are periodically trained on how to recognize and deal with incidental catches of sensitive species. | The data on Angelshark catches will be shared for Angel Shark Sightings Map after the publication of the sightings in the scientific paper. |  | Partially implemented | Awareness-raising activities are continuously implemented through direct communication with fishers during DCF onboard sampling and at landing sites. Fishers are informed about the protected status of Angelsharks, species identification, correct classification of Squatina spp., and appropriate handling and safe release in the case of accidental capture. Reporting of sightings and incidental catches is also encouraged. |  |  | Partially implemented
| 1.4 Monitoring and enforcement: Ensure that enforcement staff undertake appropriate monitoring of commercial fisheries and landings, particularly regarding those fleets that are more likely to encounter Angelsharks. Develop, or extend, national reporting framework for collating the number of inspections undertaken (by port, fleet, and month) and instances of infringement with regards to Angelsharks. | High | Ongoing | Range States where Angelsharks are extant | Monitoring and enforcement are fully in line with Control regulation in fisheries (1224/2009) and with Marine fisheries Act. |  |  | Fully implemented
Objective 2 - Identification of sites and habitats of Angelshark Squatina squatina
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
To identify former, current and potential Critical Angel Shark Areas (CASAs) and ascertain the status of Angelshark in these areas. | 2.1 Data collation: Collate national data (including both contemporary and historic sources) regarding the presence of Angelsharks Squatina squatina (and sister taxa) from relevant sources (including published studies, commercial and recreational fisheries data, fish market data, fisher and diver interviews, citizen science programmes, trawl survey data, discard observer data, museum specimens, Angelshark survey data and historical resources) to better document the contemporary and historical occurrence of Angelsharks in national waters. Such data may also be enhanced through the collection of data on the current presence of Angelshark through the use of social media. Such data could be usefully collated in a common format (see Annex II), with institutes collating national data collaborating with other national institutes in order that more robust regional data are available. The collation of comparable data for other species of Angel Shark should also be undertaken, in order to aid in the interpretation of data for Squatina squatina. The Angel Shark Sightings Map, hosted by the Angel Shark Conservation Network, is already established, open access and widely used and could be utilised for this purpose. | High | Ongoing | All Range States | Three studies, through WWF have been conducted to collect Angelshark data in Croatia: 1) Angel shark LEK case study Croatia with the objective to collect historical data as well as recent records on angelsharks catches and sightings in Croatian part of Adriatic Sea and compile them in order to build the basis for further work on protection of this critically endangered species. 2) eDNA analysis report - with the purpos of confirtmation of the presence of the Angelsharks in the Molat archipelago hotspot area. 3) Underwater visual census with the habitat mapping have been conducted in the Molat archipelago hotspot area. These studies contributed to ISRA proclamation in Croatia through IUCN Shark Specialist Group. The identification of ISRA- important areas for sharks and rays is an evidence-driven process based on the application of scientific criteria supported by the best available science. In accordance with this procedure, one area has been identified in Croatian part of the Adriatic, mainly for the angelshark, Squatina squatina - Western Virsko More https://sharkrayareas.org/e-atlas/ The occurrence of the common angel shark Squatina squatina in the Adriatic Sea // Annales. 31 (2021), 1; 37-44 |  | Attached documents: 1) Angel shark lek case study Croatia 2) eDNA analysis report 3) Underwater visual census with the habitat mapping 4) Western Virsko More ISRA | Partially implemented | National data on Angelsharks are continuously collected and updated through ongoing DCF activities, including onboard observations, landing-site monitoring and fisheries-related data collection. Additional information on the occurrence of Squatina spp. is gathered through social media channels, opportunistic observations and reports from fishers and other stakeholders. These sources contribute to documenting both contemporary occurrence and changes in distribution over time, while helping to identify new records and areas of potential importance for Angelsharks in national waters. | The data on Angelshark catches will be shared for Angel Shark Sightings Map after the publication of the sightings in the scientific paper. |  | Partially implemented
| 2.2 Habitat modelling: Based on data from action 2.1, undertake Angelshark habitat modelling in national waters and regional seas, in order to better understand and predict Critical Angel Shark Areas (CASAs), including habitats used by key life-history stages, including nursery, mating grounds, pupping and overwintering grounds. | High | Ongoing | All Range States |  | In order to conduct habitat modeling, additional data collection have to be conducted. There is a lack of data collection due to funding constraints. |  | Not addressed yet
| 2.3 Environmental DNA (eDNA) sampling: undertake eDNA sampling of appropriate areas (i.e., former, current and potential Angelshark habitats identified in 2.2) to gauge potential presence of Angelshark in the region. | Medium | Medium | All Range States | eDNA analysis report - with the purpos of confirtmation of the presence of the Angelsharks in the Molat archipelago hotspot area. | There is a lack of eDNA data collection due to funding constraints. |  | Partially implemented
| 2.4 Non-destructive site sampling: Depending on the results of 2.1, 2.2, and/or 2.3, undertake non-destructive surveys (e.g., underwater visual census) of contemporary/potential Angelshark habitat to determine whether effective non extractive field programmes could be developed in order to monitor localised populations of Angelshark. | High | Medium/Long | All Range States | Underwater visual census (UVC) with the habitat mapping have been conducted in the Molat archipelago hotspot area. | There is a lack of UVC data collection due to funding constraints. |  | Partially implemented
| 2.5 Role of current MPA network: Undertake appropriate sampling (e.g., eDNA sampling, underwater visual census) of existing Marine Protected Areas which may provide suitable habitat for Angelshark, in order to ascertain the likely presence/absence of Angelshark and the effectiveness of conservation measures in place in the current MPA network. | Medium | Long | All Range States | Three studies that have been conducted to collect Angelshark data in Croatia: 1) Angel shark lek case study Croatia, 2) eDNA analysis report and 3) Underwater visual census with the habitat mapping have all been conducted in Natura 2000 areas. However, management plans for those areas do not contain measures to adress conservation of the Angelsharks at this moment. | In order to incorporate measures for Angelshark conservation in Natura 2000 management plans, additional data have to be collected which requires additional funding. |  | Partially implemented
Objective 3 - Support and undertake scientific studies, including data collection and liaison with the fishing sectors, to improve scientific knowledge of Angelsharks Squatina squatina, including population trends
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
Improved scientific data from commercial fisheries on Angelsharks becomes available, to inform on the status of the species, pressures and enable more robust monitoring of population trends. Improved scientific data from recreational fisheries and other recreational activities on Angelsharks becomes available, to inform on the status of the species, pressures and enable more robust monitoring of population trends | 3.1 Scientific monitoring: Based on the results of 2.1, 2.2, and/or 2.3, initiate (or expand) scientific observer programmes to ensure dedicated and robust observer coverage of those commercial fleets that may interact with Angelshark, covering Angelshark habitats in order to improve contemporary data on the presence of Angelshark and their interactions with fisheries.), and associated biological information (length, gender, females that are pregnant or giving birth). | High | Medium | Range States where Angelsharks are extant | The Data collection framework is established for collection of fisheries data. Collection of data of vulnerable speciesis is included. |  |  | Fully implemented
| 3.2 Commercial fishery-dependent catch-per-unit-effort data: Improved reporting of interactions with commercial fishing fleets, including data on the numbers of Angelsharks caught, fate (discarded alive or discarded dead). Comparable data on fishing effort, especially for those fleets expected to have a higher number of interactions with Angelsharks, should also be recorded. Such work could utilise the existing reporting requirements of GFCM and potentially focus on a particular ‘reference fleet’ as a case study. | High | Short (Implementation) Ongoing (Monitoring) | Range States where Angelsharks are extant | Monitoring and enforcement are fully in line with Control regulation in fisheries (1224/2009) and with Marine fisheries Act. |  |  | Fully implemented
| 3.3 Recreational fishery: Encourage reporting of sightings to both the relevant national fisheries institute and the Angel Shark Sightings Map22. Adapt and distribute a code of conduct to safely release Angelsharks if accidentally caught (already developed by the Angel Shark Project) to the recreational fishing community. | High | Ongoing | Range States where Angelsharks are extant | New data collection framework for recreational fisheries is in the phase of public consultation. Scientific survey is conducted on yearly basis including by catch of sensitive vulnerable species. |  |  | Partially implemented | A national framework for daily electronic catch reporting has been established through the mRecFish application, including mandatory electronic reporting of incidental catches and releases of angelsharks (Squatina squatina and Squatina oculata), with phased implementation from 2027 to 2030. The scientific institute has access to the reporting database. Annual survey-based monitoring of recreational fisheries is also carried out by the responsible scientific institute. A guide for marine sport and recreational fishing has been developed, providing information on sensitive species and responsible fishing practices. |  |  | Partially implemented
| 3.4 Citizen science: Through awareness programmes developed in Action 1.3, encourage reporting of Angelshark sightings to both the relevant national fisheries institute and the Angel Shark Sightings Map22, whether amateur or commercial divers, recreational fishers or someone sighting them in a market. Adapt and share a code of conduct for scuba and snorkel23 (already developed by Angel Shark Project) with the diving community. | Medium | Ongoing | Range States where Angelsharks are extant | Project a brochure for recreational divers with the rules of conduct when meeting an Angelsharks is developed and disseminated. | Expansion of the awareness programmes developed to encourage reporting of Angelshark sightings require additional staff and funding capacities. |  | Partially implemented
| 3.5 Fishery-independent survey trends: For any areas of localised Angelshark abundance or suitable Angelshark habitat (as surveyed under Actions 2.2, 2.3 and 2.4), initiate standardised, longer-term, non-destructive monitoring programmes to understand seasonal and annual trends in the presence and relative abundance of Angelsharks. Such work could involve collaborative studies with relevant stakeholder groups (e.g., commercial fishers, recreational fishers, divers etc.). | High | Medium (Implementation) Ongoing (Monitoring) | Range States where Angelsharks are extant |  | Expansion of the fishery-independent surveys require additional staff and funding capacities. |  | Not addressed yet
| 3.6 Quantification and characterization of discarded Angelshark survival and options for minimising discard mortality: Depending on the results of Action 3.1 and 3.2, detailed studies are needed to provide more robust estimates of discard survival (at-vessel mortality and post-release mortality) of Angelsharks from commercial fleets. Such work should be undertaken in conjunction with current levels and patterns of fleet activity and should be designed in such a way that would decrease fishing mortality on Angelsharks. Such work should also identify where changes in fisher behaviour (e.g., soak times of nets) can prevent or minimise mortality of incidentally caught Angelshark. | High | Long | Range States where Angelsharks are extant |  | Quantification and characterization of discarded Angelshark survival and options for minimising discard mortality require additional staff and funding capacities. |  | Not addressed yet | Incidental catches of vulnerable species, including angelsharks, and their condition upon capture are monitored under the national scientific monitoring programme. No at-vessel mortality of angelsharks was recoreded in commercial fisheries and all recorded individuals were released alive. | No dedicated studies on post-release mortality of angelsharks have been conducted. |  | Partially implemented
| 3.7 Tagging: For any areas of localised Angelshark abundance (as surveyed under Action 2.4), consider the utility of visual and/or electronic tagging to inform on seasonality, habitat use, home range and movement. Such studies should be designed carefully and follow an ethical review process, to avoid increasing mortality. | Medium | Long | Range States where Angelsharks are extant |  | Electronic tagging of Angelsharks require additional staff and funding capacities. |  | Not addressed yet
| 3.8 Population structure and connectivity: Collect opportunistic tissue samples (e.g., from dead bycatch) and ensure appropriate longer-term archiving and storage. Subsamples of this material should be made available for scientific studies to facilitate Atlanto-Mediterranean genetic analyses to understand Angelshark connectivity in the region and global range. | Medium | Long | All Range States |  | Collection of data on population structure and connectivity of Angelsharks require additional staff and funding capacities. |  | Not addressed yet
| 3.9 Life-history studies: Depending on studies being undertaken under the Concerted Action Plan, relevant national institutes could usefully collect life-history information (length, sex, weight, maturity, collection of biological material for supporting studies, including genetic samples, stomach contents, tissue samples, and parasites). In accordance with the “no taking” rule described in CMS Article III (524) such work should only be undertaken when based on specimens of incidental dead bycatch and under authorised derogation from relevant national regulatory frameworks (see Objective 1). | Medium | Ongoing | Range States where Angelsharks are extant |  | Conducting life-history studies of Angelsharks require additional staff and funding capacities. |  | Not addressed yet
| 3.10 Longer-term, historical population dynamics: Depending on the data available (see Action 2.1), undertake analyses of longer-term population trends of Angelsharks for national waters and regional seas to understand historical population trends. | Low | Long | All Range States |  | Conducting longer-term, historical population dynamics studies of Angelsharks require additional staff and funding capacities. |  | Not addressed yet
Objective 4 - Sufficient resources secured for long-term Angelshark Squatina squatina conservation actions
Result | Action | Priority | Time Scale | Parties Responsible | Action taken | Reason if no action taken | References and links | Progress | Action taken | Reason if no action taken | References and links | Progress
Resources shall be secured on a long-term basis for the implementation of the Single Species Action Plan. | 4.1 Provide Resources: National and regional governments secure the necessary funds for the implementation of the actions at national and regional levels. Parties shall strive to provide funds to implement priority actions in the plan and financially contribute to staff time and coordination. | High | Ongoing | All Range States |  |  |  | Not addressed yet
| 4.2 Establish an international working group (IntWG) for the Mediterranean region: An IntWG will be established to coordinate and monitor the implementation of this Single Species Action Plan. | High | Ongoing | All Range States |  |  |  | Not addressed yet
| 4.3 Appraise protected areas: Expand the existing MPA network to include any identified CASAs and the effectiveness of MPA networks is continually monitored. | Medium | Long | All Range States |  |  |  | Not addressed yet | During 2026, as part of the preparation of the National Nature Restoration Plan, discussions were held on potential conservation measures for the angelshark (Squatina squatina), including proposals for the establishment of no-take zones. It was concluded that further research and consultations with relevant stakeholders, particularly fishers, are needed for the proposed areas. Therefore, restoration areas for the angelshark (Squatina squatina) are not envisaged for inclusion in the National Nature Restoration Plan for the period up to 2030. Instead, they will be considered during the revision of the Plan in 2032. |  |  | Partially implemented
Any other information |  |  |  |  | Please use this space to provide any other relevant information that was not covered by the Objectives and Actions above. |  |  |  | Please use this space to provide any other relevant information that was not covered by the Objectives and Actions above.

## Progress
Fully implemented
Partially implemented
Not addressed yet
Not relevant in my country