|  | ## CONVENTION ON ## MIGRATORY ## SPECIES | UNEP/CMS/ARG/RS1/Doc.4 12 August 2024 Original: English |
| --- | --- | --- |

## RANGE STATE MEETING ON THE

## IMPLEMENTATION AND REVISION OF

## THE INTERNATIONAL SINGLE SPECIES ACTION PLAN

## FOR THE CONSERVATION OF THE ARGALI (Ovis ammon)

## Almaty, Kazakhstan, 12-13 September 2024

## DRAFT ACTION PLAN FOR THE CONSERVATION OF THE ARGALI

(as of 12 August 2024)

DRAFT ACTION PLAN FOR THE CONSERVATION OF THE ARGALI 2025-2032

- In line with Decision 14.167 d) of the Convention on the Conservation of Migratory Species of Wild Animals (CMS) adopted at the Fourteenth Meeting of the Conference of the Parties (COP14) in Samarkand, Uzbekistan, 12-17 February 2024, the CMS Secretariat commissioned the revision of the Action Plan to streamline its activities by integrating them in the Central Asian Mammals Initiative (CAMI) Programme of Work (PoW) and developing a set of specific activities for conservation units of the species.

- Therefore, the Secretariat suggests following a different approach for the development of the Argali Action Plan for 2024-2032 than the previous Single Species Action Plan (SSAP) for 2014-2024. Cross-cutting activities concerning the species as such or other CAMI species (preliminary included in Annex 1) shall be included in the next CAMI PoW for 2026-2032, whereas this document will focus on activities of special relevance for specific conservation units of Argali.

- Conservation units can be subspecies, populations of the species or parts of populations in specific areas. This Action Plan is based on the sites identified as relevant for Argali in the report on “Mapping Transboundary Conservation Hotspots for the Central Asian Mammals Initiative” as conservation units, which are listed in the Table below.

Transboundary hotspots identified in the report “Mapping Transboundary Conservation Hotspots for the Central Asian Mammals Initiative”:

| No. | Hotspot ID as per Report | Site name | Subspecies | Geographic area | Countries |
| --- | --- | --- | --- | --- | --- |
|  | 1 | High Pamirs | Pamir Argali or Marco Polo Sheep O.a.polii | South-eastern Tajik Pamirs, Great and Little Pamir, Sarikol Pamir (Taxkorgan), Khunjerab Pass region of Karakoram | Afghanistan-China-Pakistan-Tajikistan |
|  | 25 | Western Tien Shan | Tien Shan Argali O.a.karelini | Ugam-Chatkal NNP, SSNR Chatkal, SSNR Aksu-Zhabagly, SSNR Besh Aral | Kazakhstan-Kyrgyzstan-Uzbekistan |
|  | 32 | Pamir-Alai | Pamir Argali or Marco Polo Sheep O.a.polii | Transalai and Alai ranges, Alai valley | Kyrgyzstan-Tajikistan-Uzbekistan |
|  | 14 | Khan Tengri region | Tien Shan Argali O.a.karelini | Khan Tengri massif in the Tian Shan, incl. Khan Tengri NP in Kyrgyzstan | China-Kazakhstan-Kyrgyzstan |
|  | 23 | Western Kyrgyz Range | Tien Shan Argali O.a.karelini | Kyrgyz range in Jambyl province (Kazakhstan) and Talas province (Kyrgyzstan) | Kazakhstan-Kyrgyzstan |
|  | 24 | Northern Tien Shan | Tien Shan Argali O.a.karelini | Zaili-Alatoo and Kungey-Alatoo | Kazakhstan-Kyrgyzstan |
|  | 31 | Eastern Turkestan Range | Severtzov Argali O.a.severtzovi | Hissaro-Alai system (eastern Turkestan range) | Kyrgyzstan-Tajikistan |
|  | 36 | Western Turkestan Range | Severtzov Argali O.a.severtzovi | Turkestan Range west of Shahristan | Tajikistan-Uzbekistan |
|  | 15 | Altai | Altai Argali O.a.ammon | N-Central part and SE part of Altai mountains | China-Kazakhstan-Mongolia-Russian Federation |
|  | 9 | Khangchendzonga-Sikkim Plateau | Tibet Argali O.a.hodgsoni | Khangchendzonga region, northern plateau of Sikkim and adjacent areas (Bhutan, China, India, Nepal) | China-Bhutan-India-Nepal |
|  | 10 | Western Trans-Himalaya | Tibet Argali O.a.hodgsoni | Uttarakhand (especially Gangotri NP) (India), Upper Humla valley (Nepal) and adjacent areas (China) | China-India-Nepal |
|  | 11 | Changthang and Spiti | Tibet Argali O.a.hodgsoni | Changthang plateau in Ladakh and Spiti in Himachal Pradesh with adjacent areas of northern Tibetan Plateau | China-India |
|  | 12 | Jungarian Alatau | Tien Shan Argali O.a.karelini | Jungarian Alatau, entire mountain area | China-Kazakhstan |
|  | 13 | Tarbagatay and Saur Ranges | O.a.collium or karelini | Continuous area along the China-Kazakhstan border | China-Kazakhstan |
|  | 16 | Southern Tien Shan | O.a.karelini or polii | Entire mountain range along border with China | China-Kyrgyzstan |
|  | 17 | Gobi Desert – Yin mountains | Gobi Argali O.a.darwini | Southern edges of Gobi Desert and Yin Mountains.Possibly several separate sections. | China-Mongolia |
|  | 18 | SW Gobi | Gobi Argali O.a.darwini | Gobi-Altai - Xinjiang | China-Mongolia |
|  | 19 | Jungarian Gobi | Gobi Argali O.a.darwini | Great Gobi B SPA Khovd-Xinjiang | (China)-Mongolia |
|  | 33 | Eastern Sayan | Altai Argali O.a.ammon | Tuva/Irkutsk prov. /Buryatiya - Khovsgol | Mongolia-Russian Federation |

Subspecies or populations entirely or largely restricted to one country:

- Severtzov argali O.a.severtzovi in Uzbekistan (Nurota (Nuratau) range, Oqtov (Aktau) range, Tomdi (Tamdytau) mountains)

- Karatau argali O.a.nigrimontana in Kazakhstan (Karatau range)

- Kazakhstan argali O.a.collium in the hill-lands of Kazakhstan

- Gobi argali O.a.darwini in XXX of Mongolia

INTERNATIONAL ACTION PLAN FOR THE CONSERVATION OF THE ARGALI

Goal: to maintain and restore argali populations to a favourable conservation status throughout their range, with a particular focus on transboundary populations.

| Nr. | Conservation measures | Priority | Responsibility |
| --- | --- | --- | --- |
| 1.0 | Measures affecting several or all conservation units |  |  |
| 1.1 | Develop rangeland management plans in key sites to maintain and restore intact rangelands (all) | 1 | GOs, NGOs, scientific institutions, holders of game management areas |
| 1.2 | Intensify anti-poaching in and beyond protected areas | 1 | GOs, NGOs, holders of game management areas |
| 1.3 | Strengthen the transboundary monitoring of Argali by standardizing the monitoring methods | 1 | GOs, NGOs, scientific institutions |
| 1.4 | Develop and implement monitoring programmes, conduct regular monitoring and coordinate monitoring activities with neighbouring countries (all) | 2 | GOs, NGOs, scientific institutions, holders of hunting areas |
| Specific measures for conservation units |  |  |  |
| 2.0 | 1) High Pamirs (Afghanistan, China, Pakistan, Tajikistan) |  |  |
| 2.1 | Remove or reconstruct in a wildlife-friendly manner the border fences between Tajikistan-Afghanistan and Tajikistan-China | 1 | GOs (border authorities, environmental protection authorities), advice by scientific institutions, NGOs |
| 2.2 | New fences China-Tajikistan, China-Pakistan and China-Afghanistan: limit the length of new fences and mitigate impacts of to increase connectivity, transboundary migration and range expansion (into Pakistan) for Argali. | 1 | GOs (border authorities, environmental protection authorities), advice by scientific institutions, NGOs |
| 2.3 | Start negotiations on mitigation of existing barriers | 2 | GOs, advice by scientific institutions, NGOs |
| 2.4 | Assess potential impact on Argali habitat and corridors of the infrastructure projects under the “Belt and Road Initiative” and identify necessary political intervention for avoidance, mitigation and compensation of impact. | 2 | GOs, NGOs, scientific institutions |
| 3.0 | 2) Western Tien Shan (Kazakhstan, Kyrgyzstan and Uzbekistan) |  |  |
| 3.1 | Collaborate across borders on monitoring, conservation activities and tourism development in the context of the PA network in the western Tien Shan | 1 | GOs, NGOs, scientific institutions |
| 3.2 | Conduct training for protected area staff, in particular on working with the public, law enforcement and monitoring, including application of SMART | 1 | GOs, NGOs |
| 3.3 | Assess feasibility of proposed Argali reintroduction in the Uzbekistan part of the Western Tien Shan. | 3 | GOs, NGOs, scientific institutions |
| 3.4 | Support the development of community-based wildlife watching offers including Argali through initial investment and assistance in tourism product development and marketing, ensuring the link between benefits and conservation efforts | 3 | GOs, NGOs, communities, private business |
| 3.5 | For extractive use, assign more suitable areas with potential for Argali management to community-based entities. | 3 | GOs, NGOs |
| 3.6 | Allocate hunting quotas to community-based entities managing hunting areas when Argali numbers there have reached established thresholds. | 3 | GOs, NGOs scientific institutions |
| 4.0 | - Pamir-Alai (Kyrgyzstan, Tajikistan, Uzbekistan) |  |  |
| 4.1 | Monitor grazing intensity, seasonal and spatial patterns and develop and implement restrictions, if necessary. | 1 | GOs, NGOs, scientific institutions |
| 4.2 | Strengthen community involvement in wildlife conservation: intensify anti-poaching efforts in currently neglected areas through the development of community-based wildlife management. | 1 | GOs, NGOs |
| 4.3 | For extractive use, assign more suitable areas with potential for Argali management to community-based entities. | 1 | GOs, NGOs |
| 4.4 | Allocate hunting quotas to community-based entities managing hunting areas when Argali numbers there have reached established thresholds | 2 | GOs, NGOs scientific institutions |
| 5.0 | - Khan Tengri Region (China, Kazakhstan, Kyrgyzstan) |  |  |
| 5.1 | Assess potential impact on Argali habitat and corridors of the infrastructure projects under “Belt and Road Initiative” and implement measures for avoidance, mitigation and compensation of impact. | 1 | GOs, NGOs, scientific institutions |
| 5.2 | Assess necessity and feasibility to mitigate barrier effects of existing and planned border fences, in particular between Kazakhstan and Kyrgyzstan | 1 | GOs, NGOs, scientific institutions |
| 5.3 | Develop interventions to mitigate effects of border fences on wildlife, where possible. | 1 | GOs, NGOs, scientific institutions |
| 5.4 | Involve border guards in conservation. | 1 | GOs, NGOs, scientific institutions |
| 5.5 | Prevent expansion of grazing areas. | 1 | GOs, NGOs, scientific institutions |
| 5.6 | Support development of eco-tourism and apply impact assessment procedures making sure that any planned touristic infrastructure or activities are not harmful to Argali populations and their habitat | 2 | GOs, NGOs, scientific institutions |
| 5.7 | Ensure that hunting and management in hunting concession areas are sustainable, enhance collaboration between hunting concessions and protected area administrations and conduct integrated conservation and monitoring action | 2 | private business, GOs, scientific institutions |
| 5.8 | Involve local people in management and sustainable use of Argali, where appropriate. | 2 | GOs, NGOs, scientific institutions, private business |
| 5.9 | Intensify cross-border exchange and collaboration at the level of protected areas, scientists and NGOs | 2 | GOs, NGOs, scientific institutions |
| 5.10 | Consider revision of borders, zoning and regulations of NNP Khan Tengiri for achieving better conservation of Argali and its habitats | 3 | GOs, NGOs, scientific institutions, communities, private business |
| 5.11 | Conduct transboundary assessments and monitoring of wildlife populations and habitats | 3 | GOs, NGOs, scientific institutions |
| 6.0 | - Western Kyrgyz Range (Kazakhstan, Kyrgyzstan) |  |  |
| 6.1 | Assess and monitor: Argali actual range area and population size as well as connectivity with other parts of its range area. | 1 | GOs, NGOs, scientific institutions, private business |
| 6.2 | Assess impact of livestock grazing and develop respective interventions for minimizing degradation of habitat quality for Argali, forage competition and disease transmission risk. | 1 | GOs, NGOs, scientific institutions |
| 6.3 | Improve management of hunting areas and enable local communities to develop community-based wildlife management, where possible. | 2 | GOs, NGOs |
| 6.4 | Support the development of community-based wildlife watching offers including Argali through initial investment and assistance in tourism product development and marketing, ensuring the link between benefits and conservation efforts. | 2 | GOs, NGOs, communities, private business |
| 6.5 | For extractive use, assign more suitable areas with potential for Argali management to community-based entities. | 2 | GOs, NGOs |
| 6.6 | Allocate hunting quotas to community-based entities managing hunting areas when Argali numbers there have reached established thresholds | 2 | GOs, NGOs, scientific institutions |
| 7.0 | - Northern Tien Shan (Kazakhstan, Kyrgyzstan) |  |  |
| 7.1 | Improve transboundary collaboration between protected areas, scientific organizations and NGOs in monitoring, research, conservation management and regulation of transboundary development. | 1 | GOs, NGOs, scientific institutions |
| 7.2 | Expand and consolidate zones without livestock grazing. | 1 | GOs, NGOs, scientific institutions |
| 7.3 | Support development of eco-tourism and apply impact assessment procedures making sure that any planned touristic infrastructure or activities are not harmful to Argali populations and their habitat. | 1 | GOs, NGOs, scientific institutions |
| 7.4 | Develop community-based wildlife management to prevent poaching and incentivize protection of wildlife and its habitat by local people and reduce reliance on livestock. | 1 | GOs, NGOs |
| 7.5 | Support the development of community-based wildlife watching offers including Argali through initial investment and assistance in tourism product development and marketing, ensuring the link between benefits and conservation efforts. | 2 | GOs, NGOs, communities, private business |
| 7.6 | For extractive use, where it is permitted, assign more suitable areas with potential for Argali management to community-based entities. | 2 | GOs, NGOs |
| 7.7 | Allocate hunting quotas to community-based entities managing hunting areas when Argali numbers there have reached established thresholds | 2 | GOs, NGOs scientific institutions |
| 8.0 | - Eastern Turkestan Range (Tajikistan, Uzbekistan) |  |  |
| 8.1 | Strengthen anti-poaching efforts, in particular through the development of community-based wildlife management. | 1 | GOs, NGOs |
| 8.2 | Restrict grazing to avoid pasture/land degradation and reduce competition for pasture between livestock and Argali | 1 | GOs, NGOs |
| 8.3 | Intensify and coordinate monitoring of Argali | 2 | GOs, NGOs, scientific institutions |
| 8.4 | Support the development of community-based wildlife watching offers including Argali through initial investment and assistance in tourism product development and marketing, ensuring the link between benefits and conservation efforts. | 2 | GOs, NGOs, communities, private business |
| 8.5 | Where hunting is possible, assign more suitable areas with potential for Argali management to community-based entities. | 2 | GOs, NGOs scientific institutions |
| 8.6 | Allocate hunting quotas to community-based entities managing hunting areas when Argali numbers there have reached established thresholds | 2 | GOs, NGOs scientific institutions |
| 9.0 | - Western Turkestan Range (Tajikistan-Uzbekistan) |  |  |
| 9.1 | Expand Zaamin SSNR and Zaamin National Park by annexing the adjacent north-facing slopes of the Turkestan Range. | 1 | GOs, NGOs |
| 9.2 | Restrict grazing to avoid pasture/land degradation and reduce competition for pasture between livestock and Argali | 1 | GOs, NGOs |
| 9.3 | Intensify and coordinate monitoring of Argali | 2 | GOs, NGOs, scientific institutions |
| 9.4 | Develop community-based wildlife management for the conservation of Severtzov’s Argali under consideration of transboundary management and monitoring of the population. | 2 | GOs, NGOs |
| 9.5 | Prevent trophy hunting of Argali until the population has reached sufficient size for sustainable use and suitable management and benefit sharing are in place. | 2 | GOs, NGOs |
| 9.6 | Revise Argali hunting systems or introduce hunting schemes, which ensure effective involvement of and direct benefits for local communities and conservation. | 2 | GOs, NGOs |
| 10.0 | - Altai (China, Kazakhstan, Mongolia, Russian Federation) |  |  |
| 10.1 | Remove or mitigate of border fences in critical areas. | 1 | GOs, NGOs |
| 10.2 | Restrict grazing to avoid pasture/land degradation and reduce competition for pasture between livestock and Argali | 1 | GOs, NGOs |
| 10.3 | Increase anti-poaching efforts. | 1 | GOs, NGOs |
| 10.4 | Intensify transboundary collaboration. | 2 | GOs, NGOs, scientific institutions |
| 10.5 | Implement the conservation measures of relevance for Argali recommended in the Strategy for the conservation of Snow Leopard in Russian Federation - Develop game management territories and realize measures to restore Argali populations (primarily on Chikhachev, Southern Chuisky,Tsagan-Shibetu, and Sangilen Ridges and Mongun-Taiga Massif); - Guarantee effective work by regional authorized executive agencies for wildlife protection and antipoaching enforcement against poaching of Argali. - Develop collaboration among nature conservation and legal enforcement agencies in government to strengthen the fight against illegal trade in Argali. - Create conditions for economic stimulation of game management territories in areas where the Argali is present or may reappear, including by means of attracting investment and other extra-budgetary funding sources. - Establish rigorous veterinary oversight of populations of wild and domesticated animals, conduct screenings for various infectious diseases of all dead ungulates. - Within snow leopard habitats, develop and bring into practice a system for sustainable rangeland management for free-range livestock grazing that considers the needs of wild ungulates. | 3 | GOs, NGOs, scientific institutions |
| 10.6 | Establish section of SSNR Ubsungurskaya Dolina at the Sangilen Range in Russian Federation. | 3 | GOs, NGOs |
| 11.0 | - Khangchendzonga-Sikkim Plateau (China, Bhutan, India, Nepal) |  |  |
| 11.1 | Conduct a meeting to establish transboundary collaboration, exchange of experience. | 1 | GOs, NGOs, scientific institutions |
| 11.2 | Mitigate barrier effect of border fences and border-related disturbance. | 1 | GOs, NGOs |
| 11.3 | Assess range areas, habitat use, and population connectivity, sizes and trends of Argali | 2 | GOs, NGOs, scientific institutions |
| 11.4 | Conduct research and surveys to determine conservation interventions and implement these. | 2 | GOs, NGOs, scientific institutions |
| 12.0 | - Western Trans-Himalaya (China, India, Nepal) |  |  |
| 12.1 | Enhance transboundary collaboration, exchange experience | 1 | GOs, NGOs, scientific institutions |
| 12.2 | Mitigate barrier effect of border fences | 1 | GOs, NGOs |
| 12.3 | Assess range areas, habitat use, and population sizes and trends of Argali. | 2 | GOs, NGOs, scientific institutions |
| 12.4 | Determine and implement conservation interventions. | 2 | GOs, NGOs, scientific institutions |
| 13.0 | - Changthang and Spiti (China, India) |  |  |
| 13.1 | Enhance transboundary collaboration, exchange experience and | 1 | GOs, NGOs, scientific institutions |
| 13.2 | Mitigate barrier effect of border fences. | 1 | GOs, NGOs |
| 13.3 | Assess range areas, habitat use, and population sizes and trends of target species. | 2 | GOs, NGOs, scientific institutions |
| 13.4 | Determine and implement conservation interventions specifically addressing identified threats. | 2 | GOs, NGOs, scientific institutions |
| 14.0 | - Jungarian Alatau (China, Kazakhstan) |  |  |
| 14.1 | Establish transboundary collaboration, exchange of experience | 1 | GOs, NGOs, scientific institutions |
| 14.2 | Mitigate barrier effect of border fences; address issue of parallel fences of both countries. | 1 | GOs, NGOs |
| 14.3 | Assess range areas, habitat use, and population sizes and trends of Argali. | 2 | GOs, NGOs, scientific institutions |
| 14.4 | Determine and implement conservation interventions. | 2 | GOs, NGOs, scientific institutions |
| 15.0 | - Tarbagatay and Saur Ranges (China, Kazakhstan) |  |  |
| 15.1 | Establish transboundary collaboration for exchange of information, coordinated monitoring and conservation interventions. | 1 | GOs, NGOs, scientific institutions |
| 15.2 | Enhance permeability of the border fences for Argali; address issue of parallel fences of both countries. | 1 | GOs, NGOs |
| 15.3 | Restrict livestock grazing and involve of local people in management and sustainable use of Argali. | 1 | GOs, NGOs, scientific institutions |
| 15.4 | Consider allowing limited Argali hunting in Kazakhstan | 2 | GOs, NGOs, scientific institutions |
| 15.5 | Establish incentives for Argali conservation and prevention of poaching through regulated hunting, benefiting game area holders and local people. | 2 | GOs, NGOs, scientific institutions |
| 16.0 | - Southern Tien Shan (China, Kyrgyzstan) |  |  |
| 16.1 | Assess potential impact on Argali habitat and corridors of the infrastructure projects under “Belt and Road Initiative” and implement measures for avoidance, mitigation and compensation of impact. | 1 | GOs, NGOs, scientific institutions |
| 16.2 | Assess current state and planned development of the border fences and their impact. | 1 | GOs, NGOs, scientific institutions |
| 16.3 | Develop mitigation measures for barrier effect of border fences. | 1 | GOs, NGOs |
| 16.4 | Establish seasonal and permanent grazing exclusion zones, | 1 | GOs, NGOs |
| 16.5 | Prevent poaching, in particular through community involvement in and benefit sharing from regulated hunting of Argali and Asiatic Ibex. | 2 | GOs, NGOs, scientific institutions |
| 16.6 | Assess and control impact of dogs kept by herders (herd protection dogs and hunting dogs) to reduce Argali disturbance and mortality. | 2 | GOs, NGOs, scientific institutions |
| 17.0 | - Gobi Desert – Yin mountains (China, Mongolia) |  |  |
| 17.1 | Consider fence removal proposed between Station 21 (N 43.749708°, E 111.856505°) which lies a few kilometers north of Zamyn-Uud near the border with China, and Airag (N 45.778356°, E 109.335991°) to restore animal movements | 1 | GOs, NGOs, scientific institutions |
| 17.2 | Consider leaving fencing along railways only near human settlements to prevent collisions with free ranging livestock | 1 | GOs, NGOs, scientific institutions |
| 17.3 | Restrict grazing to avoid pasture/land degradation and reduce competition for pasture between livestock and Argali | 1 | GOs, NGOs, scientific institutions |
| 17.4 | Enact veterinary measures to prevent disease transmission between Argali and livestock | 1 | GOs, NGOs, scientific institutions |
| 17.5 | Create, and/or expand livestock exclusion zones. | 1 | GOs, NGOs, scientific institutions |
| 18.0 | - SW Gobi (China, Mongolia) |  |  |
| 18.1 | Regulate grazing and restrict livestock in critical areas of the buffer zone at the boundaries of Great Gobi a Strictly Protected Area. | 1 | GOs, NGOs |
| 19.0 | - Jungarian Gobi (China, Mongolia) |  |  |
| 19.1 | Severely restrict grazing of domestic horses and reduce, or at least prevent any increase in grazing of other livestock | 1 | GOs, NGOs |
| 19.2 | Conduct studies to better understand pasture competition between the full range of wild and domestic ungulates in this area | 2 | GOs, NGOs, scientific institutions |
| 19.3 | Create transboundary wildlife corridor(s) for Argali. | 2 | GOs, NGOs, scientific institutions |
| 20.0 | - Eastern Sayan (Mongolia, Russian Federation) |  |  |
| 20.1 | Intensify transboundary collaboration. | 1 | GOs, NGOs, scientific institutions |
| 20.2 | Remove or mitigate border fences in critical areas. | 1 | GOs, NGOs, scientific institutions |
| 20.3 | Restrict grazing to avoid pasture/land degradation and reduce competition for pasture between livestock and Argali | 1 | GOs, NGOs, scientific institutions |
| 20.4 | Increase anti-poaching efforts. | 1 | GOs, NGOs, scientific institutions |
| 20.5 | Conduct status assessment of the target species with determination of conservation potential, threats and options to address these. | 2 | GOs, NGOs, scientific institutions |
| 20.6 | Implement conservation measures recommended in the Strategy for the conservation of Snow Leopard in Russian Federation as far as relevant for Argali in the conservation unit (see 10.5) | 3 | GOs, NGOs, scientific institutions |
| 20.7 | Establish a protected area in the Eastern Sayan of Russian Federation, in Mongolia in Khovsgol region protected areas are functional | 3 | GOs, NGOs, scientific institutions |
| 21.0 | - Severtzov argali O.a.severtzovi in Uzbekistan (Nurota (Nuratau) range, Oqtov (Aktau) range, Tomdi (Tamdytau) mountains |  |  |
| 21.1 | Improve the protection of Argali in the western and eastern parts of the Nuratau Range, including effective management in existing and establishment of new hunting management areas | 1 | GOs, NGOs, private business |
| 21.2 | Establish effective management of Aktau zakaznik, including development of institutional structure, management planning, implementation and enforcement of regulations | 1 | GOs, NGOs, scientific institutions, private business |
| 21.3 | Address threats related with the industrial development in the Tamdytau mountains through comprehensive assessment of Argali population, actual and potential habitat use and quality, current and predictable impact of the development and elaboration, implementation and monitoring of effectiveness of avoidance and mitigation measures. | 1 | GOs, NGOs, scientific institutions, private business |
| 21.4 | Finalize the expansion of Nuratau SSNR, adding key Argali habitat in the south of the current PA territory | 2 | GOs |
| 22.0 | - Karatau argali O.a.nigrimontana in Kazakhstan (Karatau range) |  |  |
| 22.1 | Improve the functional connectivity of the Argali habitats through identification of factors hindering movements and habitat use and addressing these, e.g. by establishment of corridors, possibly as hunting management areas, between the protected areas | 2 | GOs, NGOs, scientific institutions |
| 22.2 | Develop eco-tourism offers with integration of Argali observation in a manner benefiting the conservation work in and beyond the protected areas | 3 | GOs, NGOs, private business |
| 22.3 | Consider the development of sustainable hunting tourism as incentive for Argali conservation outside of protected areas | 3 | GOs, NGOs, scientific institutions, private business |
| 23.0 | - Kazakhstan argali O.a.collium in the hill-lands of Kazakhstan |  |  |
| 23.1 | Study the actual, past and potential connectivity and fragmentation of Argali subpopulations | 1 | NGOs, scientific institutions |
| 23.2 | Maintain and improve connectivity through appropriate means, including adequate consideration in planning of infrastructure and industrial development and improved protection | 1 | GOs, NGOs, private business |
| 23.3 | Assess the genetic diversity of small, isolated subpopulations and, where needed but connectivity for natural exchange cannot be improved, consider translocations | 2 | Scientific institutions, GOs, NGOs |
| 23.4 | Consider the development of sustainable hunting tourism as incentive for Argali conservation outside of protected areas | 2 | GOs, NGOs, scientific institutions, private business |
| 23.5 | Consider translocations of Argali for reintroduction in suitable parts of the former distribution range where recolonization by natural dispersal is not possible | 3 | GOs, NGOs, scientific institutions, private business |
| 24.0 | - Gobi argali O.a.darwini in relevant areas of Mongolia |  |  |

Annex 1

General activities from the SSAP 2014-2024 which will be integrated in CAMI POW after this meeting

(Russian version - see SSAP 2014-2024)

| Objective 1: To stabilize argali numbers and range, maintain a healthy sex/age ratio and reverse negative trends |  |  |  |  |
| --- | --- | --- | --- | --- |
| Result | Action | Priority | Time scale | Organisations responsible |
| 1.1. Poaching and other human induced mortality are reduced | 1.1.1. Implement effective anti-poaching measures addressing poaching at all levels Applicable to: All | Essential | On-going | Government agencies, Protected area managers, Hunting area managers |
|  | 1.1.2. Strengthen management capacity of trophy hunting concessions and clearly define hunting zones and seasons. Applicable to: Countries with trophy hunting programmes | Essential | On-going | Hunting area managers, CIC, Government agencies |
|  | 1.1.3. Provide relevant training and equipment for law enforcement officers, PA staff, and others. Applicable to: All | High | Medium | Government agencies, International Ranger Federation, TRAFFIC, INTERPOL, International and national NGOs |
|  | 1.1.4. Report poaching incidents to mass media. Applicable to: All | Low | Medium | CMS argali contact points, Argali Working Group (WG), NGOs |
|  | 1.1.5. Develop a confiscation policy for argali products and ensure that benefits of retailed or auctioned seized products are reinvested in argali conservation. Applicable to: All | Low | Long | Government agencies |
|  | 1.1.6. Address the threat of livestock-wildlife disease transmission through vaccination of livestock in appropriate cases, effective exclusion of livestock from PAs, health monitoring of argali and contiguous livestock populations. Applicable to: All | Medium | Long | Government veterinary agencies, hunting area managers, scientific institutions |

| 1.2. Argali is used and managed sustainably, with support of local communities | 1.2.1. Involve local communities formally in the management and sustainable use of argali and their habitat. Applicable to: All |  | Essential | Medium | Government agencies, Hunting area managers, NGOs, Development cooperation organizations |
| --- | --- | --- | --- | --- | --- |
|  | 1.2.2. Promote long-term assignment of management rights to communities. Applicable to: All |  | High | Medium | Government agencies, NGOs, Development cooperation organizations |
|  | 1.2.3. Ensure that a percentage of hunting revenues is dedicated to argali conservation Applicable to: Countries with trophy hunting programmes |  | High | Medium | Government agencies, Hunting area managers/concessions NGOs |
|  | 1.2.4. Ensure the equitable benefit sharing of revenues from trophy hunting to local communities. Applicable to: Countries with trophy hunting programmes6 |  | Essential | Medium | Government agencies, Hunting agencies, hunting area managers/concessions |
|  | 1.2.5. Promote sustainable community-based wildlife management programmes / trophy hunting programmes. Applicable to: Countries with trophy hunting programmes6 Potentially also in other areas |  | High | Medium | Hunting agencies, hunting concessions, hunting outfitters, NGOs, development cooperation organizations |
|  | 1.2.6. Ensure sustainable harvest of argali and compliance with CITES, EU regulation and the US Endangered Species Act. Applicable to: Countries with trophy hunting programmes |  | High | Medium | Law enforcement agencies, Hunting agencies, hunting concessions, scientific monitors, CITES Secretariat and argali contact points, national CITES authorities |
|  | 1.2.7. Review and where necessary strengthen legal and institutional measures concerning management of hunting areas, setting of quotas and allocation of licences and ensure their transparency. Applicable to: Countries with trophy hunting programmes7 |  | Medium | Medium | National parliaments, Hunting agencies, Hunting concessions, CIC NGOs (independent monitoring), Development cooperation organizations |
|  | 1.2.8. Coordinate the allocation of quotas in trans-boundary populations among Range States. Applicable to: Countries where trophy hunting occurs across national boundaries |  | Low | Long | Government agencies, Argali WG |
|  | 1.2.9. Training law enforcement staff in implementation of CITES regulations, identification of argali products and techniques for countering illegal trade. Applicable to: All |  | Medium | Medium | CITES Secretariat, National CITES authorities, Law enforcement agencies, TRAFFIC |
|  | 1.2.10 Discuss among all stakeholders the possibility of sustainable use of argali in countries where hunting does not exist at present. Applicable to: All, except Countries with trophy hunting programmes7 |  | Medium | Medium | Government agencies, Protected area managers, Hunting agencies, Hunting associations, CITES etc. |
| Objective 2: To maintain and restore intact argali habitat and migration routes |  |  |  |  |  |  |
| Result |  | Action | Priority | Time scale | Organisations responsible |
| 2.1. Rangelands are sustainably managed and availability and quality for argali have improved |  | 2.1.1. Develop rangeland management plans in key sites to maintain and restore intact rangelands. Applicable to: All | High | Medium | Government agencies, hunting area managers, range biologists, NGOs |
|  |  | 2.1.2. Involve local people living on and using argali habitat to improve land management and cohabitation of argali, livestock and people, including through Community Conservation Incentive Agreements. Applicable to: All | Medium | Long | Government agencies, hunting area managers, NGOs |
|  |  | 2.1.3. Monitor the effects of climate change on argali habitat and integrate mitigation measures and climate change adaptation scenarios into habitat/site management. Applicable to: All | Medium | Long | Government agencies, Herder associations,, scientific institutions NGOs |
|  |  | 2.1.4. Increase the effectiveness of protected area networks and hunting concessions for argali (including trans boundary), their coverage and interconnectivity. Applicable to: All | High | Long | Government agencies, hunting area managers, international conservation NGOs |
|  |  | 2.1.5. Provide adequate transport, equipment, and training to protected areas and rangers Applicable to: All | Essential | Short | Government agencies, NGOs |
| 2.2. Forage shortages for argali in critical areas and times of year are reduced |  | 2.2.1. Increase energy efficiency and use of alternative fuel by local households to reduce the collection of fuel wood (e.g. teresken). Applicable to: All (in particular Tajikistan for teresken) | Low | Long | Government agencies, Herder and community associations, development cooperation organizations |
|  |  | 2.2.2 Develop and implement temporal and spatial restrictions on livestock grazing to ensure adequate forage for argali during critical seasons. Applicable to: All | High | Medium | Government agencies, Herder associations, hunting area managers, NGOs |
| 2.3. Disturbance and displacement of argali are minimized |  | 2.3.1. Work with local herders to reduce the threat of guard and feral dogs preying on argali lambs. Applicable to: All | Medium | Medium | Government agencies, Herder associations |
|  |  | 2.3.2. Reduce or prevent disturbance at key sites from livestock herding, poaching and hunting, mining, and recreational activities through zoning, compensatory payments and other site management measures. Applicable to: All | Medium | Medium | Government agencies, |
| 2.4. Negative impacts of mining and infrastructure development are minimized and mitigated |  | 2.4.1. Ensure Environmental Impact Assessments / Strategic Environmental Assessments are conducted rigorously and transparently. Applicable to: All | High | Long | Government agencies, IFC, consultancy companies |
|  |  | 2.4.2. Ensure compliance with International Finance Corporation (IFC) Performance Standard 6 to reduce the negative impact on biodiversity of infrastructure developments and apply appropriate suitable mitigation measures. Applicable to: All | High | Long | Government agencies, IFC, consultancy companies |
|  |  | 2.4.3. Improve connectivity by removing barriers between populations and migration corridors, and if removal is not possible, by adjusting infrastructure (e.g. fences) to make it permeable for argali. Applicable to: All | High | Long | Government agencies. , Border agencies, customs agencies, NGOs |
| 2.5. Conservation management and international cooperation especially for trans-boundary populations are maximized |  | 2.5.1. Increase the capacity of protected area and hunting area managers to monitor and sustainably manage argali populations through training. Applicable to: All | High | Medium | Government agencies, scientific institutions, INGOs |
|  |  | 2.5.2. Engage international agencies that provide common platforms for knowledge sharing and best practices. Applicable to: All | Medium | Long | INGOs, Development cooperation organizations |
|  |  | 2.5.3. Facilitate transboundary activities including information exchange on trade and use, joint law enforcement and anti-poaching activities. penetration of border fences, transboundary monitoring & research, communication and other actions related to wildlife diseases and transboundary protected areas. Applicable to: 1-19 | Medium | Medium | Government agencies, INGOs, CMS. TRAFFIC |
|  |  | 2.5.4. Establish data sharing protocols and regularly submit information to the Action Plan coordinator. Applicable to: All | Medium | Medium | Argali WG |
| Objective 3: To fill knowledge and information gaps |  |  |  |  |  |  |
| Result | Action |  | Priority | Time scale | Organisations responsible |
| 3.1. Sufficient information on argali status, trends, ecology and management is available to all stakeholders | 3.1.1. Review different census methods, and methodologies for reliable population monitoring of argali. Applicable to: All |  | High | Medium | Argali WG, IUCN SSC Caprinae SG, Universities, scientific institutions |
|  | 3.1.2. Develop a best-practice manual for argali monitoring using standardised techniques and promote its use in all Range States. Applicable to: All |  | High | Medium | Argali WG, IUCN SSC Caprinae SG, Universities, scientific institutions |
|  | 3.1.3. Implement robust monitoring programs for all argali populations. Applicable to: All |  | High | Medium | Argali WG, IUCN SSC Caprinae SG, Universities, scientific institutions |
|  | 3.1.4. Monitor and study argali and its habitat to improve management. Applicable to: All |  | High | Long | Universities, protected areas, research organizations, government agencies, scientific institutions |
|  | 3.1.5. Assess the root causes and impact of natural and human induced threats to argali populations and the key drivers of population dynamics. Applicable to: All |  | High | Long | Universities, protected areas, research organizations, government agencies, scientific institutions |
|  | 3.1.6. Determine national capacity needs, in terms of human resources, knowledge and facilities. Applicable to: All |  | Medium | Long | Government agencies, INGOs |
|  | 3.1.7. Establish a group of management and monitoring experts from different countries and stakeholder groups to inform sound management and steer Action Plan implementation. Applicable to: All |  | High | On-going | Argali WG, CMS |
|  | 3.1.8. Organize training, workshops and joint monitoring missions for management staff and scientists as well as local people. Applicable to: All |  | Medium | Medium | Government agencies, INGOs |
|  | 3.1.9. Compile a shared data pool with available information on argali ecology and harvest indicating major knowledge gaps and research needs in different languages. Applicable to: All |  | Medium | Medium | Argali WG |
|  | 3.1.10. Carry out a thorough genetic analysis to clarify the taxonomy of argali. Applicable to: All |  | Medium | Medium | Universities, scientific institutions |
| Objective 4: To ensure effective implementation of the action plan |  |  |  |  |  |  |
| Result | Action |  | Priority | Time scale | Organisations responsible |
| ### 4.1. An implementation mechanism is established | 4.1.1. Develop National Action Plans for argali and integrate these into National Biodiversity Strategy and Action Plans. Applicable to: All |  | High | Short | Government agencies, scientific institutions |
|  | 4.1.2. Conduct periodic meetings of Range States to share experiences, evaluate success and adapt management plans accordingly. Applicable to: All |  | Low | Long | CMS, Argali WG |
|  | 4.1.3. Establish a dedicated argali page using the CMS website and a mailing list to facilitate information sharing and coordination of joint activities. Applicable to: All |  | High | Short | Argali WG, GIZ CMS |
|  | 4.1.4. Designate national lead agency and argali contact points responsible for coordinating argali conservation and management policy and implementation of the action plan in each Range State. Applicable to: All |  | Essential | On-going / Completed | Government agencies, CMS |
|  | 4.1.5. Identify a suitable mechanism for the coordination and revision of the Action Plan implementation activities including developing terms of reference for the argali working group. Applicable to: All |  | Essential | On-going | CMS, Argali WG, Range States, NGOs |
|  | 4.1.6. Establish a formal cooperation agreement or Memorandum of Understanding on argali among Range States. Applicable to: All |  | High | On-going | CMS, Range States |
|  | 4.1.7. Submit Range State monitoring data every two years for publication on the CMS argali web page. Applicable to: All |  | Medium | Medium | Argali WG, CMS |
|  | 4.1.8. Secure funding for sustainable financing of Action Plan activities. Applicable to: All |  | Essential | Long | Government agencies, CMS, NGOs |
|  | 4.1.9. Review and adapt or revise the action plan at regular intervals. Applicable to: All |  | Essential | Medium | Government agencies, CMS, NGOs |

https://www.cms.int/sites/default/files/document/Argali_SSAP_final_English.pdf

Priority for implementing within 6 years: 1 – high (high importance and urgency for solving conservation issues affecting the animals and their habitat now). 2 - medium (necessary for stabilization of numbers within 3-5 years). 3 -low (will contribute to population restoration, but is not urgently needed).

Modified for relevance for Argali. Strategy available at:

https://www.researchgate.net/publication/312300067_STRATEGY_for_snow_leopard_conservation_in_the_Russian_Federation [accessed Aug 08 2024].

As of 2024, range countries with current trophy hunting programmes are Kyrgyzstan, Mongolia, Tajikistan and Uzbekistan.

As of 2024, range countries with current trophy hunting programmes are Kyrgyzstan, Mongolia, Tajikistan and Uzbekistan.

As of 2024, range countries with current trophy hunting programmes are Kyrgyzstan, Mongolia, Tajikistan and Uzbekistan.